## Sheet1
Number | Site | Lift | Title | Type | Status | BIC Contact | Reason | Date | Last Edit By | Last Edit Date | Record Identifier | Created By
8153 |  |  | AQ0216 CAR COMM test HVAC DEF | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2016-09-27 | Zosimo Correa | 2016-09-27 11:56 | 15100- Expansion Locks Atlantic | Zosimo Correa
8152 |  |  | AQ0215 CAR Tripping Hazard Safe DEF | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2016-09-23 | Zosimo Correa | 2016-09-23 11:17 | 15100- Expansion Locks Atlantic | Zosimo Correa
8151 |  |  | VOID | Corrective Action Request | Void | No Ball in Court | Construction Deficiency |  | Abdiel Santos | 2016-12-21 09:47 | 15100- Expansion Locks Atlantic | Zosimo Correa
8151 |  |  | VOID | Corrective Action Request | New Item | J Castro |  |  | Maria Elena Navarro | 2016-05-09 17:50 | 15200- Expansion Locks Pacific | Maria Elena Navarro
8150 |  |  | AM2551 CAR CB Damaged cards | Corrective Action Request | Open | Javier Barrera | Quality Mgt Sys | 2016-02-18 | Monica Oviedo | 2016-02-18 10:42 | 15100- Expansion Locks Atlantic | Monica Oviedo
8149 |  |  | AM2551 CAR CB Damaged cards | Corrective Action Request | Open | Javier Barrera | Quality Mgt Sys | 2016-02-18 | Monica Oviedo | 2016-02-18 10:30 | 15100- Expansion Locks Atlantic | Monica Oviedo
8148 |  |  | AM2551 CAR CB Damaged cards | Corrective Action Request | Open | Javier Barrera | Quality Mgt Sys | 2016-02-18 | Monica Oviedo | 2016-02-18 10:29 | 15100- Expansion Locks Atlantic | Monica Oviedo
8147 |  |  | AM2551 CAR CB Damaged cards | Corrective Action Request | Open | Javier Barrera | Quality Mgt Sys | 2016-02-18 | Monica Oviedo | 2016-02-18 10:26 | 15100- Expansion Locks Atlantic | Monica Oviedo
8146 |  |  | PQ0020 CAR Lack of Electronical Doc | Corrective Action Request | Closed | NO BIC-GUPC | Administrative | 2010-07-28 | Luz Arosemena | 2016-01-22 12:01 | 15200- Expansion Locks Pacific | Luz Arosemena
8145 |  |  | PQ0019 CAR Def on Doc Stamping | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2010-01-28 | Luz Arosemena | 2016-01-22 12:03 | 15200- Expansion Locks Pacific | Luz Arosemena
8144 |  |  | AM2549 CAR EIASA Equip with dust | Corrective Action Request | Open | Javier Barrera | Quality Mgt Sys | 2015-12-14 | Zosimo Correa | 2015-12-14 15:01 | 15100- Expansion Locks Atlantic | Zosimo Correa
8143 |  |  | AM2547 CAR INDRA Equip with dust | Corrective Action Request | Open | Javier Barrera | Quality Mgt Sys | 2015-12-14 | Zosimo Correa | 2015-12-14 14:32 | 15100- Expansion Locks Atlantic | Zosimo Correa
8142 |  |  | AM2546 CAR SELEX Equip with dust | Corrective Action Request | Closed | Javier Barrera | Quality Mgt Sys | 2015-12-14 | Abdiel Santos | 2016-12-21 11:09 | 15100- Expansion Locks Atlantic | Zosimo Correa
8141 |  |  | AM2544 CAR MCB FM200 Paint DEF | Corrective Action Request | Open | Javier Barrera | Quality Mgt Sys | 2015-12-14 | Zosimo Correa | 2015-12-14 14:06 | 15100- Expansion Locks Atlantic | Zosimo Correa
8140 |  |  | AM2542 CAR Elev Equip not prop stor | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2015-12-10 | Maylin Moreno | 2016-06-07 11:37 | 15100- Expansion Locks Atlantic | Zosimo Correa
8139 |  |  | AM2538 CAR DPD Hydro Test Criteria | Corrective Action Request | Open | Fernando Dominguez | Quality Mgt Sys | 2015-12-10 | Zosimo Correa | 2015-12-10 10:51 | 15100- Expansion Locks Atlantic | Zosimo Correa
8138 |  |  | AM2537 CAR Commisioning HPU V06 DEF | Corrective Action Request | Open | Javier Barrera | Quality Mgt Sys | 2015-12-10 | Zosimo Correa | 2015-12-10 10:32 | 15100- Expansion Locks Atlantic | Zosimo Correa
8137 |  |  | AM2534 CAR Auditel MV Cable INS Doc | Corrective Action Request | Open | Javier Barrera | Quality Mgt Sys | 2015-12-10 | Zosimo Correa | 2015-12-10 10:11 | 15100- Expansion Locks Atlantic | Zosimo Correa
8136 |  |  | AM2539 CAR MCC Inst not Folllowing | Corrective Action Request | Open | Javier Barrera | Quality Mgt Sys | 2015-11-04 | Zosimo Correa | 2015-11-04 10:34 | 15100- Expansion Locks Atlantic | Zosimo Correa
8135 |  |  | AQ0214 CAR Fine Agg from new source | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2015-08-04 | Zosimo Correa | 2016-09-27 09:22 | 15100- Expansion Locks Atlantic | Zosimo Correa
8134 |  |  | AQ0195 CAR WWTP 1&2 Without RFC DRW | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2015-07-18 | Zosimo Correa | 2015-12-10 09:33 | 15100- Expansion Locks Atlantic | Zosimo Correa
8133 |  |  | AM2536 CAR PCS Without ITP Approved | Corrective Action Request | Open | Kelvin Arteaga | Quality Mgt Sys | 2015-07-17 | Zosimo Correa | 2015-07-17 15:20 | 15100- Expansion Locks Atlantic | Zosimo Correa
8132 |  |  | PE8070 CAR- Lack of MSDS | Corrective Action Request | Closed | Enrique Knoop | Environmental Situation | 2015-07-14 | Martin Morales | 2016-08-19 11:18 | 15200- Expansion Locks Pacific | Alicia Villalobos
8131 |  |  | PE8069 CAR-WWTP2 noncompliant | Corrective Action Request | Closed | Werner Verbrugge | Environmental Situation | 2015-07-14 | Marta Small | 2015-08-27 13:57 | 15200- Expansion Locks Pacific | Alicia Villalobos
8130 |  |  | PE8038 CAR Filtration Sec. Contain. | Corrective Action Request | Closed | Werner Verbrugge | Environmental Situation | 2011-11-18 | Marta Small | 2015-08-27 13:58 | 15000- Expansion Locks | Alicia Villalobos
8129 |  |  | PM2527 CAR SAMPOL - CQP follow up | Corrective Action Request | Closed | Sergio Garcia | Quality Mgt Sys | 2015-07-13 | Ian Barria | 2016-09-06 14:31 | 15200- Expansion Locks Pacific | Luz Arosemena
8128 |  |  | PM2526 CAR HSH - WPR follow up | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2015-07-13 | Luz Arosemena | 2015-07-22 11:38 | 15200- Expansion Locks Pacific | Luz Arosemena
8127 |  |  | PQ0134 CAR MRB3 - Telecom ROOM 1 | Corrective Action Request | Closed | Rafael Sarmiento | Construction Deficiency | 2015-07-07 | Ian Barria | 2016-09-06 14:37 | 15200- Expansion Locks Pacific | Luz Arosemena
8126 |  |  | PQ0133 CAR SELEX QMS Docs | Corrective Action Request | Closed | Rafael Sarmiento | Quality Mgt Sys | 2015-07-07 | Ian Barria | 2016-09-06 14:40 | 15200- Expansion Locks Pacific | Luz Arosemena
8125 |  |  | AQ0213 CAR Plant B Without QMS doc | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2015-07-06 | Maylin Moreno | 2016-02-10 12:03 | 15100- Expansion Locks Atlantic | Zosimo Correa
8124 |  |  | AM2532 CAR SAT 3 without QMS Doc | Corrective Action Request | Closed | GUPC Doc Control | Construction Deficiency | 2015-06-26 | Abdiel Santos | 2016-12-21 10:39 | 15000- Expansion Locks | Zosimo Correa
8123 |  |  | PQ0124 CAR Pipe Inst Calib Certific | Corrective Action Request | Closed | NO BIC-GUPC | Construction Deficiency | 2015-06-26 | Luz Arosemena | 2015-07-20 11:28 | 15200- Expansion Locks Pacific | Lorely Rivera
8122 |  |  | PM2524 CAR QA/QC Documentation | Corrective Action Request | Closed | Rafael Sarmiento | Quality Mgt Sys | 2015-06-19 | Ian Barria | 2016-09-06 14:25 | 15200- Expansion Locks Pacific | Luz Arosemena
8121 |  |  | PQ0131 CAR Gatun Cofferdam Drawing | Corrective Action Request | Closed | NO BIC-GUPC | Construction Deficiency | 2015-06-19 | Luz Arosemena | 2015-08-11 15:38 | 15200- Expansion Locks Pacific | Luz Arosemena
8120 |  |  | PQ0130 CAR MRB1 QMS Documentation | Corrective Action Request | Closed | Rafael Sarmiento | Quality Mgt Sys | 2015-06-19 | Ian Barria | 2016-09-07 14:15 | 15200- Expansion Locks Pacific | Luz Arosemena
8119 |  |  | PQ0129 CAR Disposal No Name Hill | Corrective Action Request | Closed | NO BIC-GUPC | Construction Deficiency | 2015-06-19 | Lorely Rivera | 2015-09-11 11:42 | 15200- Expansion Locks Pacific | Luz Arosemena
8118 |  |  | PQ0128 CAR Super Disposal Validatio | Corrective Action Request | Terminated | Jorge Perez Blanco | Construction Deficiency | 2015-06-19 | Lorely Rivera | 2016-08-23 08:39 | 15200- Expansion Locks Pacific | Luz Arosemena
8117 |  |  | AM2533 CAR Bushings Miss in Condu | Corrective Action Request | Open | Javier Barrera | Quality Mgt Sys | 2015-06-12 | Tamira Baird | 2015-09-04 14:53 | 15100- Expansion Locks Atlantic | Mayra Santos
8116 |  |  | AM2535 CAR PCS inst without QMS | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2015-06-12 | Maylin Moreno | 2016-06-07 11:47 | 15100- Expansion Locks Atlantic | Mayra Santos
8115 |  |  | PQ0125 CAR MRB5 Missing Ducts | Corrective Action Request | Closed | NO BIC-GUPC | Construction Deficiency | 2015-05-25 | Luz Arosemena | 2015-07-15 15:56 | 15200- Expansion Locks Pacific | Luz Arosemena
8114 |  |  | AM2531 CAR Corrosion HSI Elements | Corrective Action Request | Closed | No Ball in Court | Other | 2015-05-21 | Armando Quintero | 2016-06-01 10:20 | 15100- Expansion Locks Atlantic | Zosimo Correa
8113 |  |  | AQ0212 CAR Blasting Works Without | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2015-05-12 | Maylin Moreno | 2016-02-10 11:51 | 15100- Expansion Locks Atlantic | Zosimo Correa
8112 |  |  | PM2522 CAR LV Cable Instalation MCB | Corrective Action Request | Closed | Rafael Sarmiento | Construction Deficiency | 2015-05-12 | Martin Morales | 2016-09-20 09:05 | 15200- Expansion Locks Pacific | Luz Arosemena
8111 |  |  | PM2521 CAR LV Inst. Handover | Corrective Action Request | Terminated | Rafael Sarmiento | Construction Deficiency | 2015-05-12 | Lorely Rivera | 2016-08-23 08:53 | 15200- Expansion Locks Pacific | Luz Arosemena
8110 |  |  | PQ0126 CAR Handover area protection | Corrective Action Request | Terminated | Andrea Sesenna | Construction Deficiency | 2015-05-12 | Lorely Rivera | 2016-08-23 08:47 | 15200- Expansion Locks Pacific | Luz Arosemena
8109 |  |  | PQ0122 CAR Fill & Spreading Def | Corrective Action Request | Closed | NO BIC-GUPC | Construction Deficiency | 2015-04-29 | Lorely Rivera | 2015-10-09 13:24 | 15200- Expansion Locks Pacific | Luz Arosemena
8108 |  |  | AQ0211 CAR SSC Water Blasting DEF | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2015-04-16 | Armando Quintero | 2016-06-01 10:03 | 15100- Expansion Locks Atlantic | Zosimo Correa
8107 |  |  | PQ0121 CAR Mandrel Test | Corrective Action Request | Closed | NO BIC-GUPC | Construction Deficiency | 2015-04-14 | Luz Arosemena | 2015-08-03 16:58 | 15200- Expansion Locks Pacific | Luz Arosemena
8106 |  |  | AQ0210 CAR A9 with fiber not appro | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2015-04-14 | Zosimo Correa | 2016-09-23 10:26 | 15100- Expansion Locks Atlantic | Zosimo Correa
8105 |  |  | PQ0120 CAR MCC Rooms Conditions | Corrective Action Request | Closed | NO BIC-GUPC | Construction Deficiency | 2015-04-13 | Luz Arosemena | 2015-07-15 16:38 | 15200- Expansion Locks Pacific | Luz Arosemena
8104 |  |  | VOID - GENERATED IN ERROR | Corrective Action Request | Void | Beltran Valls | Environmental Situation |  | Marta Small | 2015-08-27 14:31 | 15100- Expansion Locks Atlantic | Alicia Villalobos
8103 |  |  | AQ0208 CAR North Plug Exc DEF | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2015-04-04 | Marta Small | 2015-08-27 14:32 | 15100- Expansion Locks Atlantic | Zosimo Correa
8102 |  |  | AQ0207 CAR Missing RFC DRW CB works | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2015-04-01 | Mayra Santos | 2016-05-31 16:33 | 15100- Expansion Locks Atlantic | Zosimo Correa
8101 |  |  | AQ0206 CAR Access Roads QMS Failure | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2015-03-17 | Zosimo Correa | 2015-06-02 08:42 | 15100- Expansion Locks Atlantic | Zosimo Correa
8100 |  |  | AQ0205 CAR WSB Acc Roads QMS fail | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2015-03-16 | Zosimo Correa | 2015-06-02 08:36 | 15100- Expansion Locks Atlantic | Zosimo Correa
8099 |  |  | AQ0204 CAR HML QMS Failure | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2015-03-16 | Zosimo Correa | 2015-06-02 08:22 | 15100- Expansion Locks Atlantic | Zosimo Correa
8098 |  |  | AM2530 CAR Grinding on lintels Culv | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2015-03-13 | Marta Small | 2015-08-27 14:39 | 15100- Expansion Locks Atlantic | Zosimo Correa
8097 |  |  | PQ0117 CAR WSB1-DW-03 QC System | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2015-02-21 | Lorely Rivera | 2016-07-06 11:03 | 15200- Expansion Locks Pacific | Luz Arosemena
8096 |  |  | PQ0116 CAR Dam 2W Release without | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2015-02-12 | Luz Arosemena | 2015-03-26 09:02 | 15200- Expansion Locks Pacific | Lorely Rivera
8095 |  |  | AQ0203 CAR Fail to comply SOP11 LH4 | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2015-02-09 | Marta Small | 2015-08-27 14:40 | 15100- Expansion Locks Atlantic | Zosimo Correa
8094 |  |  | AQ0202 CAR Build Finishes QMS fail | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2015-02-02 | Mayra Santos | 2016-05-31 11:07 | 15100- Expansion Locks Atlantic | Zosimo Correa
8093 |  |  | AQ0201 CAR A5 Mix Design Not Appro | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2015-02-02 | Marta Small | 2015-08-27 14:42 | 15100- Expansion Locks Atlantic | Zosimo Correa
8092 |  |  | PQ0114 CAR APP Precast Beam Deck QA | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2015-01-30 | Lorely Rivera | 2015-08-21 15:02 | 15200- Expansion Locks Pacific | Luz Arosemena
8091 |  |  | PQ0115 CAR Incident MRB1 Drive M. | Corrective Action Request | Closed | NO BIC-GUPC | Safety & Health Issue | 2015-01-28 | Luz Arosemena | 2015-07-14 11:19 | 15200- Expansion Locks Pacific | Luz Arosemena
8090 |  |  | AE8059-CAR Access to Gatun Cemetery | Corrective Action Request | Closed | Beltran Valls | Environmental Situation | 2015-01-23 | Marta Small | 2015-08-27 14:43 | 15100- Expansion Locks Atlantic | Luis Villarreal
8089 |  |  | AQ0200 CAR Compression Column inst. | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2015-01-10 | Zosimo Correa | 2015-03-23 16:13 | 15100- Expansion Locks Atlantic | Abdiel Santos
8088 |  |  | PQ0113 CAR WSB Cut-off Wall QMS | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2015-01-08 | Luz Arosemena | 2015-03-27 10:02 | 15200- Expansion Locks Pacific | Luz Arosemena
8087 |  |  | PQ0109 CAR Survey Procedure | Corrective Action Request | Closed | Rafael Sarmiento | Quality Mgt Sys | 2014-12-30 | Martin Morales | 2016-08-19 10:14 | 15200- Expansion Locks Pacific | Luz Arosemena
8086 |  |  | PQ0111 CAR APP-OW-P18 QMS System | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2014-12-29 | Luz Arosemena | 2015-03-26 09:04 | 15200- Expansion Locks Pacific | Luz Arosemena
8085 |  |  | PQ0110 CAR Electical Piles MRB1 | Corrective Action Request | Closed | Kurt Zwanenepoel | Construction Deficiency | 2014-12-29 | Ian Barria | 2016-09-07 14:07 | 15200- Expansion Locks Pacific | Luz Arosemena
8084 |  |  | AM2526 CAR Inst of Gate in Recess 4 | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-12-15 | Zosimo Correa | 2015-06-22 14:20 | 15100- Expansion Locks Atlantic | Abdiel Santos
8083 |  |  | PQ0112 CAR CB-HVAC QMS Process | Corrective Action Request | Closed | Kurt Zwanenepoel | Quality Mgt Sys | 2014-12-18 | Martin Morales | 2016-08-23 14:39 | 15200- Expansion Locks Pacific | Lorely Rivera
8082 |  |  | PM2517 CAR Gate Embeds RFC Drawings | Corrective Action Request | New Item | Rafael Sarmiento | Quality Mgt Sys | 2014-12-17 | Luz Arosemena | 2014-12-29 10:57 | 15200- Expansion Locks Pacific | Luz Arosemena
8081 |  |  | AM2525 CAR SAT1 Test Without QMS | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-12-12 | Zosimo Correa | 2015-06-22 13:39 | 15100- Expansion Locks Atlantic | Zosimo Correa
8080 |  |  | PQ0108 CAR Sub Drainage System QMS | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2014-12-10 | Luz Arosemena | 2015-03-26 15:44 | 15200- Expansion Locks Pacific | Luz Arosemena
8079 |  |  | AQ0199 CAR Concrete Temp. Clarific. | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-11-20 | Zosimo Correa | 2015-02-25 15:58 | 15100- Expansion Locks Atlantic | Abdiel Santos
8078 |  |  | AQ0198 CAR Backfill Test Frequency | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-11-20 | Zosimo Correa | 2014-12-11 11:33 | 15100- Expansion Locks Atlantic | Abdiel Santos
8077 |  |  | AQ0197 CAR Missing RFC DRWs for CU1 | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-11-19 | Zosimo Correa | 2015-03-23 15:39 | 15100- Expansion Locks Atlantic | Abdiel Santos
8076 |  |  | AQ0196 CAR Formwork Removal before | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-11-17 | Zosimo Correa | 2015-01-21 15:58 | 15100- Expansion Locks Atlantic | Abdiel Santos
8075 |  |  | AM2524 CAR Storage Condition Bosch | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-10-15 | Zosimo Correa | 2015-01-24 11:44 | 15100- Expansion Locks Atlantic | Abdiel Santos
8074 |  |  | AQ0194 CAR - Manholes with Debris. | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-10-07 | Zosimo Correa | 2015-01-21 15:54 | 15100- Expansion Locks Atlantic | Abdiel Santos
8073 |  |  | AQ0193 CAR SMC A3P Low Break Result | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-10-07 | Zosimo Correa | 2015-03-17 15:40 | 15100- Expansion Locks Atlantic | Abdiel Santos
8072 |  |  | AM2522 CAR Repair Aft. Mandrel Test | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-08-19 | Zosimo Correa | 2015-02-19 10:16 | 15100- Expansion Locks Atlantic | Abdiel Santos
8071 |  |  | AM2523 CAR Stora. Condit. EM Wareh. | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-09-25 | Abdiel Santos | 2014-10-15 10:37 | 15100- Expansion Locks Atlantic | Abdiel Santos
8070 |  |  | AQ0192 CAR QMS Fail Liner Panel Ins | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-09-25 | Zosimo Correa | 2015-02-25 16:07 | 15100- Expansion Locks Atlantic | Abdiel Santos
8069 |  |  | AE8058-CAR HazMat in buildings | Corrective Action Request | Closed | Julio Achiaga | Environmental Situation | 2014-08-27 | Marta Small | 2015-08-27 14:45 | 15100- Expansion Locks Atlantic | Alicia Villalobos
8068 |  |  | PQ0107 CAR Duct Bank & EMH QMS | Corrective Action Request | Closed | Andrea Sesenna | Quality Mgt Sys | 2014-08-27 | Martin Morales | 2016-08-23 09:05 | 15200- Expansion Locks Pacific | Luz Arosemena
8067 |  |  | PQ0106 CAR Inlet AS Bored Piles QMS | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2014-08-27 | Lorely Rivera | 2014-10-28 09:25 | 15200- Expansion Locks Pacific | Luz Arosemena
8066 |  |  | PQ0104 CAR Chamber Grouting QMS | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2014-08-27 | Lorely Rivera | 2014-10-28 09:23 | 15200- Expansion Locks Pacific | Luz Arosemena
8065 |  |  | AM2521 CAR WSB Underdrainage System | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-08-18 | Zosimo Correa | 2014-12-11 11:11 | 15100- Expansion Locks Atlantic | Abdiel Santos
8064 |  |  | AQ0190 CAR WPR-Second Stage Concre. | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-07-28 | Abdiel Santos | 2014-10-24 14:26 | 15100- Expansion Locks Atlantic | Abdiel Santos
8063 |  |  | AM2519 CAR FPW System Followup Doc. | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-07-10 | Abdiel Santos | 2014-10-27 14:51 | 15100- Expansion Locks Atlantic | Abdiel Santos
8062 |  |  | AM2518 CAR PWD System Followup Doc. | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-07-07 | Abdiel Santos | 2014-10-27 14:38 | 15100- Expansion Locks Atlantic | Abdiel Santos
8061 |  |  | AM2517 CAR DPD System Followup Doc. | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-07-07 | Zosimo Correa | 2014-12-15 15:48 | 15100- Expansion Locks Atlantic | Abdiel Santos
8060 |  |  | AM2516 CAR DR System followup doc. | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-07-07 | Armando Quintero | 2016-06-01 09:57 | 15100- Expansion Locks Atlantic | Abdiel Santos
8059 |  |  | AM2515 CAR Sor System followup doc. | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-07-10 | Armando Quintero | 2016-06-01 09:53 | 15100- Expansion Locks Atlantic | Abdiel Santos
8058 |  |  | AM2514 CAR - Welding Recess Panels | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-07-07 | Zosimo Correa | 2015-04-08 16:14 | 15100- Expansion Locks Atlantic | Abdiel Santos
8057 |  |  | AQ0191 CAR - Structural Steel Logis | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-06-19 | Zosimo Correa | 2014-11-17 14:30 | 15100- Expansion Locks Atlantic | Abdiel Santos
8056 |  |  | PM2516 CAR Ductbank RFC Drawings | Corrective Action Request | Void | Rafael Sarmiento | Construction Deficiency | 2014-06-27 | Lorely Rivera | 2016-08-23 08:25 | 15200- Expansion Locks Pacific | Karlos Azuz
8055 |  |  | AM2513 CAR Pad Mounted Transformer | Corrective Action Request | Open | Michele Chiesa | Construction Deficiency | 2014-06-23 | Zosimo Correa | 2014-10-27 11:34 | 15100- Expansion Locks Atlantic | Abdiel Santos
8054 |  |  | AM2512 CAR - Survey Incongruence | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-06-19 | Abdiel Santos | 2014-08-25 16:04 | 15100- Expansion Locks Atlantic | Abdiel Santos
8053 |  |  | AQ0189 CAR Missing RFCDRW/Pipe Inst | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-06-12 | Abdiel Santos | 2014-08-21 13:57 | 15100- Expansion Locks Atlantic | Abdiel Santos
8052 |  |  | PQ0103 CAR Approach Structure QMS | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2014-06-06 | Lorely Rivera | 2014-10-28 09:23 | 15200- Expansion Locks Pacific | Luz Arosemena
8051 |  |  | PQ0102 CAR IE-M03-C01 System Def | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2014-06-06 | Lorely Rivera | 2014-10-28 09:19 | 15200- Expansion Locks Pacific | Luz Arosemena
8050 |  |  | AM2510 CAR - Storage Condition DEF | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-05-23 | Abdiel Santos | 2014-08-25 15:51 | 15100- Expansion Locks Atlantic | Abdiel Santos
8049 |  |  | AS5037 CAR Fall Protection at TRF | Corrective Action Request | Closed | No Ball in Court | Unsafe conditions | 2014-05-24 | Abdiel Santos | 2014-06-26 07:22 | 15100- Expansion Locks Atlantic | Jianey Abrahams
8048 |  |  | AQ0187 CAR QMS Fail - Duct Bank FOW | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-04-21 | Abdiel Santos | 2014-07-15 09:20 | 15100- Expansion Locks Atlantic | Abdiel Santos
8047 |  |  | AQ0186 CAR Mechanical QOR Failure | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-04-17 | Abdiel Santos | 2014-08-21 13:39 | 15100- Expansion Locks Atlantic | Abdiel Santos
8046 |  |  | AQ0185 CAR Fail in NCR 419 closure | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-04-10 | Abdiel Santos | 2014-10-15 15:03 | 15100- Expansion Locks Atlantic | Abdiel Santos
8045 |  |  | AQ0184 CAR QMS Failure Insp. MRB-4 | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-04-10 | Abdiel Santos | 2014-07-15 09:11 | 15100- Expansion Locks Atlantic | Abdiel Santos
8044 |  |  | AQ0183 CAR QMS Failure App. Struct. | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-04-07 | Abdiel Santos | 2014-07-08 14:13 | 15100- Expansion Locks Atlantic | Abdiel Santos
8043 |  |  | AM2511 CAR Valve Wheel Rust Repair | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-02-28 | Abdiel Santos | 2014-08-25 15:46 | 15100- Expansion Locks Atlantic | Abdiel Santos
8042 |  |  | AQ0180 CAR Backfill Test. Frequency | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-03-17 | Abdiel Santos | 2014-10-17 15:54 | 15100- Expansion Locks Atlantic | Abdiel Santos
8041 |  |  | AQ0181 CAR Plant Equip. Exp. Calib. | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-03-15 | Abdiel Santos | 2014-04-14 15:07 | 15100- Expansion Locks Atlantic | Abdiel Santos
8040 |  |  | PM2515 CAR Potable Water Hydrotest | Corrective Action Request | Closed | NO BIC-GUPC | Other | 2014-03-11 | Juan Rivera | 2014-05-07 17:37 | 15200- Expansion Locks Pacific | Juan Rivera
8039 |  |  | PM2512 CAR DIP Section Flooded | Corrective Action Request | Closed | NO BIC-GUPC | Construction Deficiency | 2014-01-17 | Luz Arosemena | 2015-07-21 10:57 | 15200- Expansion Locks Pacific | Martin Duran
8038 |  |  | AE8038 CAR General Services DEF | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2012-05-30 | Marta Small | 2015-08-27 14:46 | 15100- Expansion Locks Atlantic | Diana Velasco
00137 |  |  | P - 24 Inch Water Line | Noncompliance Notice | Closed | Javier Gutierrez | Construction Deficiency | 2011-06-02 | Rick Montanari | 2011-11-09 11:24 | 15200- Expansion Locks Pacific | Vielka Walters
00138 |  |  | P - Borinquen Road Maintenance | Noncompliance Notice | Closed | Juan H Wong | Safety & Health Issue | 2011-06-16 | Cecilia Ung | 2011-08-22 11:23 | 15200- Expansion Locks Pacific | Marisol Fabrega
00139 |  |  | P - WIR Process | Noncompliance Notice | Closed | Javier Gutierrez | Quality Mgt Sys | 2011-06-21 | Rick Montanari | 2011-10-24 09:54 | 15200- Expansion Locks Pacific | Marisol Fabrega
00003 |  |  | void | Noncompliance Notice | Void | Juan H Wong | Construction Deficiency | 2011-06-21 | Marisol Fabrega | 2011-06-21 13:36 | 15200- Expansion Locks Pacific | Marisol Fabrega
00002 |  |  | void | Noncompliance Notice | Void | Juan H Wong | Construction Deficiency | 2011-06-21 | Marisol Fabrega | 2011-06-21 13:35 | 15200- Expansion Locks Pacific | Marisol Fabrega
00140 |  |  | VOID P-Hazardous Storage Area | Noncompliance Notice | Void | No Ball in Court | Environmental Situation | 2011-06-24 | Lorri Cullivan | 2011-06-24 11:28 |  | Lorri Cullivan
00144 |  |  | A - Exc in Atl Ocean Access Channel | Noncompliance Notice | Closed | Mario L. Montemayor | Quality Mgt Sys | 2011-07-06 | Tamira Baird | 2012-02-17 15:08 | 15100- Expansion Locks Atlantic | Tamira Baird
00143 |  |  | A - Exc in Lower Water Savin (LLC) | Noncompliance Notice | Closed | Mario L. Montemayor | Quality Mgt Sys | 2011-07-06 | Mario Montemayor | 2011-09-01 07:37 | 15100- Expansion Locks Atlantic | Tamira Baird
8003A |  |  | PE8003 CAR GUPC Subcontractor Audit | Corrective Action Request | Closed | Rafael Sarmiento | Environmental Situation | 2014-10-29 | Luis Villarreal | 2014-10-29 16:50 | 15200- Expansion Locks Pacific | Luis Villarreal
00142 |  |  | A - Exc in Middle Water Savi (LMC) | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2011-07-06 | Mario Montemayor | 2011-09-01 14:14 | 15100- Expansion Locks Atlantic | Tamira Baird
00141 |  |  | A - Exc in Upper Water Sav Bas (LUC | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2011-07-06 | Mario Montemayor | 2011-09-01 14:13 | 15100- Expansion Locks Atlantic | Tamira Baird
00145 |  |  | P - Discharge of Sewage Treat Plant | Noncompliance Notice | Closed | Juan H Wong | Environmental Situation | 2011-07-07 | Cecilia Ung | 2011-08-25 19:21 | 15200- Expansion Locks Pacific | Vielka Walters
00147 |  |  | P - Hauling Road - Disposal No. 2 | Noncompliance Notice | Closed | Juan H Wong | Construction Deficiency | 2011-07-18 | Cecilia Ung | 2011-10-22 14:05 | 15200- Expansion Locks Pacific | Vielka Walters
5088 |  |  | PQ0099 CAR Rain Event Plan/Failure | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2014-01-08 | Luz Arosemena | 2015-07-14 11:02 | 15200- Expansion Locks Pacific | Luz Arosemena
5087 |  |  | PQ0098 CAR Weighted Average Temp | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2013-12-30 | Luz Arosemena | 2015-07-14 10:47 | 15200- Expansion Locks Pacific | Veronica Cash
5086 |  |  | AQ0178 CAR Weighted Average Temp | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2013-12-30 | Veronica Cash | 2014-02-18 14:25 | 15100- Expansion Locks Atlantic | Veronica Cash
5085 |  |  | AE8048 CAR - Mat'ls Mng't Deficieny | Corrective Action Request | Closed | Ariel Soto del Solar | Environmental Situation | 2013-12-26 | Marta Small | 2015-08-27 14:49 | 15100- Expansion Locks Atlantic | Yira Mootoo
5084 |  |  | AQ0176 CAR - 7 Day Compressive Test | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2013-12-03 | Abdiel Santos | 2014-03-10 14:37 | 15100- Expansion Locks Atlantic | Abdiel Santos
5083 |  |  | AQ0175 CAR - 37.5mm Superfine Sand | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2013-12-03 | Abdiel Santos | 2014-03-17 16:57 | 15100- Expansion Locks Atlantic | Abdiel Santos
5082 |  |  | AQ0174 CAR QMS Failure/Concrete W. | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2013-11-30 | Abdiel Santos | 2014-01-20 10:07 | 15100- Expansion Locks Atlantic | Abdiel Santos
5081 |  |  | PQ0096 CAR Builgings Corrosion Prot | Corrective Action Request | Closed | NO BIC-GUPC | Construction Deficiency | 2013-11-21 | Luz Arosemena | 2015-07-14 16:05 | 15200- Expansion Locks Pacific | Luz Arosemena
5080 |  |  | PM2510 CAR Mar Bol Storage | Corrective Action Request | Open | NO BIC-GUPC | Errors and Omissions | 2013-11-12 | Luz Arosemena | 2015-07-21 10:46 | 15000- Expansion Locks | Alberto Alonzo
5079 |  |  | AS CAR5036 - Tower Cranes Incidents | Corrective Action Request | Closed | Michele Chiesa |  | 2013-10-31 | Jianey Abrahams | 2014-05-22 13:43 | 15100- Expansion Locks Atlantic | Jianey Abrahams
5078 |  |  | AQ0172 CAR Geocomposite Inst. | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2013-10-24 | Marta Small | 2015-08-27 14:50 | 15100- Expansion Locks Atlantic | Abdiel Santos
5077 |  |  | AQ0171 CAR-Batch-Rep. Code mistake | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2013-10-21 | Marta Small | 2015-08-27 14:52 | 15100- Expansion Locks Atlantic | Abdiel Santos
5076 |  |  | AQ0170 CAR Adding Water to the pump | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2013-10-17 | Marta Small | 2015-08-27 14:52 | 15100- Expansion Locks Atlantic | Abdiel Santos
5075 |  |  | PQ0095 CAR MB01- QMS Process | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2013-08-20 | Luz Arosemena | 2015-07-14 15:55 | 15200- Expansion Locks Pacific | Luz Arosemena
5074 |  |  | AQ0169 CAR Unapproved Mix Designs | Corrective Action Request | Closed | No Ball in Court | Administrative | 2013-10-07 | Zosimo Correa | 2014-10-14 09:18 | 15100- Expansion Locks Atlantic | Abdiel Santos
5073 |  |  | AM2509 CAR Lower TrackWay CAST SEQ | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2013-10-02 | Zosimo Correa | 2015-01-28 14:58 | 15100- Expansion Locks Atlantic | Karla Jones
5072 |  |  | PQ0086 CAR QC Field Tets | Corrective Action Request | Closed | NO BIC-GUPC | Construction Deficiency | 2013-04-04 | Javier Gutierrez | 2013-10-09 10:50 | 15200- Expansion Locks Pacific | Veronica Cash
5071 |  |  | GQ0103 CAR Fail to PRVD DES & SDR | Corrective Action Request | Closed | NO BIC-GUPC | Contract Term | 2013-02-04 | Tamira Baird | 2015-09-04 15:30 | 15000- Expansion Locks | Veronica Cash
5070 |  |  | AM2508 CAR Cimolai Daily RPTS DEF | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2013-09-25 | Karla Jones | 2013-10-01 09:22 | 15100- Expansion Locks Atlantic | Karla Jones
5069 |  |  | AM2507 CAR FSE Repair Method WPR20 | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2013-09-25 | Abdiel Santos | 2014-07-15 08:52 | 15100- Expansion Locks Atlantic | Karla Jones
5068 |  |  | AE8057 CAR Unathorized Conc Washout | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2013-09-23 | Tamira Baird | 2015-09-04 15:31 | 15100- Expansion Locks Atlantic | Adrian Lee
5067 |  |  | PM2508 CAR Mandrel Test | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2013-09-17 | Luz Arosemena | 2015-07-20 11:15 | 15200- Expansion Locks Pacific | Martin Duran
5066 |  |  | PENDING TO USE | Corrective Action Request | Void | Veronica Cash |  | 2013-09-16 | Tamira Baird | 2015-09-07 08:35 |  | Veronica Cash
5065 |  |  | PQ0094 CAR Doval Building | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2013-09-16 | Luz Arosemena | 2015-07-15 16:23 | 15200- Expansion Locks Pacific | Veronica Cash
5064 |  |  | AE8049 CAR Mindi Camp | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2013-09-11 | Marta Small | 2015-08-27 14:57 | 15100- Expansion Locks Atlantic | Adrian Lee
5063 |  |  | AE8046 CAR Crushing Plant | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2013-01-31 | Marta Small | 2015-08-27 14:58 | 15100- Expansion Locks Atlantic | Adrian Lee
5062 |  |  | AS CAR5035-Suspended Scaffold Use | Corrective Action Request | Closed | Michele Chiesa |  | 2013-09-03 | Jianey Abrahams | 2013-11-02 08:28 | 15100- Expansion Locks Atlantic | Jianey Abrahams
5061 |  |  | AQ0166 CAR- Div. Walls without RFC | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2013-09-03 | Abdiel Santos | 2014-01-20 10:10 | 15100- Expansion Locks Atlantic | Abdiel Santos
5060 |  |  | PQ0088 CAR Lack of Detailed Info | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2013-08-23 | Marta Small | 2015-08-27 13:49 | 15200- Expansion Locks Pacific | Veronica Cash
5059 |  |  | PQ0081 CAR Production daily reports | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2013-08-23 | Veronica Cash | 2014-01-21 14:56 | 15200- Expansion Locks Pacific | Veronica Cash
5058 |  |  | AQ0168 CAR Lack of Detailed Info | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2013-08-23 | Veronica Cash | 2013-11-22 14:30 | 15100- Expansion Locks Atlantic | Veronica Cash
5057 |  |  | AQ0167 CAR Production daily reports | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2013-08-23 | Abdiel Santos | 2014-02-24 16:43 | 15100- Expansion Locks Atlantic | Veronica Cash
5056 |  |  | AQ0165 CAR Rebar Installation DEF | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2013-08-15 | Abdiel Santos | 2013-10-07 15:26 | 15100- Expansion Locks Atlantic | Karla Jones
5055 |  |  | AQ0164 CAR QMS FAIL Main CTRL BLD | Corrective Action Request | Closed | No Ball in Court | Administrative | 2013-08-13 | Abdiel Santos | 2013-12-03 11:39 | 15100- Expansion Locks Atlantic | Karla Jones
5054 |  |  | AQ0163 CAR QMS FAIL Machinery BLD | Corrective Action Request | Closed | No Ball in Court | Administrative | 2013-08-13 | Abdiel Santos | 2013-09-16 16:26 | 15100- Expansion Locks Atlantic | Karla Jones
5053 |  |  | VOID - GENERATED IN ERROR | Corrective Action Request | Void | NO BIC-GUPC |  | 2013-08-13 | Nayubel Cordoba | 2013-09-16 16:43 |  | Karla Jones
5052 |  |  | AM2506 CAR Mandrel Test | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2013-08-07 | Abdiel Santos | 2014-08-25 15:39 | 15100- Expansion Locks Atlantic | Maria Saenz
5051 |  |  | AS CAR5034-Safety Glasses | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2013-08-01 | Abdiel Santos | 2014-01-22 10:56 | 15100- Expansion Locks Atlantic | Jianey Abrahams
5050 |  |  | AS CAR5033-Formwork | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2013-08-01 | Abdiel Santos | 2014-10-27 15:07 | 15100- Expansion Locks Atlantic | Jianey Abrahams
5049 |  |  | GQ0107 CAR PAC MRB1 Shop Drawings | Corrective Action Request | Closed | NO BIC-GUPC | Other | 2013-08-01 | Marta Small | 2015-08-27 15:17 | 15200- Expansion Locks Pacific | Veronica Cash
5048 |  |  | AQ0162 CAR Use of SMCA3 in HSA | Corrective Action Request | Closed | No Ball in Court | Administrative | 2013-07-16 | Larry Ohrn | 2013-10-07 16:14 | 15100- Expansion Locks Atlantic | Karla Jones
5047 |  |  | AE8056 CAR Lck Hskping Silica | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2013-07-06 | Tamira Baird | 2015-09-04 15:32 | 15100- Expansion Locks Atlantic | Adrian Lee
5046 |  |  | AE8055 CAR Entrena Cocasa Area | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2013-07-06 | Gene Williams | 2015-09-04 15:32 | 15100- Expansion Locks Atlantic | Adrian Lee
5045 |  |  | PQ0085 CAR Concrete Repair Works | Corrective Action Request | Closed | Maria Baz |  | 2013-07-11 | Marta Small | 2015-08-27 15:23 | 15200- Expansion Locks Pacific | Veronica Cash
5044 |  |  | AS CAR5025-Riggers | Corrective Action Request | Closed | Michele Chiesa | Safety & Health Issue | 2012-07-15 | Jianey Abrahams | 2013-06-29 11:09 | 15100- Expansion Locks Atlantic | Jianey Abrahams
5043 |  |  | AS CAR5023-Hazcom | Corrective Action Request | Closed | Federico Accorsi | Safety & Health Issue | 2012-04-11 | Marta Small | 2015-08-27 15:24 | 15100- Expansion Locks Atlantic | Jianey Abrahams
5042 |  |  | AS CAR5032-Tecnogruas | Corrective Action Request | Closed | Michele Chiesa | Safety & Health Issue | 2013-05-24 | Marta Small | 2015-08-27 15:25 | 15100- Expansion Locks Atlantic | Jianey Abrahams
5041 |  |  | AE8054 CAR Mn Wrkshp o/w Sep | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2013-06-27 | Marta Small | 2015-08-27 15:27 | 15100- Expansion Locks Atlantic | Adrian Lee
5040 |  |  | AE8053 CAR Mn Wrkshp Illgl Rep Area | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2013-06-27 | Marta Small | 2015-08-27 15:29 | 15100- Expansion Locks Atlantic | Adrian Lee
5039 |  |  | AE8052 CAR Illgl Dschrge Dewatering | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2013-06-27 | Marta Small | 2015-08-27 15:30 | 15100- Expansion Locks Atlantic | Adrian Lee
5038 |  |  | AQ0160 CAR Rep. Hydraulic Surf | Corrective Action Request | Closed | NO BIC-GUPC | Construction Deficiency | 2013-06-22 | Veronica Cash | 2013-08-27 15:57 | 15100- Expansion Locks Atlantic | Veronica Cash
5037 |  |  | PE8068 CAR-Cylinder Handling | Corrective Action Request | Closed | Francisco Moreno | Environmental Situation | 2013-05-03 | Martin Morales | 2016-08-19 11:12 | 15200- Expansion Locks Pacific | Gonzalo Menendez
5036 |  |  | PE8067 CAR-Lack of Hazar Wast Inven | Corrective Action Request | Closed | Francisco Moreno | Environmental Situation | 2013-05-03 | Martin Morales | 2016-08-19 11:07 | 15200- Expansion Locks Pacific | Gonzalo Menendez
5035 |  |  | PE8066 CAR-Proc in Mech Workshop | Corrective Action Request | Closed | Francisco Moreno | Environmental Situation | 2013-05-03 | Martin Morales | 2016-08-19 11:02 | 15200- Expansion Locks Pacific | Gonzalo Menendez
5034 |  |  | PQ0093 CAR LE-M16 Settlement | Corrective Action Request | Closed | NO BIC-GUPC | Construction Deficiency | 2013-06-10 | Lorely Rivera | 2015-07-04 10:31 | 15200- Expansion Locks Pacific | Javier Gutierrez
5033 |  |  | PQ0092 CAR H2W-Concealed Defect Wrk | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2013-06-10 | Luz Arosemena | 2013-10-08 11:39 | 15200- Expansion Locks Pacific | Javier Gutierrez
5032 |  |  | PQ0089 CAR Water Stop Installation | Corrective Action Request | Closed | NO BIC-GUPC | Construction Deficiency | 2013-04-17 | Luz Arosemena | 2015-07-14 11:04 | 15200- Expansion Locks Pacific | Yissel Wong
5031 |  |  | AS CAR5031- Safety Glasses | Corrective Action Request | Closed | No Ball in Court |  | 2013-03-09 | Marta Small | 2015-08-27 15:34 | 15100- Expansion Locks Atlantic | Jianey Abrahams
5030 |  |  | AS5030 CAR DSB Compliance | Corrective Action Request | Closed | No Ball in Court |  | 2013-03-21 | Gene Williams | 2015-09-04 15:31 | 15100- Expansion Locks Atlantic | Jianey Abrahams
0184 |  |  | AQ0159 CAR QMS FAIL for Buildings | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2013-03-20 | Abdiel Santos | 2013-09-11 10:00 | 15100- Expansion Locks Atlantic | Karla Jones
0183 |  |  | AM2504 CAR Hyd. Cyl. Ship Storage | Corrective Action Request | Closed | NO BIC-GUPC | Errors and Omissions | 2013-03-18 | Juan Rivera | 2014-02-27 22:01 | 15100- Expansion Locks Atlantic | Juan Rivera
0182 |  |  | PM2506 CAR Hyd. Cyl. Stor. 1st Ship | Corrective Action Request | Closed | NO BIC-GUPC | Errors and Omissions | 2013-03-18 | Martin Duran | 2013-12-11 14:21 | 15200- Expansion Locks Pacific | Juan Rivera
0181 |  |  | PQ0087 CAR Perimeter Road WSB LH2 | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2013-03-16 | Javier Gutierrez | 2013-09-04 09:23 | 15200- Expansion Locks Pacific | Luz Arosemena
0180 |  |  | AQ0158 CAR QMS FAIL During Backfill | Corrective Action Request | Closed | No Ball in Court | Administrative | 2013-03-14 | Karla Jones | 2013-05-30 14:21 | 15100- Expansion Locks Atlantic | Karla Jones
0179 |  |  | AM2503 CAR Electrical Pipes Inst. | Corrective Action Request | Closed | NO BIC-GUPC | Errors and Omissions | 2013-03-13 | Juan Rivera | 2014-02-27 22:08 | 15100- Expansion Locks Atlantic | Juan Rivera
0178 |  |  | AQ0155 CAR REB INST_CONC COV TSC D | Corrective Action Request | Closed | No Ball in Court | Administrative | 2013-03-11 | Karla Jones | 2013-05-23 10:52 | 15100- Expansion Locks Atlantic | Karla Jones
0177 |  |  | AQ0157 CAR QMS FAIL during an INSP | Corrective Action Request | Closed | No Ball in Court | Administrative | 2013-03-04 | Karla Jones | 2013-05-23 10:36 | 15100- Expansion Locks Atlantic | Karla Jones
0176 |  |  | PE8065 CAR-Sed Trap Disposal #1 | Corrective Action Request | Closed | Jorge Perez Blanco | Environmental Situation | 2013-01-22 | Martin Morales | 2016-08-19 10:58 | 15200- Expansion Locks Pacific | Gonzalo Menendez
0175 |  |  | PE8064 CAR-Earth Mov Housekeeping | Corrective Action Request | Closed | Jorge Perez Blanco | Environmental Situation | 2013-01-22 | Martin Morales | 2016-08-19 10:49 | 15200- Expansion Locks Pacific | Gonzalo Menendez
0174 |  |  | PE8064 CAR Housekeeping | Corrective Action Request | Closed | Jorge Perez Blanco | Environmental Situation | 2013-01-22 | Martin Morales | 2016-08-19 10:53 | 15200- Expansion Locks Pacific | Gonzalo Menendez
0173 |  |  | PE8063 CAR-Disposal 12 Landslide | Corrective Action Request | Closed | Rafael Sarmiento | Environmental Situation | 2013-03-04 | Martin Morales | 2016-08-19 10:42 | 15200- Expansion Locks Pacific | Gonzalo Menendez
0172 |  |  | WWTP#3 acidic pH levels | Corrective Action Request | Void | Jonnathan Santana | Environmental Situation | 2013-03-04 | Ian Barria | 2016-09-21 08:16 | 15200- Expansion Locks Pacific | Gonzalo Menendez
0171 |  |  | AQ0156 CAR SMC A50 & SMC A50P | Corrective Action Request | Closed | No Ball in Court | Administrative | 2013-02-23 | Karla Jones | 2013-06-14 15:20 | 15100- Expansion Locks Atlantic | Karla Jones
0170 |  |  | AQ0150 CAR QMS FAIL_Pre Signed TSC | Corrective Action Request | Closed | No Ball in Court | Administrative | 2013-02-18 | Karla Jones | 2013-05-01 09:08 | 15100- Expansion Locks Atlantic | Karla Jones
0169 |  |  | AQ0154 CAR IMC A18 Internal Mass C | Corrective Action Request | Closed | No Ball in Court | Administrative | 2013-02-14 | Karla Jones | 2013-07-05 09:50 | 15100- Expansion Locks Atlantic | Karla Jones
0168 |  |  | AQ0153 CAR IMC A14P Internal Mass C | Corrective Action Request | Closed | No Ball in Court | Administrative | 2013-02-07 | Karla Jones | 2013-07-05 09:24 | 15100- Expansion Locks Atlantic | Karla Jones
0167 |  |  | AQ0152 CAR SMC A56 & SMC A56P | Corrective Action Request | Closed | No Ball in Court | Administrative | 2013-02-07 | Karla Jones | 2013-06-14 14:55 | 15100- Expansion Locks Atlantic | Karla Jones
0166 |  |  | AQ0151 CAR Mass & Marine CONC PROP | Corrective Action Request | Closed | No Ball in Court | Administrative | 2013-02-02 | Abdiel Santos | 2013-11-19 08:15 | 15100- Expansion Locks Atlantic | Karla Jones
0165 |  |  | AE8047 CAR Mat Mangmt BatchingPlant | Corrective Action Request | Closed | Patricio Vilo | Environmental Situation | 2012-11-29 | Marta Small | 2015-08-27 15:53 | 15100- Expansion Locks Atlantic | Adrian Lee
0164 |  |  | AE8044 CAR Matl Mngmt. Vila Plano | Corrective Action Request | Closed | Jose Pelaez | Environmental Situation | 2012-10-05 | Marta Small | 2015-08-27 15:54 | 15100- Expansion Locks Atlantic | Adrian Lee
0163 |  |  | AE8043 CAR Workers Cond. Vila Plano | Corrective Action Request | Closed | Jose Pelaez | Environmental Situation | 2012-10-05 | Marta Small | 2015-08-27 15:55 | 15100- Expansion Locks Atlantic | Adrian Lee
0162 |  |  | PE8061 CAR-WWTP#3 pH level | Corrective Action Request | Closed | Jorge Gomez | Environmental Situation | 2012-12-14 | Martin Morales | 2016-09-20 15:12 | 15200- Expansion Locks Pacific | Gonzalo Menendez
0161 |  |  | PE8049CAR Manag of Hazar Mat Issues | Corrective Action Request | Closed | Dino Desiati | Environmental Situation | 2012-07-16 | Tamira Baird | 2015-09-04 13:25 | 15200- Expansion Locks Pacific | Gonzalo Menendez
0160 |  |  | AQ0149 CAR TEMP CTRL Batching Plant | Corrective Action Request | Closed | NO BIC-GUPC | Administrative | 2012-12-04 | Veronica Cash | 2013-08-28 17:08 | 15100- Expansion Locks Atlantic | Maria Ho
0159 |  |  | PE8062 CAR Wast Cent Acc/Lack Seg | Corrective Action Request | Closed | Antonio Pelusi | Environmental Situation | 2012-12-20 | Marta Small | 2015-08-27 16:02 | 15200- Expansion Locks Pacific | Gonzalo Menendez
0158 |  |  | GQ0102 CAR Pouring Plan | Corrective Action Request | Closed | NO BIC-GUPC | Administrative | 2012-12-04 | Veronica Cash | 2013-08-27 15:59 | 15000- Expansion Locks | Maria Ho
0157 |  |  | GQ0100 CAR Thermocouples SCHED INST | Corrective Action Request | Closed | NO BIC-GUPC | Administrative | 2012-12-20 | Veronica Cash | 2014-01-23 14:01 | 15000- Expansion Locks | Maria Ho
0156 |  |  | GQ0099 CAR DTL Method Statements | Corrective Action Request | Closed | NO BIC-GUPC | Administrative | 2012-12-04 | Veronica Cash | 2013-08-27 16:02 | 15000- Expansion Locks | Maria Ho
0155 |  |  | GQ0097 CAR Volume & TMP Monitoring | Corrective Action Request | Closed | NO BIC-GUPC | Administrative | 2012-12-04 | Veronica Cash | 2013-08-28 14:44 | 15000- Expansion Locks | Maria Ho
0154 |  |  | GQ0096 CAR NO FML WT AVG TEMP | Corrective Action Request | Closed | NO BIC-GUPC | Administrative | 2012-12-04 | Veronica Cash | 2013-08-29 10:35 | 15000- Expansion Locks | Maria Ho
0153 |  |  | A00/UPCCAR5027/Ice Plant | Corrective Action Request | Closed | Peterjan Versteele |  | 2012-12-06 | Marta Small | 2015-08-27 16:01 | 15100- Expansion Locks Atlantic | Jianey Abrahams
0152 |  |  | AE8037 CAR WMP Distribution | Corrective Action Request | Closed | Jose Pelaez | Environmental Situation | 2012-12-11 | Marta Small | 2015-08-28 07:13 | 15100- Expansion Locks Atlantic | Adrian Lee
0151 |  |  | AE8031 CAR Sec. Cont. Multiequipos | Corrective Action Request | Closed | Jose Pelaez | Environmental Situation | 2012-12-11 | Marta Small | 2015-08-28 07:14 | 15100- Expansion Locks Atlantic | Adrian Lee
0150 |  |  | AE8047 CAR Material Management | Corrective Action Request | Void | Patricio Vilo | Environmental Situation | 2012-12-01 | Marta Small | 2015-08-28 07:15 | 15100- Expansion Locks Atlantic | Adrian Lee
0149 |  |  | AE8033 CAR MSDS Multiequipos | Corrective Action Request | Closed | Jose Pelaez | Environmental Situation | 2012-12-01 | Marta Small | 2015-08-28 07:17 | 15100- Expansion Locks Atlantic | Adrian Lee
0148 |  |  | AE8030 CAR Env Induct Multiequipos | Corrective Action Request | Closed | Jose Pelaez | Environmental Situation | 2012-05-21 | Marta Small | 2015-08-28 07:21 | 15100- Expansion Locks Atlantic | Adrian Lee
0147 |  |  | AQ0148 CAR Using CEMEX Cement | Corrective Action Request | Closed | No Ball in Court | Administrative | 2012-11-27 | Maylin Moreno | 2016-02-10 11:32 | 15100- Expansion Locks Atlantic | Karla Jones
0146 |  |  | PE8058 CAR - Scrap/Used Tires Manag | Corrective Action Request | Closed | Jonnathan Santana | Environmental Situation | 2012-11-15 | Marta Small | 2015-08-28 07:22 | 15200- Expansion Locks Pacific | Gonzalo Menendez
0145 |  |  | PE8059 CAR Lack MSDS Silica Hazcom | Corrective Action Request | Closed | Peterjan Versteele | Environmental Situation | 2012-11-06 | Marta Small | 2015-08-28 07:23 | 15200- Expansion Locks Pacific | Gonzalo Menendez
0144 |  |  | AQ0072 CAR Mindi Camp Cutting DEF | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2010-10-11 | Karla Jones | 2012-11-14 15:49 | 15100- Expansion Locks Atlantic | Karla Jones
0143 |  |  | AQ0074 CAR EXC outsided Firts PCKG | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-10-12 | Karla Jones | 2012-11-14 15:06 | 15100- Expansion Locks Atlantic | Karla Jones
0142 |  |  | AQ0075 CAR Employee Transportation | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-10-22 | Karla Jones | 2012-11-14 14:48 | 15100- Expansion Locks Atlantic | Karla Jones
0141 |  |  | AQ0076 CAR MTE Lirio Disposal WPR | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-11-26 | Karla Jones | 2012-11-14 14:29 | 15100- Expansion Locks Atlantic | Karla Jones
0140 |  |  | AQ0077 CAR Monte Lirio ENP RR Stats | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-11-26 | Karla Jones | 2012-11-14 14:16 | 15100- Expansion Locks Atlantic | Karla Jones
0139 |  |  | AQ0079 CAR GEOTECH RPTS Submissions | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-11-26 | Karla Jones | 2012-11-14 14:03 | 15100- Expansion Locks Atlantic | Karla Jones
0138 |  |  | AQ0080 CAR SWP for CLR & Grubbing | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-11-26 | Karla Jones | 2012-11-14 13:47 | 15100- Expansion Locks Atlantic | Karla Jones
0137 |  |  | AQ0089 CAR No Storm Water DRNG EXC | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-11-22 | Karla Jones | 2012-11-14 13:24 | 15100- Expansion Locks Atlantic | Karla Jones
0136 |  |  | AQ0097 CAR No ITP or ICL for Sewer | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-11-19 | Karla Jones | 2012-11-14 12:57 | 15100- Expansion Locks Atlantic | Karla Jones
0135 |  |  | AQ0103 CAR Uncontrolled DRW Gatun D | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-11-14 | Karla Jones | 2012-11-14 12:13 | 15100- Expansion Locks Atlantic | Karla Jones
0134 |  |  | AE8044 CAR HAZMAT Handlin VilaPlano | Corrective Action Request | Void | Jose Pelaez | Environmental Situation | 2012-10-05 | Marta Small | 2015-08-28 07:33 | 15100- Expansion Locks Atlantic | Alberto Lezcano
0133 |  |  | AE8043 CAR HKeeping VilaPlano Area | Corrective Action Request | Void | Jose Pelaez | Environmental Situation | 2012-10-05 | Marta Small | 2015-08-28 07:34 | 15100- Expansion Locks Atlantic | Alberto Lezcano
0132 |  |  | AE8036 CAR Access HazWaste Area | Corrective Action Request | Closed | Werner Verbrugge | Environmental Situation | 2012-09-29 | Marta Small | 2015-08-28 07:35 | 15100- Expansion Locks Atlantic | Adrian Lee
0131 |  |  | AE8042 CAR - Ind. Park Decanter Eff | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2012-09-24 | Marta Small | 2015-08-28 07:36 | 15100- Expansion Locks Atlantic | Graciela Palacios
0130 |  |  | PE8056-CAR Bus maintenance. | Corrective Action Request | Closed | Peterjan Versteele |  | 2012-08-31 | Marta Small | 2015-08-28 07:37 | 15200- Expansion Locks Pacific | Gonzalo Menendez
0129 |  |  | PE8055-CAR Defensive Driving Course | Corrective Action Request | Closed | Peterjan Versteele | Environmental Situation | 2012-08-31 | Marta Small | 2015-08-28 07:38 | 15200- Expansion Locks Pacific | Gonzalo Menendez
0128 |  |  | PE8051-CAR Oily water overflow. | Corrective Action Request | Closed | Peterjan Versteele | Environmental Situation | 2012-07-05 | Martin Morales | 2016-08-19 10:02 | 15200- Expansion Locks Pacific | Gonzalo Menendez
0127 |  |  | AQ0071B CAR QC Daily Report Proc. | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-10-27 | Maria Ho | 2012-09-07 14:32 | 15100- Expansion Locks Atlantic | Maria Ho
0126 |  |  | AQ0071A CAR Follow Up Documents | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-10-27 | Maria Ho | 2012-09-07 13:46 | 15100- Expansion Locks Atlantic | Maria Ho
0125 |  |  | PE8050-CAR Hazard.Waste StorageArea | Corrective Action Request | Closed | Laureano Jaramillo | Environmental Situation | 2012-08-20 | Marta Small | 2015-08-28 07:40 | 15200- Expansion Locks Pacific | Gonzalo Menendez
0124 |  |  | PE8048-CAR Soild waste in the WMC. | Corrective Action Request | Closed | Laureano Jaramillo | Environmental Situation | 2012-06-26 | Marta Small | 2015-08-28 07:42 | 15200- Expansion Locks Pacific | Gonzalo Menendez
0123 |  |  | PE8047-CAR Spills Workshop. | Corrective Action Request | Closed | Peterjan Versteele | Environmental Situation | 2012-06-25 | Marta Small | 2015-08-28 07:48 | 15200- Expansion Locks Pacific | Gonzalo Menendez
0122 |  |  | AQ0073 CAR NCN0066 PreCONST MTG DEF | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-10-12 | Gloria Leguias | 2012-09-01 09:32 | 15100- Expansion Locks Atlantic | Gloria Leguias
0121 |  |  | AQ0069 CAR EXC bejond the limits | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-08-10 | Gloria Leguias | 2012-09-01 08:58 | 15100- Expansion Locks Atlantic | Gloria Leguias
0120 |  |  | AQ0071 CAR WIR PROCESS NOTICE | Corrective Action Request | Closed | NO BIC-GUPC | Administrative | 2010-09-01 | Veronica Cash | 2013-08-27 16:03 | 15100- Expansion Locks Atlantic | Maria Ho
0119 |  |  | AQ0070C CAR Vehicle List Updated | Corrective Action Request | Closed | NO BIC-GUPC | Administrative | 2010-09-30 | Veronica Cash | 2013-08-27 16:04 | 15100- Expansion Locks Atlantic | Maria Ho
0118 |  |  | AQ0070B CAR DEF of Moving Loads | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2010-09-06 | Maria Ho | 2012-08-29 11:07 | 15100- Expansion Locks Atlantic | Maria Ho
0117 |  |  | AQ0070A CAR Mindi Bridge DEF | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-09-06 | Maria Ho | 2012-08-29 10:35 | 15100- Expansion Locks Atlantic | Maria Ho
0116 |  |  | AQ0069 CAR Cut Beyond Limits EST | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2010-08-10 | Maria Ho | 2012-08-29 10:00 | 15100- Expansion Locks Atlantic | Maria Ho
0115 |  |  | PQ0038 CAR Foundation Treatment | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2012-08-28 | Luz Arosemena | 2012-08-28 15:30 | 15200- Expansion Locks Pacific | Luz Arosemena
0114 |  |  | PQ0034 CAR Excavation Dry Condition | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2012-08-28 | Luz Arosemena | 2012-08-28 15:22 | 15200- Expansion Locks Pacific | Luz Arosemena
01133 |  |  | A55M0037 NCR WW&OWW CORROSION PROT. | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2016-02-16 | Abdiel Santos | 2016-12-27 15:32 | 15100- Expansion Locks Atlantic | Abdiel Santos
01132 |  |  | A55M0034 NCR LH2 CORROSION PROTECT. | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2016-12-27 | Abdiel Santos | 2016-12-27 15:21 | 15100- Expansion Locks Atlantic | Abdiel Santos
01131 |  |  | A55M0036 NCR LH4 CORROSION PROTECT. | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2016-02-16 | Abdiel Santos | 2016-12-27 15:16 | 15100- Expansion Locks Atlantic | Abdiel Santos
01130 |  |  | A55M0035 NCR LH3 CORROSION PROTECT. | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2016-02-16 | Abdiel Santos | 2016-12-27 15:08 | 15100- Expansion Locks Atlantic | Abdiel Santos
0113 |  |  | PQ0033 CAR D&B Permitted Time | Corrective Action Request | Closed | No Ball in Court | Blasting | 2012-08-28 | Luz Arosemena | 2012-08-28 15:12 | 15200- Expansion Locks Pacific | Luz Arosemena
01129 |  |  | A55M0033 NCR LH1 CORROSION PROTECT. | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2016-02-16 | Abdiel Santos | 2016-12-27 14:46 | 15100- Expansion Locks Atlantic | Abdiel Santos
01128 |  |  | A55M0032 NCR VS6&CC6 CORROSION PROT | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2016-02-16 | Abdiel Santos | 2016-12-27 14:33 | 15100- Expansion Locks Atlantic | Abdiel Santos
01127 |  |  | A55M0031 NCR VS5&CC5 CORROSION PROT | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2016-02-16 | Abdiel Santos | 2016-12-27 14:27 | 15100- Expansion Locks Atlantic | Abdiel Santos
01126 |  |  | A55M0030 NCR VS4&CC4 CORROSION PROT | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2016-02-16 | Abdiel Santos | 2016-12-27 13:57 | 15100- Expansion Locks Atlantic | Abdiel Santos
01125 |  |  | AQ0495 NCR - SDS Repairs West Side | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2016-09-24 | Abdiel Santos | 2016-12-07 10:53 | 15100- Expansion Locks Atlantic | Abdiel Santos
01124 |  |  | AQ0493 NCR - Manhole Covers DEFF | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2016-03-08 | Abdiel Santos | 2016-12-07 10:16 | 15100- Expansion Locks Atlantic | Abdiel Santos
01123 |  |  | AQ0478 NCR LWSB-1&2 Road Slab Fail | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2016-01-28 | Abdiel Santos | 2016-12-07 10:03 | 15100- Expansion Locks Atlantic | Abdiel Santos
00056 |  |  | AQ0040 NCR Vert Anc Pull Out test | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-06-14 | Karla Jones | 2011-09-07 15:44 | 15100- Expansion Locks Atlantic | Javier Gutierrez
01121 |  |  | P55M0054 NCR SSE Underwater Paint | Nonconformance Report | Open | Juan Arturo Rivera | Construction Deficiency | 2016-07-12 | Rick Montanari | 2016-07-18 14:35 | 15200- Expansion Locks Pacific | Lorely Rivera
01120 |  |  | P66M0004 Hydrant PWD Heigth OOT | Nonconformance Report | Closed | Juan Arturo Rivera |  | 2016-05-24 | Lorely Rivera | 2016-08-22 09:26 | 15200- Expansion Locks Pacific | Maria Elena Navarro
0112 |  |  | PQ0032 CAR Slope Stability SDR | Corrective Action Request | Closed | No Ball in Court | Administrative | 2012-08-28 | Luz Arosemena | 2012-08-28 15:03 | 15200- Expansion Locks Pacific | Luz Arosemena
01119 |  |  | A40B0025 PB Ducts material DEF | Nonconformance Report | Open | Ramon Porcell | Construction Deficiency | 2016-05-19 | Mayra Santos | 2016-05-19 15:53 | 15100- Expansion Locks Atlantic | Mayra Santos
01118 |  |  | P66M0003 NCR CU2 PWD Pipe Coating D | Nonconformance Report | Closed | NO BIC-GUPC |  | 2016-05-05 | Lorely Rivera | 2016-10-28 11:03 | 15200- Expansion Locks Pacific | Maria Elena Navarro
01117 |  |  | AQ0491 NCR Sed. & Water underd LWSB | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2016-05-04 | Abdiel Santos | 2016-12-05 16:03 | 15100- Expansion Locks Atlantic | Abdiel Santos
01116 |  |  | P55M0053 NCR Cylinder Rod Scratch | Nonconformance Report | Open | Karel Dewaele | Construction Deficiency | 2016-04-28 | Lorely Rivera | 2016-04-28 09:03 | 15200- Expansion Locks Pacific | Lorely Rivera
01115 |  |  | P55M0052 NCR Valve Seal Damage | Nonconformance Report | Open | Sergi Ametller | Construction Deficiency | 2016-04-21 | Lorely Rivera | 2016-04-21 09:12 | 15200- Expansion Locks Pacific | Lorely Rivera
01114 |  |  | VOID | Nonconformance Report | Void | NO BIC-GUPC | Construction Deficiency | 2016-04-15 | Lorely Rivera | 2016-07-18 14:21 | 15200- Expansion Locks Pacific | Luz Arosemena
01113 |  |  | AQ0486 NCR AR Flex Test fail DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2016-04-14 | Armando Quintero | 2016-05-18 12:10 | 15100- Expansion Locks Atlantic | Jose Dorantes
01112 |  |  | AQ0488 NCR Underdrain pipes LWS DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2016-04-13 | Abdiel Santos | 2016-12-05 15:44 | 15100- Expansion Locks Atlantic | Jose Dorantes
01111 |  |  | AQ0490 NCR Sed. & Water underd MWSB | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2016-04-11 | Abdiel Santos | 2016-12-05 15:57 | 15100- Expansion Locks Atlantic | Armando Quintero
01110 |  |  | NCRP0498CS WSB1 Leakage OOT | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2016-04-06 | Lorely Rivera | 2016-04-26 17:32 | 15200- Expansion Locks Pacific | Lorely Rivera
0111 |  |  | PQ0030 CAR Slope Stability System | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2012-08-28 | Luz Arosemena | 2012-08-28 14:42 | 15200- Expansion Locks Pacific | Luz Arosemena
01109 |  |  | NCRP0497CS Overflow Incident | Nonconformance Report | Closed | NO BIC-GUPC |  | 2016-04-06 | Lorely Rivera | 2016-08-03 09:55 | 15200- Expansion Locks Pacific | Lorely Rivera
01108 |  |  | P67M0002 NCR FPS Hyd Paint Coat Def | Nonconformance Report | Open | Karel Dewaele | Construction Deficiency | 2016-04-06 | Lorely Rivera | 2016-04-06 08:35 | 15200- Expansion Locks Pacific | Lorely Rivera
01107 |  |  | P67M0003 NCR FPS Def at FER and WW | Nonconformance Report | Open | Karel Dewaele | Construction Deficiency | 2016-04-06 | Lorely Rivera | 2016-04-06 08:30 | 15200- Expansion Locks Pacific | Lorely Rivera
01106 |  |  | P67M0003 NCR FPS Def at FER and WW | Nonconformance Report | Open | Karel Dewaele | Construction Deficiency | 2016-04-06 | Lorely Rivera | 2016-04-06 08:24 |  | Lorely Rivera
01105 |  |  | NCRP0499CS Gate Clashing Incident | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2016-05-11 | Lorely Rivera | 2016-07-04 15:40 | 15200- Expansion Locks Pacific | Lorely Rivera
01104 |  |  | P67M0003 NCR FPS Def at FER and WW | Nonconformance Report | Open | Sergi Ametller |  | 2016-04-02 | Lorely Rivera | 2016-04-02 11:56 |  | Lorely Rivera
01103 |  |  | AQ0492 NCR WLT Handholes Inst DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2016-03-29 | Abdiel Santos | 2016-12-05 16:11 | 15100- Expansion Locks Atlantic | Mayra Santos
01102 |  |  | P67M0004 NCR FPS Bolts Deviation | Nonconformance Report | Open | Juan Arturo Rivera | Defective Materials | 2016-03-17 | Maria Elena Navarro | 2016-03-17 17:48 | 15200- Expansion Locks Pacific | Maria Elena Navarro
01101 |  |  | P66M0002 NCR Painting Pipe Deficien | Nonconformance Report | Closed | Sergi Ametller | Defective Materials | 2016-03-15 | Lorely Rivera | 2016-08-30 17:13 | 15200- Expansion Locks Pacific | Maria Elena Navarro
01100 |  |  | P78M0001 NCR WWTP Flange Replace | Nonconformance Report | Closed | Juan Arturo Rivera | Construction Deficiency | 2016-03-11 | Lorely Rivera | 2016-06-13 16:02 | 15200- Expansion Locks Pacific | Maria Elena Navarro
0110 |  |  | PQ0029 CAR D&B Permitted Time | Corrective Action Request | Closed | No Ball in Court | Blasting | 2012-08-28 | Luz Arosemena | 2012-08-28 14:16 | 15200- Expansion Locks Pacific | Luz Arosemena
01099 |  |  | NCRP0494CS WSB3 Leakage OOT | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2016-03-10 | Rick Montanari | 2016-04-06 11:17 | 15200- Expansion Locks Pacific | Luz Arosemena
01098 |  |  | NCRP0012CS BLD Stairs not installed | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2016-05-21 | Lorely Rivera | 2016-08-24 09:22 | 15200- Expansion Locks Pacific | Luz Arosemena
01097 |  |  | NCRP0500CS EMH Covers | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2016-05-24 | Lorely Rivera | 2016-09-24 10:19 | 15200- Expansion Locks Pacific | Luz Arosemena
01096 |  |  | NCRP0011CS Bld WHA Embedded | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2016-05-25 | Lorely Rivera | 2016-08-29 16:02 | 15200- Expansion Locks Pacific | Luz Arosemena
01095 |  |  | A78M0001 NCR WWTP Lifting Lugs DEF | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2016-03-03 | Maylin Moreno | 2016-03-03 11:20 | 15100- Expansion Locks Atlantic | Maylin Moreno
01094 |  |  | A55M0029 NCR VS3CC3 SSE Corr DEF | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2016-03-03 | Maylin Moreno | 2016-03-03 10:41 | 15100- Expansion Locks Atlantic | Maylin Moreno
01093 |  |  | A55M0028 NCR VS2CC2 SSE Corr DEF | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2016-03-01 | Maylin Moreno | 2016-03-01 16:23 | 15100- Expansion Locks Atlantic | Maylin Moreno
01092 |  |  | A55M0027 NCR VS1CC1 SSE Corr DEF | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2016-03-01 | Maylin Moreno | 2016-03-01 16:10 | 15100- Expansion Locks Atlantic | Maylin Moreno
01091 |  |  | VOID | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2016-03-01 | Veronica Cash | 2016-05-03 11:27 | 15100- Expansion Locks Atlantic | Maylin Moreno
01090 |  |  | NCRP0003CS Bld Concrete Block Def | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2016-02-23 | Lorely Rivera | 2016-07-07 15:33 | 15200- Expansion Locks Pacific | Luz Arosemena
0109 |  |  | PQ0028 CAR D&B Material Approval | Corrective Action Request | Closed | No Ball in Court | Blasting | 2012-08-28 | Luz Arosemena | 2012-08-28 14:16 | 15200- Expansion Locks Pacific | Luz Arosemena
01089 |  |  | NCRP0008CS Bld MCB Cut Stru. Rebar | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2016-02-18 | Lorely Rivera | 2016-10-04 14:19 | 15200- Expansion Locks Pacific | Luz Arosemena
01088 |  |  | NCRP0005CS Bld Def Concrete Block | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2016-02-18 | Lorely Rivera | 2016-07-11 11:45 | 15200- Expansion Locks Pacific | Luz Arosemena
01087 |  |  | AQ0464 NCR AR-UW-110 pipe not INST | Nonconformance Report | Open | Fernando Dominguez | Construction Deficiency | 2016-02-13 | Maylin Moreno | 2016-02-13 09:54 | 15100- Expansion Locks Atlantic | Maylin Moreno
01086 |  |  | AQ0489 NCR Sed. & Water underd UWSB | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2016-01-28 | Abdiel Santos | 2016-12-05 15:53 | 15100- Expansion Locks Atlantic | Abdiel Santos
00057 |  |  | PQ0036 NCR DISPOSAL No. 5 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-06-16 | Luz Arosemena | 2011-08-16 14:16 | 15200- Expansion Locks Pacific | Luz Arosemena
01084 |  |  | A55M0026 NCR LC SSE Corrosion DEF | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2016-01-11 | Jose Dorantes | 2016-04-22 10:26 | 15100- Expansion Locks Atlantic | Armando Quintero
01083 |  |  | A55M0025 NCR MC SSE Corrosion DEF | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2016-01-11 | Jose Dorantes | 2016-04-22 10:03 | 15100- Expansion Locks Atlantic | Armando Quintero
01082 |  |  | A55M0024 NCR UC SSE Corrosion def | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2016-01-11 | Jose Dorantes | 2016-04-22 09:55 | 15100- Expansion Locks Atlantic | Armando Quintero
01081 |  |  | P92M0002 NCR MRB1 SWGR-S OOP | Nonconformance Report | Closed | Juan Arturo Rivera | Construction Deficiency | 2016-01-05 | Lorely Rivera | 2016-04-01 14:22 | 15200- Expansion Locks Pacific | Lorely Rivera
00058 |  |  | PQ0038 NCR EAST LATERAL COFFERDAM | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-06-22 | Luz Arosemena | 2012-04-14 11:17 | 15200- Expansion Locks Pacific | Luz Arosemena
0108 |  |  | PQ0027 CAR QMS Process - CIQP | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-08-28 | Luz Arosemena | 2012-08-28 13:59 | 15200- Expansion Locks Pacific | Luz Arosemena
00061 |  |  | AQ0042 NCR WSB Exc limits Exceeded | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-06-23 | Zosimo Correa | 2011-09-16 14:44 | 15100- Expansion Locks Atlantic | Zosimo Correa
00060 |  |  | AQ0041 NCR EXC WSBs West Slopes | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-06-23 | Tamira Baird | 2015-09-04 13:19 | 15100- Expansion Locks Atlantic | Zosimo Correa
00059 |  |  | AE8000 NCR spill at the excavation | Nonconformance Report | Closed | Bernardo Gonzalez | Environmental Situation | 2011-06-23 | Eliza Florendo | 2012-02-11 08:33 | 15100- Expansion Locks Atlantic | Abed Camarena
00062 |  |  | AE8002 NCR Rainwater sediment contr | Nonconformance Report | Closed | Federico Casanova | Environmental Situation | 2011-06-28 | Abed Camarena | 2011-10-21 14:32 | 15100- Expansion Locks Atlantic | Abed Camarena
00066 |  |  | PQ0041 NCR HONEYCOMBS F. TREATMENT | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-06-30 | Luz Arosemena | 2011-12-28 09:53 | 15200- Expansion Locks Pacific | Luz Arosemena
00065 |  |  | PQ0040 NCR FOUND. TREATMENT UE-M21 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-06-30 | Luz Arosemena | 2012-04-14 11:12 | 15200- Expansion Locks Pacific | Luz Arosemena
00064 |  |  | AQ0043 NCR EXC YIELD POINT 8 ANCHOR | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-06-30 | Maria Ho | 2011-09-26 09:16 | 15100- Expansion Locks Atlantic | Zosimo Correa
00063 |  |  | NCRP0037CS DISPOSAL No. 4 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-06-30 | Luz Arosemena | 2014-01-31 10:58 | 15200- Expansion Locks Pacific | Luz Arosemena
00067 | Atlantic | FS-U16D | AQ0044 NCR GEOM of Slab 16D changed | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-07-04 | Karla Jones | 2011-10-31 18:27 | 15100- Expansion Locks Atlantic | Zosimo Correa
00068 |  |  | PQ0042 NCR UTILITY RELOCATION 16" | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-07-07 | Luz Arosemena | 2012-09-01 10:38 | 15200- Expansion Locks Pacific | Luz Arosemena
0107 |  |  | PQ0026 CAR NCR Process | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-08-28 | Luz Arosemena | 2012-08-28 13:54 | 15200- Expansion Locks Pacific | Luz Arosemena
00078 |  |  | AQ0047 NCR Agg 75 mm not meet specs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-07-13 | Karla Jones | 2011-09-01 15:22 | 15100- Expansion Locks Atlantic | Karla Jones
00073 |  |  | AQ0053 NCR Gatun Plug plastic CONC | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-07-18 | Karla Jones | 2012-02-16 09:14 | 15100- Expansion Locks Atlantic | Zosimo Correa
00072 |  |  | AQ0050 NCR Plug Cut of Wall | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-07-18 | Karla Jones | 2011-11-07 11:41 | 15100- Expansion Locks Atlantic | Zosimo Correa
00146 |  |  | VOID | Noncompliance Notice | Void | Bernardo Gonzalez |  | 2011-07-18 | Lorri Cullivan | 2011-07-20 11:04 |  | John Lopacki
00071 |  |  | AQ0049 NCR Lack - Anchor on UOM 50E | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-07-18 | Karla Jones | 2011-09-29 10:58 | 15100- Expansion Locks Atlantic | Zosimo Correa
00070 |  |  | AQ0046 NCR Dock 45 East BYD Limits | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-07-18 | Karla Jones | 2012-02-16 09:33 | 15100- Expansion Locks Atlantic | Zosimo Correa
00069 |  |  | AQ0045 NCR DEF of Concrete Dish | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-07-18 | Karla Jones | 2011-11-17 13:22 | 15100- Expansion Locks Atlantic | Zosimo Correa
00074 |  |  | PQ0043 NCR DISPOSAL No. 2 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-07-19 | Luz Arosemena | 2011-12-28 09:38 | 15200- Expansion Locks Pacific | Luz Arosemena
00003 |  |  | G55M0004 NCR HSH Pack Boxes Damage | Nonconformance Report | Closed | NO BIC-GUPC | Defective Materials | 2011-07-22 | Alberto Alonzo | 2014-05-21 15:35 | 15000- Expansion Locks | Maria Ho
00076 |  |  | AQ0054 NCR Lack of PROT in slab | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-07-27 | Karla Jones | 2012-02-08 08:50 | 15100- Expansion Locks Atlantic | Zosimo Correa
00077 |  |  | AQ0048 NCR Gabion Walls Deficiency | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-07-30 | Zosimo Correa | 2011-09-16 15:02 | 15100- Expansion Locks Atlantic | Zosimo Correa
0106 |  |  | PQ0025 CAR Excavation and Fill | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-08-28 | Luz Arosemena | 2012-08-28 13:42 | 15200- Expansion Locks Pacific | Luz Arosemena
00080 |  |  | AQ0056 NCR Cold joint in slab 4C | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-08-02 | Zosimo Correa | 2011-09-16 15:30 | 15100- Expansion Locks Atlantic | Zosimo Correa
00079 |  |  | AQ0055 NCR Cold joint in slab 2H | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-08-02 | Zosimo Correa | 2011-09-16 15:25 | 15100- Expansion Locks Atlantic | Zosimo Correa
00082 |  |  | PQ0045 NCR 3rd Supply Reinf Rebars | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-08-10 | Luz Arosemena | 2012-04-13 11:48 | 15200- Expansion Locks Pacific | Luz Arosemena
00081 |  |  | AQ0052 NCR Slab 15B Deficiencies | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-08-10 | Karla Jones | 2012-02-17 16:08 | 15100- Expansion Locks Atlantic | Zosimo Correa
00083 |  |  | AQ0057 NCR Deficiency of Rebar Inst | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-08-12 | Karla Jones | 2011-11-07 12:26 | 15100- Expansion Locks Atlantic | Zosimo Correa
00002 |  |  | A55M0001 NCR HSH Clv Lnr Ship 1 | Nonconformance Report | Closed | NO BIC-GUPC | Defective Materials | 2011-08-12 | Juan Rivera | 2014-07-09 00:58 | 15100- Expansion Locks Atlantic | Maria Ho
00084 | Pacific | CU2-2W-14 | PQ0046 NCR CU2-2W-14 Concrete Cover | Nonconformance Report | Closed | Javier Gutierrez | Construction Deficiency | 2011-08-13 | Veronica Cash | 2013-08-28 08:38 | 15200- Expansion Locks Pacific | Javier Gutierrez
00085 | Atlantic | FS-U09G | AQ0058 NCR SF 9G East large void | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-08-17 | Karla Jones | 2011-10-17 11:03 | 15100- Expansion Locks Atlantic | Karla Jones
00001 |  |  | P55M0001 NCR HSH Clv Lnr Ship 1 | Nonconformance Report | Closed | No Ball in Court | Defective Materials | 2011-08-22 | Lorely Rivera | 2016-03-30 08:40 | 15200- Expansion Locks Pacific | Maria Ho
00091 |  |  | G55M0003 NCR HSH Clv Lnr Ship 1 | Nonconformance Report | Closed | NO BIC-GUPC | Defective Materials | 2011-08-23 | Alberto Alonzo | 2013-06-03 13:40 | 15000- Expansion Locks | Miguel Tome
0105 |  |  | PQ0024 CAR Preparatory Documents | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-08-28 | Luz Arosemena | 2012-08-28 13:29 | 15200- Expansion Locks Pacific | Luz Arosemena
00089 | Pacific | CU2-2W-14 | PQ0048 NCR CU2-2W-14 Misalignment | Nonconformance Report | Closed | Javier Gutierrez | Construction Deficiency | 2011-08-23 | Veronica Cash | 2013-08-28 08:44 | 15200- Expansion Locks Pacific | Luz Arosemena
00088 | Atlantic | CC2-I-05 | AQ0059 NCR Slabs Void CC2-I-05 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-08-23 | Karla Jones | 2011-10-19 08:07 | 15100- Expansion Locks Atlantic | Karla Jones
00090 | Atlantic | CU1-2W-16 | AQ0060 Cold Joint in UOM CU1-2W-16 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-08-24 | Zosimo Correa | 2011-09-16 15:16 | 15100- Expansion Locks Atlantic | Karla Jones
00092 |  |  | AQ0008 NCR Spot Audit No. 100823 Mt | Nonconformance Report | Closed | No Ball in Court | Contract Term | 2011-09-05 | Karla Jones | 2011-09-07 15:26 | 15100- Expansion Locks Atlantic | Karla Jones
00093 | Atlantic |  | AQ0061 NCR Monolith 11 deficiencies | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-06 | Karla Jones | 2012-01-25 16:25 | 15100- Expansion Locks Atlantic | Karla Jones
00096 | Atlantic |  | AQ0062 NCR Monolith 15 deficiencies | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-13 | Karla Jones | 2011-10-31 13:39 | 15100- Expansion Locks Atlantic | Karla Jones
00098 | Atlantic | CC2-I-05 | AQ0064 NCR CC2-I-05 repaired W/O ap | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-15 | Karla Jones | 2011-10-04 11:29 | 15100- Expansion Locks Atlantic | Karla Jones
00097 | Atlantic |  | AQ0063 NCR UOM´s W/O Trowel Finish | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-15 | Abdiel Santos | 2014-08-25 15:06 | 15100- Expansion Locks Atlantic | Karla Jones
00101 | Atlantic |  | AQ0067 NCR Curing dont comply W/SPE | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-16 | Karla Jones | 2011-12-13 15:39 | 15100- Expansion Locks Atlantic | Karla Jones
00100 |  |  | AQ0066 NCR Fine sand dont comply | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-16 | Karla Jones | 2011-12-05 14:34 | 15100- Expansion Locks Atlantic | Karla Jones
0104 |  |  | PQ0023 CAR Drilling and Blasting | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-08-28 | Luz Arosemena | 2012-08-28 11:52 | 15200- Expansion Locks Pacific | Luz Arosemena
00099 |  |  | AQ0065 NCR 37.5mm Agg dont comply w | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-16 | Karla Jones | 2011-10-31 17:18 | 15100- Expansion Locks Atlantic | Karla Jones
00106 |  |  | AQ0070 NCR SF-M22-E Cracks noted | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2011-09-19 | Karla Jones | 2013-02-18 10:38 | 15100- Expansion Locks Atlantic | Karla Jones
00105 |  |  | AE8004 NCR JDN/CUSA workshop 2 | Nonconformance Report | Closed | Pedro Cuenca | Environmental Situation | 2011-09-19 | Tamira Baird | 2015-09-04 15:26 | 15100- Expansion Locks Atlantic | Abed Camarena
00104 |  |  | AE8003 NCR JDN/CUSA Workshop | Nonconformance Report | Closed | Pedro Cuenca | Environmental Situation | 2011-09-19 | Abed Camarena | 2011-12-01 15:18 | 15100- Expansion Locks Atlantic | Abed Camarena
00103 | Atlantic | FS-M15F | AQ0069 NCR Cold Joint - UOM SF-M15F | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-19 | Karla Jones | 2011-10-04 14:29 | 15100- Expansion Locks Atlantic | Karla Jones
00102 | Atlantic | CU2-2W-14 | AQ0068 NCR Cold Joint in CU2-2W-14 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-19 | Karla Jones | 2011-10-04 12:10 | 15100- Expansion Locks Atlantic | Karla Jones
00108 | Atlantic | UW-M13-F03 | AQ0072 NCR Def on rebar UW-M13-F03 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-20 | Karla Jones | 2011-10-25 16:04 | 15100- Expansion Locks Atlantic | Karla Jones
00107 | Atlantic | UW-M13-F03 | AQ0071 NCR Def on pour UW-M13-F03 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-20 | Karla Jones | 2011-10-31 18:11 | 15100- Expansion Locks Atlantic | Karla Jones
00109 | Pacific | UW-M21-F01 | PQ0050 NCR Re-bar on UW-M21 F01 | Nonconformance Report | Closed | Richard Van Hellemondt | Construction Deficiency | 2011-09-22 | Luz Arosemena | 2012-02-08 15:33 | 15200- Expansion Locks Pacific | Luz Arosemena
00113 | Pacific | UW-M09-F02 | PQ0054 NCR Honeycombing UW-M09-F02 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-23 | Luz Arosemena | 2012-09-24 09:30 | 15200- Expansion Locks Pacific | Luz Arosemena
0103 |  |  | PQ0022 CAR East West Cofferdams | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-08-28 | Luz Arosemena | 2012-08-28 11:39 | 15200- Expansion Locks Pacific | Luz Arosemena
00112 | Pacific | UE-M09-F01 | PQ0053 NCR Honeycombing UE-M9-F01 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-23 | Luz Arosemena | 2012-08-24 08:54 | 15200- Expansion Locks Pacific | Luz Arosemena
00111 | Pacific |  | PQ0052 NCR Curing on CU & Monoliths | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-23 | Luz Arosemena | 2012-09-01 10:32 | 15200- Expansion Locks Pacific | Luz Arosemena
00110 | Pacific |  | PQ0051 NCR Temp & over break CU2 | Nonconformance Report | Closed | Javier Gutierrez | Construction Deficiency | 2011-09-23 | Luz Arosemena | 2011-11-23 15:40 | 15200- Expansion Locks Pacific | Luz Arosemena
00130 |  |  | PE8000 NCR Contaminated soil | Nonconformance Report | Closed | Laureano Jaramillo | Environmental Situation | 2011-09-24 | Tamira Baird | 2015-09-04 14:15 | 15200- Expansion Locks Pacific | Luz Arosemena
00127 |  | UE-M23-F06 | NCRP0049CS Irregularities UE-M23-F6 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-24 | Javier Gutierrez | 2014-01-18 08:54 | 15200- Expansion Locks Pacific | Luz Arosemena
00126 | Pacific |  | PQ0068 NCR Joint treatment | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-24 | Luz Arosemena | 2011-12-06 10:42 | 15200- Expansion Locks Pacific | Luz Arosemena
00125 | Pacific |  | NCRP0067CS Poor Finishing Practices | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-24 | Javier Gutierrez | 2013-12-01 15:42 | 15200- Expansion Locks Pacific | Luz Arosemena
00124 | Pacific |  | PQ0066 NCR WaterStop UW-M11 South | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-24 | Luz Arosemena | 2012-01-28 11:58 | 15200- Expansion Locks Pacific | Luz Arosemena
00123 | Pacific |  | PQ0065 NCR Honeycombing UW-M11-1 S | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-24 | Luz Arosemena | 2012-05-04 15:06 | 15200- Expansion Locks Pacific | Luz Arosemena
00122 | Atlantic | CU2-2W-14 | NCRP0064CS Gutter on CU2-2W-14 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-24 | Luz Arosemena | 2013-07-15 11:20 | 15200- Expansion Locks Pacific | Luz Arosemena
0102 |  |  | PQ0021 CAR Environment Quality Actv | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2012-08-28 | Luz Arosemena | 2012-08-28 11:08 | 15200- Expansion Locks Pacific | Luz Arosemena
00121 | Pacific | CU2-1W-3N | PQ0063 NCR Poor Consol. CU2-1W-3 N | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-24 | Luz Arosemena | 2012-02-09 10:58 | 15200- Expansion Locks Pacific | Luz Arosemena
00120 | Pacific | CU2-1W-03N | PQ0062 NCR WaterStop CU2-1W-3 North | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-24 | Luz Arosemena | 2011-11-30 16:13 | 15200- Expansion Locks Pacific | Luz Arosemena
00119 | Pacific | CU2-1W-03S | PQ0061 NCR Waterstop-CU2-1W-3 South | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-24 | Luz Arosemena | 2011-12-13 08:28 | 15200- Expansion Locks Pacific | Luz Arosemena
00118 | Pacific | CU2-1W-04 | PQ0060 NCR Honeycombing - CU2-1W-04 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-24 | Luz Arosemena | 2011-12-13 08:22 | 15200- Expansion Locks Pacific | Luz Arosemena
00117 | Pacific |  | NCRP0058CS Damage Finish Floor CU2 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-24 | Luz Arosemena | 2013-07-15 11:15 | 15200- Expansion Locks Pacific | Luz Arosemena
00116 | Pacific | UE-M09-F02 | PQ0057 NCR 1st Embed UE-M09-F02 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-24 | Veronica Cash | 2013-08-28 08:47 | 15200- Expansion Locks Pacific | Luz Arosemena
00115 | Pacific | CU2-2W-13 | PQ0056 NCR Honeycombing CU2-2W-13 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-24 | Luz Arosemena | 2012-12-14 11:54 | 15200- Expansion Locks Pacific | Luz Arosemena
00114 | Pacific | UW-M21-F02 | PQ0055 NCR Honeycombing - UW-M21-F2 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-24 | Luz Arosemena | 2012-05-04 14:32 | 15200- Expansion Locks Pacific | Luz Arosemena
00129 | Atlantic |  | AQ0073 NCR Insufficient splice leng | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-26 | Karla Jones | 2011-10-13 13:38 | 15100- Expansion Locks Atlantic | Karla Jones
00128 | Pacific |  | PQ0069 NCR Reinforcing Steel Break | Nonconformance Report | Closed | No Ball in Court | Defective Materials | 2011-09-26 | Luz Arosemena | 2012-05-11 10:26 | 15200- Expansion Locks Pacific | Luz Arosemena
00131 | Atlantic | UW-M15-C04 | AQ0074 NCR UW-M15-C04 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-28 | Karla Jones | 2011-11-10 08:00 | 15100- Expansion Locks Atlantic | Karla Jones
00133 | Atlantic | FS-M13B | AQ0079 NCR Cold Joint UOM SF-M13B | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-29 | Karla Jones | 2011-10-17 11:27 | 15100- Expansion Locks Atlantic | Karla Jones
00132 | Atlantic | CU1-2W-13 | AQ0075 NCR CU1-2W-13 Rebar def | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-29 | Karla Jones | 2011-10-08 08:26 | 15100- Expansion Locks Atlantic | Karla Jones
0101 |  |  | PQ0018 CAR DQP Subcontractor | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-08-21 | Luz Arosemena | 2012-08-21 16:01 | 15200- Expansion Locks Pacific | Luz Arosemena
00135 | Atlantic | H2W-1C-F02 | AQ0081 NCR H2W-1C-F02 Rebar def | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-30 | Karla Jones | 2011-10-13 13:49 | 15100- Expansion Locks Atlantic | Karla Jones
00134 | Atlantic | UW-M03 | AQ0080 NCR Cold Joint in UOM UW-M03 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-09-30 | Karla Jones | 2011-10-08 08:30 | 15100- Expansion Locks Atlantic | Karla Jones
00136 | Atlantic | CC1-C-05 | AQ0082 NCR CC1-C-05 Rebar def | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-01 | Bennie Torres | 2012-04-19 07:32 | 15100- Expansion Locks Atlantic | Abdiel Santos
00138 | Pacific | UW-M09-F01S | PQ0071 NCR WATER STOP UW-M09-F01 S. | Nonconformance Report | Closed | Javier Gutierrez | Construction Deficiency | 2011-10-04 | Luz Arosemena | 2011-10-18 11:28 | 15200- Expansion Locks Pacific | Luz Arosemena
00137 | Pacific | UW-M11-F01N | PQ0070 NCR WATER STOP UW-M11-F01 N. | Nonconformance Report | Closed | Javier Gutierrez | Construction Deficiency | 2011-10-04 | Luz Arosemena | 2011-10-18 11:21 | 15200- Expansion Locks Pacific | Luz Arosemena
00139 | Atlantic | CC2-I-05 | AQ0084 NCR CC2-I-05 West face void | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-06 | Karla Jones | 2011-10-17 11:56 | 15100- Expansion Locks Atlantic | Karla Jones
00142 | Pacific | CU2-C-04C-E | PQ0074 NCR CU2-C-4c EAST | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-10 | Luz Arosemena | 2012-09-21 10:03 | 15200- Expansion Locks Pacific | Luz Arosemena
00141 | Pacific | CU2-C-04C-W | PQ0073 NCR CU2-C-4c WEST | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-10 | Luz Arosemena | 2012-02-02 15:01 | 15200- Expansion Locks Pacific | Luz Arosemena
00140 | Pacific | CU2-C-04C-W | PQ0075 NCR Water Stop CU2-C-4a WEST | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-10 | Rick Montanari | 2012-09-26 11:00 | 15200- Expansion Locks Pacific | Luz Arosemena
00144 | Atlantic | CU1-C-01aS | AQ0087 NCR CU1-C-01a S face Void | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-11 | Karla Jones | 2012-01-20 16:31 | 15100- Expansion Locks Atlantic | Karla Jones
00143 | Atlantic | FS-M13B | AQ0085 NCR SF-M13-B South face void | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-11 | Karla Jones | 2011-10-19 08:28 | 15100- Expansion Locks Atlantic | Karla Jones
00147 | Pacific | UW-M23-F01a | PQ0088 NCR Cleaning Rebar UW-M23F01 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-12 | Maria Ho | 2012-02-15 15:41 | 15200- Expansion Locks Pacific | Luz Arosemena
0100 |  |  | AQ0040A CAR Lack of Temp Drainage | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-07-19 | Maria Ho | 2012-08-21 16:00 | 15100- Expansion Locks Atlantic | Maria Ho
00146 | Pacific | UW-M23-F01a | PQ0087 NCR Joint Treat. UW-M23-F01a | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-12 | Luz Arosemena | 2011-12-13 08:49 | 15200- Expansion Locks Pacific | Luz Arosemena
00145 | Pacific | UW-M21-F01 | PQ0086 NCR Honeycombs UW-M21-F01 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-12 | Javier Gutierrez | 2012-05-01 17:48 | 15200- Expansion Locks Pacific | Luz Arosemena
00148 | Atlantic | LH2 | AQ0094 NCR Lockhead 2 UOMs seepage | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-14 | Karla Jones | 2012-01-27 12:35 | 15100- Expansion Locks Atlantic | Karla Jones
00149 | Pacific | H2E-3A | PQ0079 NCR H2E-3A CHAMFER COVER LOW | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-15 | Veronica Cash | 2013-08-28 08:49 | 15200- Expansion Locks Pacific | Luz Arosemena
00156 | Atlantic | FS-M13B | AQ0093 NCR SF-M13-B West face void | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-17 | Karla Jones | 2011-11-21 09:57 | 15100- Expansion Locks Atlantic | Karla Jones
00155 |  |  | AQ0083 NCR Access Road fiber optic | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-17 | Karla Jones | 2011-11-18 16:45 | 15100- Expansion Locks Atlantic | Karla Jones
00154 | Pacific | ME-M02-F03 | PQ0078 NCR ME-M02-F03 Reinforcing | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-17 | Luz Arosemena | 2011-12-13 08:35 | 15200- Expansion Locks Pacific | Luz Arosemena
00153 | Atlantic | UW-M15-C04b | AQ0078 NCR UOM UW-M15-C04b Wall fac | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-17 | Karla Jones | 2012-01-10 18:10 | 15100- Expansion Locks Atlantic | Karla Jones
00152 | Pacific | MW-M03-F03 | PQ0077 NCR MW-M03-F03 Reinforcing | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-17 | Luz Arosemena | 2012-02-13 17:00 | 15200- Expansion Locks Pacific | Luz Arosemena
00151 | Atlantic | UW-M15-C04b | AQ0077 NCR UW-M15-C04b Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-17 | Karla Jones | 2012-02-24 11:27 | 15100- Expansion Locks Atlantic | Karla Jones
0099 |  |  | PQ0017 CAR Audit to Subcontractors | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-08-21 | Luz Arosemena | 2012-08-21 15:39 | 15200- Expansion Locks Pacific | Luz Arosemena
00150 | Atlantic | UW-M15-C04a | AQ0076 NCR UOM UW-M15-C04a backfill | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-17 | Karla Jones | 2012-02-29 17:44 | 15100- Expansion Locks Atlantic | Karla Jones
00162 | Pacific | H2E-3C-F05 | PQ0091 NCR H2E-3C-F05 Reinforcing | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-18 | Luz Arosemena | 2012-08-28 16:23 | 15200- Expansion Locks Pacific | Luz Arosemena
00161 | Pacific | UE-M16 | PQ0090 NCR UE-M16b Honeycombs | Nonconformance Report | Closed | Javier Gutierrez | Construction Deficiency | 2011-10-18 | Javier Gutierrez | 2012-05-30 13:16 | 15200- Expansion Locks Pacific | Luz Arosemena
00160 | Pacific | UW-M23-F01a | PQ0089 NCR UW-M23-F01a N Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-18 | Luz Arosemena | 2012-08-24 16:07 | 15200- Expansion Locks Pacific | Luz Arosemena
00159 | Pacific | CU1-1E-13b | PQ0085 NCR CU1-1E-13b Wall Blow Out | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-18 | Luz Arosemena | 2011-12-13 08:43 | 15200- Expansion Locks Pacific | Luz Arosemena
00158 | Pacific | H2E-3A | PQ0084 NCR H2E-3A- Chamfer | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-18 | Luz Arosemena | 2013-02-04 12:01 | 15200- Expansion Locks Pacific | Luz Arosemena
00157 | Pacific | UE-M10-F01 | PQ0083 NCR UE-M10-F01 Mass Concrete | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-18 | Luz Arosemena | 2012-09-12 14:28 | 15200- Expansion Locks Pacific | Luz Arosemena
00164 | Atlantic | H2W-1C-F03 | AQ0089 NCR H2W-1C-F03 E S LRG void | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-19 | Karla Jones | 2011-11-18 13:12 | 15100- Expansion Locks Atlantic | Karla Jones
00163 | Atlantic | H2W-1A-F03N | AQ0088 NCR H2W-1A-F03 N LRG Voids | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-19 | Karla Jones | 2011-11-18 11:52 | 15100- Expansion Locks Atlantic | Karla Jones
00168 | Atlantic | H2W-1C-F02 | AQ0096 NCR H2W-1C-F02 Larger voids | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-24 | Karla Jones | 2012-03-03 14:00 | 15100- Expansion Locks Atlantic | Karla Jones
0098 |  |  | PQ0016 CAR ACP Audit-GUPC-P-2010-09 | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-08-21 | Luz Arosemena | 2012-08-21 15:29 | 15200- Expansion Locks Pacific | Luz Arosemena
00167 | Atlantic | UW-M09-F01 | AQ0100 NCR UW-M09-F01 Large voids | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-24 | Karla Jones | 2012-01-20 16:41 | 15100- Expansion Locks Atlantic | Karla Jones
00166 | Atlantic | H2W-1C-F02 | AQ0097 NCR H2W-1C-F02 Large voids | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-24 | Karla Jones | 2012-03-03 14:00 | 15100- Expansion Locks Atlantic | Karla Jones
00165 | Atlantic | CC2-C-04c | AQ0098 NCR CC2C04c Start bar issue | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-24 | Karla Jones | 2011-12-03 11:23 | 15100- Expansion Locks Atlantic | Karla Jones
00174 | Atlantic | CU1-03b-N | AQ0086 NCR CU1-03b-N Reinforcement | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-25 | Karla Jones | 2011-12-03 11:30 | 15100- Expansion Locks Atlantic | Karla Jones
00173 | Pacific | UE-M21-F02b | PQ0093 NCR Honeycombs UE-M21-F02b | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-25 | Luz Arosemena | 2012-08-24 15:51 | 15200- Expansion Locks Pacific | Luz Arosemena
00974 |  |  | NCRP0501CS Roads 145 & 232 Cracks | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2016-05-30 | Lorely Rivera | 2016-07-06 11:58 | 15200- Expansion Locks Pacific | Lorely Rivera
00172 | Pacific | UW-M23-F01b | PQ0096 NCR UW-M23-F01b Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-25 | Luz Arosemena | 2013-01-22 15:28 | 15200- Expansion Locks Pacific | Luz Arosemena
00171 | Pacific | UW-M23-F01b | NCRP0095CS Cracks UW-M23-F01b | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-25 | Luz Arosemena | 2013-02-09 10:05 | 15200- Expansion Locks Pacific | Luz Arosemena
00170 | Pacific | UW-M23-F02S | PQ0094 NCR Honeycombs UW-M23-F02 S. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-25 | Veronica Cash | 2013-08-28 08:53 | 15200- Expansion Locks Pacific | Luz Arosemena
00169 | Pacific | UW-M23-F01b | PQ0092 NCR Honeycombs UW-M23-F01b | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-25 | Luz Arosemena | 2012-02-14 07:32 | 15200- Expansion Locks Pacific | Luz Arosemena
0097 |  |  | PQ0014 CAR Technical Specifications | Corrective Action Request | Closed | No Ball in Court | Administrative | 2012-08-21 | Luz Arosemena | 2012-08-21 15:09 | 15200- Expansion Locks Pacific | Luz Arosemena
00177 | Atlantic | H2W-1A-F02 | AQ0091 NCR H2W-1A-F02 CONC SURR LOC | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-26 | Karla Jones | 2012-02-16 10:23 | 15100- Expansion Locks Atlantic | Karla Jones
00176 | Atlantic | H2W-1C-F02 | AQ0090 NCR H2W-1C-F02 CONC SURR LOC | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-26 | Karla Jones | 2012-02-14 14:19 | 15100- Expansion Locks Atlantic | Karla Jones
00175 | Atlantic | H2W-1A-F01 | AQ0099 NCR H2W-1A-F1-Water Stop LOC | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-10-26 | Karla Jones | 2011-11-23 16:40 | 15100- Expansion Locks Atlantic | Karla Jones
00207 |  |  | A50M0001 NCR 1st Embed out toleranc | Nonconformance Report | Terminated | NO BIC-GUPC | Construction Deficiency | 2011-11-01 | Alberto Alonzo | 2012-10-09 14:34 | 15100- Expansion Locks Atlantic | Juan Rivera
00965 |  |  | NCRP0493CS WSB Lateral Collector | Nonconformance Report | Concluded | Juan Arturo Rivera | Construction Deficiency | 2016-01-26 | Lorely Rivera | 2016-04-15 16:28 | 15200- Expansion Locks Pacific | Lorely Rivera
00181 |  |  | PQ0100 NCR N4 Wrong height & dike | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-01 | Luz Arosemena | 2011-12-01 09:47 | 15200- Expansion Locks Pacific | Luz Arosemena
00180 |  |  | PQ0082 NCR N4 Poor Compaction Emban | Nonconformance Report | Closed | Jorge Perez Blanco | Construction Deficiency | 2011-11-01 | Veronica Cash | 2013-08-28 08:55 | 15200- Expansion Locks Pacific | Luz Arosemena
00179 |  |  | PQ0081 NCR Lean concrete CU1-C-04b | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-01 | Luz Arosemena | 2012-10-13 11:36 | 15200- Expansion Locks Pacific | Luz Arosemena
00178 |  |  | PQ0076 NCR Dobies Blocks w/Rebar | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-01 | Luz Arosemena | 2012-10-18 10:56 | 15200- Expansion Locks Pacific | Luz Arosemena
00182 | Atlantic | UW-M11-F01 | AQ0114 NCR UW-M11-F01Water Stop LOC | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-08 | Karla Jones | 2012-01-05 16:06 | 15100- Expansion Locks Atlantic | Karla Jones
0096 |  |  | PQ0013 CAR Disposal Site #1 | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-08-21 | Luz Arosemena | 2012-08-21 14:59 | 15200- Expansion Locks Pacific | Luz Arosemena
00185 | Atlantic | MW-M02-F02 | AQ0109 NCR Cold Joint in MW-M02-F02 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-10 | Karla Jones | 2011-11-17 13:20 | 15100- Expansion Locks Atlantic | Karla Jones
00184 | Atlantic |  | AQ0113 NCR wall East face Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-10 | Karla Jones | 2011-11-17 14:02 | 15100- Expansion Locks Atlantic | Karla Jones
00183 | Atlantic | UW-M08-F02 | AQ0110 NCR CONC SEQ Pour UW-M08-F02 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-10 | Karla Jones | 2011-11-30 16:39 | 15100- Expansion Locks Atlantic | Karla Jones
00186 | Atlantic | CC2-B-04b&05b | AQ0102 NCR CC2-B-04b & CC2-B-05b | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-11 | Karla Jones | 2013-03-18 13:59 | 15100- Expansion Locks Atlantic | Karla Jones
00187 | Atlantic | UW-M15-C04c | AQ0111 NCR UW-M15-C04C Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-11-12 | Karla Jones | 2011-12-27 09:02 | 15100- Expansion Locks Atlantic | Karla Jones
00191 | Atlantic | UW-M23-F01 | AQ0095 NCR UW-M23-F01 Final Finish | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-15 | Zosimo Correa | 2012-03-27 11:42 | 15100- Expansion Locks Atlantic | Karla Jones
00190 | Atlantic | CU2-C02a&C02b | AQ0115 NCR CU2-C02a & CU2-C02b GEOM | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-15 | Karla Jones | 2011-11-18 16:14 | 15100- Expansion Locks Atlantic | Karla Jones
00189 | Pacific | UW-M10-C04c | PQ0102 NCR UW-M10-04c East Side | Nonconformance Report | Closed | Richard Van Hellemondt | Construction Deficiency | 2011-11-15 | Luz Arosemena | 2011-11-25 14:54 | 15200- Expansion Locks Pacific | Luz Arosemena
00188 | Pacific | UW-M21-C04c | PQ0101 NCR UW-M21-04c W Side Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-15 | Rick Montanari | 2012-02-16 11:54 | 15200- Expansion Locks Pacific | Luz Arosemena
00192 | Atlantic | CC2-D-05 | AQ0117 NCR CC2-D-05 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-16 | Karla Jones | 2011-11-18 16:28 | 15100- Expansion Locks Atlantic | Karla Jones
0095 |  |  | PQ0012 CAR ETF Files Implementation | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-08-21 | Luz Arosemena | 2012-08-21 14:35 | 15200- Expansion Locks Pacific | Luz Arosemena
00194 | Atlantic | UW-M16-C04c | AQ0118 NCR UW-M16-C04c Central Wall | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-17 | Karla Jones | 2011-12-01 08:10 | 15100- Expansion Locks Atlantic | Karla Jones
00193 | Atlantic | MW-M04- | AQ0116 NCR UOM MW-M04 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-17 | Karla Jones | 2012-01-13 11:01 | 15100- Expansion Locks Atlantic | Karla Jones
00201 | Pacific | UW-M23-F06 | PQ0106 NCR Voids UW-M23-F06 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-18 | Luz Arosemena | 2013-03-12 16:34 | 15200- Expansion Locks Pacific | Luz Arosemena
00200 | Pacific | UW-M11-W10 | NCRP0107CS UW-M11-10, UE-M10-16 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-18 | Javier Gutierrez | 2013-12-01 15:39 | 15200- Expansion Locks Pacific | Luz Arosemena
00199 | Pacific | UE-M23-F06 | PQ0105 NCR Void & Crack UE-M23-F06 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-18 | Rick Montanari | 2012-02-16 09:06 | 15200- Expansion Locks Pacific | Luz Arosemena
00198 | Pacific | H2W-6C-F03 | PQ0099 NCR Cracks H2W-6C-F03 S&N | Nonconformance Report | Closed | Javier Gutierrez | Construction Deficiency | 2011-11-18 | Veronica Cash | 2013-08-28 08:58 | 15200- Expansion Locks Pacific | Luz Arosemena
00197 | Pacific | UE-M10-F01&F02 | NCRP0098CS Honeycombs UE-M10-F01/02 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-18 | Rick Montanari | 2014-03-13 12:12 | 15200- Expansion Locks Pacific | Luz Arosemena
00196 | Pacific | UW-M10-F01&F02 | PQ0097 NCR Repair UW-M10-F01/02 QMS | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-18 | Luz Arosemena | 2012-10-06 11:31 | 15200- Expansion Locks Pacific | Luz Arosemena
00195 | Atlantic | UW-M06-F02 | AQ0119 NCR Cold Joint UW-M06-F02 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-18 | Karla Jones | 2011-12-01 09:44 | 15100- Expansion Locks Atlantic | Karla Jones
00203 | Atlantic | UW-M01-F01b | AQ0120 NCR Cold Joint UW-M01-F01-b | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-22 | Karla Jones | 2011-12-01 10:17 | 15100- Expansion Locks Atlantic | Karla Jones
0094 |  |  | AQ0038 CAR Debris & Metal Pipes | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-06-18 | Maria Ho | 2012-08-21 11:11 | 15100- Expansion Locks Atlantic | Maria Ho
00202 | Atlantic | H2W-1A-12W | AQ0121 NCR Cold Joint in H2W-1A-12W | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-22 | Karla Jones | 2011-12-06 14:44 | 15100- Expansion Locks Atlantic | Karla Jones
00204 | Pacific | H2E-3C-C04c | PQ0108 NCR Rebar Cover H2E-3C-04c | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-23 | Veronica Cash | 2013-08-28 08:59 | 15200- Expansion Locks Pacific | Luz Arosemena
00205 | Atlantic | UW-M09-F01 | AQ0122 NCR Cracks-corner UW-M09-F01 | Nonconformance Report | Closed | Maria Baz | Construction Deficiency | 2011-11-24 | Larry Ohrn | 2012-03-13 13:13 | 15100- Expansion Locks Atlantic | Karla Jones
00001 |  |  | PQ0103 NCR Missing testing Found. T | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-24 | Veronica Cash | 2013-08-28 09:02 | 15200- Expansion Locks Pacific | Luz Arosemena
00206 | Atlantic | FS-M01E | AQ0123 NCR SF-M01-E LMCl Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-25 | Karla Jones | 2011-12-06 14:17 | 15100- Expansion Locks Atlantic | Karla Jones
00211 |  |  | A55M0002 NCR FSE out Tolerance | Nonconformance Report | Terminated | NO BIC-GUPC | Construction Deficiency | 2011-11-29 | Alberto Alonzo | 2012-10-09 14:35 | 15100- Expansion Locks Atlantic | Juan Rivera
00210 | Atlantic | CC2-C-03b | AQ0124 NCR CC2-C-03b Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-29 | Karla Jones | 2012-12-26 09:58 | 15100- Expansion Locks Atlantic | Karla Jones
00209 | Pacific | H2E-2C-F02 | PQ0109 NCR H2E-2C-F02 Stirrups | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-29 | Luz Arosemena | 2012-11-13 11:01 | 15200- Expansion Locks Pacific | Luz Arosemena
00208 |  |  | PQ0080 NCR Thermocouples Not Instal | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-29 | Luz Arosemena | 2012-09-13 10:59 | 15200- Expansion Locks Pacific | Luz Arosemena
00214 | Atlantic | CC2-D-05 | AQ0127 NCR CC2-D-05 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-30 | Karla Jones | 2012-01-13 07:41 | 15100- Expansion Locks Atlantic | Karla Jones
0093 |  |  | AQ0045 CAR TEMPR DSG Planning & CTR | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-07-16 | Karla Jones | 2012-08-21 10:20 | 15100- Expansion Locks Atlantic | Karla Jones
00213 | Atlantic | CU1-2W-12a&b | AQ0126 NCR CU1-2W-12a-b Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-11-30 | Karla Jones | 2011-12-05 17:27 | 15100- Expansion Locks Atlantic | Karla Jones
00212 | Atlantic | UW-M18-F02 | AQ0125 NCR UW-M18-F02 Rebar DEF | Nonconformance Report | Closed | Maria Baz | Construction Deficiency | 2011-11-30 | Larry Ohrn | 2012-03-13 16:03 | 15100- Expansion Locks Atlantic | Karla Jones
00215 | Atlantic | ME-M16-F01 | AQ0129 NCR UOM ME-M16-F01 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-01 | Karla Jones | 2012-01-13 08:08 | 15100- Expansion Locks Atlantic | Karla Jones
00218 | Pacific | UE-M23-F06 | NCRP0110CS UE-M23-F06 Cracking | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-02 | Luz Arosemena | 2013-03-09 11:40 | 15200- Expansion Locks Pacific | Luz Arosemena
00217 | Pacific |  | NCRP0104CS #11Rebar Vertical Missed | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-02 | Veronica Cash | 2013-08-28 09:04 | 15200- Expansion Locks Pacific | Luz Arosemena
00216 | Pacific | H2W-6A-F02 | PQ0111 NCR H2W-6A-F02 Chamfer Low | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-02 | Luz Arosemena | 2012-09-19 14:41 | 15200- Expansion Locks Pacific | Luz Arosemena
00219 |  |  | AQ0009 NCR Reloc Sanitary Sewer I | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-03 | Karla Jones | 2011-12-05 10:39 | 15100- Expansion Locks Atlantic | Karla Jones
00222 | Atlantic | UW-M23-F06 | AQ0051 NCR UW-M23-F06 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-05 | Karla Jones | 2012-05-15 18:05 | 15100- Expansion Locks Atlantic | Karla Jones
00221 |  |  | AQ0013 NCR Waste MGMT MTE L Haul RD | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-05 | Karla Jones | 2011-12-05 13:29 | 15100- Expansion Locks Atlantic | Karla Jones
00220 |  |  | AQ0011 NCR Spot Audit MTE Lirio DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-05 | Karla Jones | 2011-12-05 13:56 | 15100- Expansion Locks Atlantic | Karla Jones
0092 |  |  | AQ0040 CAR Temp DSGN of Cofferdam | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-07-16 | Maria Ho | 2012-08-21 15:05 | 15100- Expansion Locks Atlantic | Karla Jones
00224 | Atlantic | MW-M04- | AQ0131 NCR UOM MW-M04-Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-07 | Karla Jones | 2012-01-13 09:15 | 15100- Expansion Locks Atlantic | Karla Jones
00223 | Pacific | CU2-C02 | PQ0113 NCR CU2-C02 Improper Lenght | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-07 | Luz Arosemena | 2011-12-28 10:45 | 15200- Expansion Locks Pacific | Luz Arosemena
00227 |  |  | AQ0015 NCR MNG CONC water S Batch P | Nonconformance Report | Closed | No Ball in Court |  | 2011-12-09 | Karla Jones | 2011-12-09 16:07 | 15100- Expansion Locks Atlantic | Karla Jones
00226 |  |  | AQ0014 NCR Delivery of the Canteen | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-09 | Karla Jones | 2011-12-09 15:03 | 15100- Expansion Locks Atlantic | Karla Jones
00225 | Pacific | UE-M11-C03c | PQ0112 NCR UE-M11-C03c Cover Low | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-09 | Veronica Cash | 2013-08-28 09:06 | 15200- Expansion Locks Pacific | Luz Arosemena
00229 | Pacific | UE-M11-C04b | PQ0115 NCR UE-M11-C04b Wall Corner | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-10 | Luz Arosemena | 2012-11-13 10:57 | 15200- Expansion Locks Pacific | Luz Arosemena
00228 | Pacific | MW-M09-F01 | NCRP0114CS MW-M09-F01 Rebar Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-10 | Javier Gutierrez | 2013-05-01 17:15 | 15200- Expansion Locks Pacific | Luz Arosemena
00232 | Atlantic | UW-M22 | AQ0130 NCR FAIL FINISH, GEOM UW-M22 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-12 | Karla Jones | 2013-03-08 12:55 | 15100- Expansion Locks Atlantic | Karla Jones
00231 | Pacific | H2E-3B-F07 | PQ0117 NCR Crack on H2E-3B-F07 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-12 | Gustavo Rivas | 2012-06-29 12:59 | 15200- Expansion Locks Pacific | Luz Arosemena
00230 | Pacific | H2E-3C-F06 | NCRP0116CS Cracks on H2E-3C-F06 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-12 | Luz Arosemena | 2013-05-18 10:36 | 15200- Expansion Locks Pacific | Luz Arosemena
0091 |  |  | AQ0044 CAR DEF on Contract Template | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-07-16 | Karla Jones | 2012-08-21 10:08 | 15100- Expansion Locks Atlantic | Karla Jones
00236 |  |  | AQ0025 NCR Over Excavation at CC2 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-13 | Karla Jones | 2011-12-13 16:10 | 15100- Expansion Locks Atlantic | Karla Jones
00235 | Atlantic | UW-M09-C04b | AQ0134 NCR UW-M09-C04b Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-13 | Karla Jones | 2012-01-13 09:22 | 15100- Expansion Locks Atlantic | Karla Jones
00234 |  |  | AQ0020 NCR Geotechnical INVESTN | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-13 | Bennie Torres | 2012-04-19 07:31 | 15100- Expansion Locks Atlantic | Karla Jones
00233 |  |  | AQ0133 NCR Main B. P. Sand out of T | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-13 | Karla Jones | 2012-02-23 10:46 | 15100- Expansion Locks Atlantic | Karla Jones
00241 | Atlantic | CC2-C-04c&05c | AQ0105 NCR CC2-C-04c & CC2-C-05c | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-14 | Karla Jones | 2013-01-21 15:54 | 15100- Expansion Locks Atlantic | Karla Jones
00240 | Atlantic | CC2-C-04a&05a | AQ0104 NCR CC2-C-04a & CC2-C-05a | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-14 | Karla Jones | 2013-02-20 09:13 | 15100- Expansion Locks Atlantic | Karla Jones
00239 | Atlantic | CC2-B-04a&05a | AQ0103 NCR CC2-B-04a & CC2-B-05a | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-14 | Karla Jones | 2013-03-18 14:20 | 15100- Expansion Locks Atlantic | Karla Jones
00238 | Atlantic | UW-M08-F02 | AQ0128 NCR UW-M08-F02 Crack & FILTR | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-14 | Karla Jones | 2012-01-30 14:08 | 15100- Expansion Locks Atlantic | Karla Jones
00237 |  |  | NCRP0119CS Victoria Disposal | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2011-12-14 | Lorely Rivera | 2014-10-06 11:11 | 15200- Expansion Locks Pacific | Luz Arosemena
00246 | Pacific | UW-M15-C04a | PQ0118 NCR UW-M15-C04a Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-15 | Luz Arosemena | 2012-10-02 09:01 | 15200- Expansion Locks Pacific | Luz Arosemena
0090 |  |  | AQ0043 CAR Audit Programme DEF | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-07-16 | Karla Jones | 2012-08-21 10:08 | 15100- Expansion Locks Atlantic | Karla Jones
00245 | Atlantic | CC2-I-03a | AQ0112 NCR CC2-I-03a Wall Surface F | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-15 | Karla Jones | 2012-12-04 15:03 | 15100- Expansion Locks Atlantic | Karla Jones
00244 | Atlantic | CC1-C05a&b&c | AQ0108 NCR CC1-C-05a, b, c | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-15 | Karla Jones | 2013-04-02 10:43 | 15100- Expansion Locks Atlantic | Karla Jones
00243 | Atlantic | CC2-C-04b&05b | AQ0107 NCR CC2-C-04b & CC2-C-05b | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-15 | Karla Jones | 2013-01-21 16:19 | 15100- Expansion Locks Atlantic | Karla Jones
00242 | Atlantic | CC2-C-03b | AQ0106 NCR CC2-C-03b Wall Surface F | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-15 | Abdiel Santos | 2013-12-10 14:18 | 15100- Expansion Locks Atlantic | Karla Jones
00250 | Atlantic | CU2-2W-12a&b | AQ0135 NCR CU2-2W-12a-b Rebar DEF | Nonconformance Report | Closed | Maria Baz | Construction Deficiency | 2011-12-19 | Larry Ohrn | 2012-03-13 16:21 | 15100- Expansion Locks Atlantic | Karla Jones
00249 | Atlantic | H2W-3C-F06 | AQ0136 NCR H2W-3C-F06 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-19 | Karla Jones | 2012-01-31 08:18 | 15100- Expansion Locks Atlantic | Karla Jones
00251 | Atlantic | CC2-B-04a | AQ0132 NCR CC2-B-04a CONC out TOL | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-23 | Karla Jones | 2012-02-16 09:55 | 15100- Expansion Locks Atlantic | Karla Jones
00260 | Pacific | CU2-C-02c | PQ0133 NCR CU2-C-02c Water Stop | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-29 | Luz Arosemena | 2012-05-09 16:18 | 15200- Expansion Locks Pacific | Luz Arosemena
00259 | Pacific | H2E-2C-F02 | PQ0130 NCR H2E-2C-F02 Bar spacing | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-29 | Luz Arosemena | 2012-11-01 15:23 | 15200- Expansion Locks Pacific | Luz Arosemena
00258 | Pacific | UW-M12-13-14 | NCRP0134CS UW-M12-13-14 Finishing | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-29 | Luz Arosemena | 2013-10-26 10:27 | 15200- Expansion Locks Pacific | Luz Arosemena
0089 |  |  | AQ0042 CAR DQP IMPL AFR02 A-2010-10 | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-07-16 | Karla Jones | 2012-08-21 10:09 | 15100- Expansion Locks Atlantic | Karla Jones
00257 | Pacific | H2W-6A-F01&W13 | PQ0126 NCR H2W-6A-F01W13 Chamfer | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-29 | Luz Arosemena | 2012-11-13 11:12 | 15200- Expansion Locks Pacific | Luz Arosemena
00256 | Pacific | LH2-MC | PQ0125 NCR Pour height strip LH2-MC | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-29 | Luz Arosemena | 2012-11-15 14:51 | 15200- Expansion Locks Pacific | Luz Arosemena
00255 |  |  | PQ0124 NCR H2E-3A-F04c Thermocouple | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-29 | Luz Arosemena | 2012-09-07 09:24 | 15200- Expansion Locks Pacific | Luz Arosemena
00254 | Pacific | CU2-1W-04 | PQ0123 NCR CU2-1W-04 Low break | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-29 | Luz Arosemena | 2012-08-28 16:26 | 15200- Expansion Locks Pacific | Luz Arosemena
00253 | Pacific | H2E-2C-F02 | NCRP0122CS H2E-2C-F02 Rebar Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-29 | Luz Arosemena | 2013-06-22 11:39 | 15200- Expansion Locks Pacific | Luz Arosemena
00252 | Pacific | H2E-3C-F04b | NCRP0120CS H2E-3C-F04b South Wall | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-12-29 | Luz Arosemena | 2013-10-26 10:24 | 15200- Expansion Locks Pacific | Luz Arosemena
00261 | Atlantic | MW-M09-F01 | AQ0139 NCR MW-M09-F01 WaterStop DEV | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-06 | Karla Jones | 2012-02-23 10:20 | 15100- Expansion Locks Atlantic | Karla Jones
00265 | Pacific | CU2-2W-13 | PQ0129 NCR Honeycomb CU2-2W-13 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-10 | Luz Arosemena | 2013-02-04 11:56 | 15200- Expansion Locks Pacific | Luz Arosemena
00264 | Pacific | UE-M12-F01 | PQ0128 NCR UE-M12-F01 stirrup wrong | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-10 | Luz Arosemena | 2012-09-12 14:34 | 15200- Expansion Locks Pacific | Luz Arosemena
00263 |  |  | NCRP0127CS Disposal #2 Access Road | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-10 | Javier Gutierrez | 2014-01-17 16:16 | 15200- Expansion Locks Pacific | Luz Arosemena
0088 |  |  | AQ0028 CAR Concrete Truck Washout | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-05-27 | Maria Ho | 2012-08-17 15:57 | 15100- Expansion Locks Atlantic | Maria Ho
00262 | Pacific | MW-M09-F01 | PQ0121 NCR MW-M9-F01 Voids | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-10 | Luz Arosemena | 2012-12-01 10:32 | 15200- Expansion Locks Pacific | Luz Arosemena
00270 | Atlantic | MW-M04-F01 | AQ0137 NCR MW-M04-F01 CET K rebar D | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-11 | Karla Jones | 2012-02-16 10:49 | 15100- Expansion Locks Atlantic | Karla Jones
00269 | Atlantic | ME-M15-F01 | AQ0142 NCR UOM ME-M15-F01 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-11 | Karla Jones | 2012-01-30 14:44 | 15100- Expansion Locks Atlantic | Karla Jones
00268 | Atlantic | MW-M16-F01 | AQ0140 NCR MW-M16-F01 WaterStop DEV | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-11 | Karla Jones | 2012-02-08 08:11 | 15100- Expansion Locks Atlantic | Karla Jones
00267 |  |  | PQ0131 NCR 1939 Fill Rock too large | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-11 | Luz Arosemena | 2012-06-07 15:01 | 15200- Expansion Locks Pacific | Luz Arosemena
00266 |  |  | PQ0132 NCR Approach Channel Exc. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-11 | Luz Arosemena | 2012-09-17 14:04 | 15200- Expansion Locks Pacific | Luz Arosemena
00274 |  |  | AQ0018 NCR Initial MTG 44 kV Line | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-12 | Karla Jones | 2012-01-12 13:00 | 15100- Expansion Locks Atlantic | Karla Jones
00273 | Atlantic | CC1-B-05 | AQ0138 NCR CC1-B05 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-12 | Karla Jones | 2012-02-11 12:09 | 15100- Expansion Locks Atlantic | Karla Jones
00272 | Atlantic | UW-M09-C03 | AQ0143 NCR UW-M09-C03 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-12 | Karla Jones | 2012-01-25 16:40 | 15100- Expansion Locks Atlantic | Karla Jones
00271 | Atlantic | UW-M03-C04 | AQ0144 NCR UW-M03-C04 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-12 | Karla Jones | 2012-01-25 17:08 | 15100- Expansion Locks Atlantic | Karla Jones
0087 |  |  | GQ0089 CAR CONC Curing & Protection | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2012-08-14 | Samuel Santamaría | 2013-01-17 08:14 | 15200- Expansion Locks Pacific | Maria Ho
00277 | Pacific | H1E-1A-F03 | PQ0135 NCR H1E-1A-F03 FORM MOVED | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-13 | Luz Arosemena | 2012-06-28 11:33 | 15200- Expansion Locks Pacific | Luz Arosemena
00276 | Atlantic | H2W-1A-W12 | AQ0145 NCR H2W-1A-W12 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-13 | Karla Jones | 2012-01-26 07:57 | 15100- Expansion Locks Atlantic | Karla Jones
00275 | Atlantic | H2W-1C-W10 | AQ0141 NCR H2W-1C-W10 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-13 | Karla Jones | 2012-01-30 15:07 | 15100- Expansion Locks Atlantic | Karla Jones
00279 | Atlantic | CC2-B-04b&05b | AQ0151 NCR CC2-B04b CONC out of TOL | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-19 | Karla Jones | 2012-02-14 13:09 | 15100- Expansion Locks Atlantic | Karla Jones
00278 | Atlantic | H2E-6D-6E | AQ0146 NCR H2E-6D-6E Water Stop DEV | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-19 | Larry Ohrn | 2012-06-04 10:02 | 15100- Expansion Locks Atlantic | Karla Jones
00284 | Atlantic | ME-M13-F02 | AQ0147 NCR ME-M13-F02 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-20 | Karla Jones | 2012-05-02 08:37 | 15100- Expansion Locks Atlantic | Karla Jones
00283 | Atlantic | ME-M14-F02 | AQ0148 NCR ME-M14-F02 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-20 | Karla Jones | 2012-05-02 08:41 | 15100- Expansion Locks Atlantic | Karla Jones
00282 | Atlantic | CC2-B-05 | AQ0092 NCR CC2-B-05 Chamfer GEOM | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-20 | Karla Jones | 2013-03-18 13:52 | 15100- Expansion Locks Atlantic | Karla Jones
00281 | Atlantic | UW-M10-F02 | AQ0150 NCR UW-M10-F01 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-20 | Karla Jones | 2012-05-02 08:45 | 15100- Expansion Locks Atlantic | Karla Jones
00280 | Atlantic | UW-M20-F01 | AQ0149 NCR UW-M20-F01 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-20 | Karla Jones | 2012-01-30 14:24 | 15100- Expansion Locks Atlantic | Karla Jones
0086 |  |  | AQ0068 CAR NcN0056 Dock 45 West | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-08-10 | Karla Jones | 2012-08-14 13:33 | 15100- Expansion Locks Atlantic | Karla Jones
00004 |  |  | P55M0003 NCR HSH Clv Lnr Ship 2 | Nonconformance Report | Closed | NO BIC-GUPC | Defective Materials | 2012-01-20 | Juan Rivera | 2014-02-27 22:15 | 15200- Expansion Locks Pacific | Maria Ho
00287 | Atlantic | UW-M06-F01 | AQ0152 NCR UW-M06-F01 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-24 | Karla Jones | 2012-02-08 07:38 | 15100- Expansion Locks Atlantic | Karla Jones
00286 |  | CU1 | NCRP0136CS CU1 Concrete Finishing | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-01-24 | Lorely Rivera | 2016-08-30 14:36 | 15200- Expansion Locks Pacific | Luz Arosemena
00285 | Pacific | UW-M10-C04b | PQ0143 NCR Crack top of UW-M10-C04B | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-24 | Luz Arosemena | 2012-09-05 15:18 | 15200- Expansion Locks Pacific | Luz Arosemena
00289 |  |  | AQ0101 NCR Sewage Line Manhole | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-25 | Karla Jones | 2012-04-12 08:55 | 15100- Expansion Locks Atlantic | Karla Jones
00288 | Atlantic | H2W-1C-W10 | AQ0153 NCR H2W-1C-W10 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-25 | Karla Jones | 2012-01-31 08:52 | 15100- Expansion Locks Atlantic | Karla Jones
00290 |  | H1E-1C-F03 | NCRP0139CS H1E-1C-F03 Rebar | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-01-26 | Luz Arosemena | 2015-09-12 10:26 | 15200- Expansion Locks Pacific | Luz Arosemena
00296 | Atlantic | UW-M12-F02 | AQ0155 NCR UW-M12-F02 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-27 | Karla Jones | 2012-03-02 10:30 | 15100- Expansion Locks Atlantic | Karla Jones
00294 | Pacific | UW-M09-C03b | PQ0145 NCR UW-M09-C03b S Forms | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-27 | Luz Arosemena | 2012-09-29 11:00 | 15200- Expansion Locks Pacific | Luz Arosemena
00293 | Pacific | CC2-A-05 | PQ0144 NCR CC2-A-05 Pouring | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-27 | Luz Arosemena | 2012-11-16 15:51 | 15200- Expansion Locks Pacific | Luz Arosemena
0085 |  |  | AQ0067 CAR Concrete Repairs | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-07-30 | Karla Jones | 2012-08-14 11:56 | 15100- Expansion Locks Atlantic | Karla Jones
00292 | Pacific | H2W-6C-F03 | PQ0137 NCR Honeycomb H2W-6C-F03 SE | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-27 | Luz Arosemena | 2012-09-29 11:10 | 15200- Expansion Locks Pacific | Luz Arosemena
00291 | Atlantic | UW-M13-C03c | AQ0156 NCR UW-M13-C03c Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-27 | Karla Jones | 2012-02-08 07:56 | 15100- Expansion Locks Atlantic | Karla Jones
00299 |  | H2W-6E-F03 | NCRP0142CS H2W-6E-F03 2d Cracks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-28 | Javier Gutierrez | 2014-01-03 16:29 | 15200- Expansion Locks Pacific | Luz Arosemena
00298 | Pacific | H2E-2C-F02 | PQ0140 NCR H2E-2C-F02 2d Cracks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-28 | Luz Arosemena | 2012-10-18 11:02 | 15200- Expansion Locks Pacific | Luz Arosemena
00297 |  | H2C-4C-F01 | NCRP0138 CS H2C-4C-F01 Water Stop | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-28 | Luz Arosemena | 2013-02-04 11:55 | 15200- Expansion Locks Pacific | Luz Arosemena
00301 | Atlantic | CC1-B-04a | AQ0158 NCR CC1-B-04a LGE V & LEAK J | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-30 | Karla Jones | 2013-03-18 14:26 | 15100- Expansion Locks Atlantic | Karla Jones
00300 | Atlantic | UW-M22-F02 | AQ0157 NCR UW-M22-F02 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-30 | Karla Jones | 2012-03-06 16:05 | 15100- Expansion Locks Atlantic | Karla Jones
00302 | Atlantic | CC1-B-04b | AQ0159 NCR CC1-B-04b CONC out TOL | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-01-31 | Karla Jones | 2012-02-16 11:23 | 15100- Expansion Locks Atlantic | Karla Jones
00303 |  | H1E-1A-F03 | NCRP0146CS H1E-1A-F03 Misalignment | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-02 | Javier Gutierrez | 2013-11-12 15:20 | 15200- Expansion Locks Pacific | Luz Arosemena
00307 | Pacific | H2E-2A-F02 | PQ0147 NCR H2E-2A-F02 Voids | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-03 | Luz Arosemena | 2012-12-01 10:38 | 15200- Expansion Locks Pacific | Luz Arosemena
0084 |  |  | AQ0065 CAR CONC Placing DEF | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-08-02 | Karla Jones | 2012-08-14 11:40 | 15100- Expansion Locks Atlantic | Karla Jones
00306 | Atlantic | UW-M20-F01 | AQ0166 NCR UW-M20-F01 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-03 | Karla Jones | 2012-05-15 11:29 | 15100- Expansion Locks Atlantic | Karla Jones
00305 | Atlantic | UW-M11-C04c | AQ0162 NCR UW-M11-C04c Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-03 | Karla Jones | 2012-02-14 14:03 | 15100- Expansion Locks Atlantic | Karla Jones
00304 | Atlantic | H2E-6D-F04 | AQ0165 NCR H2E-6D-F04 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-03 | Karla Jones | 2012-02-23 10:41 | 15100- Expansion Locks Atlantic | Karla Jones
00295 | Atlantic | UW-M14-F02 | AQ0154 NCR UW-M14-F02 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-03 | Karla Jones | 2012-02-23 10:50 | 15100- Expansion Locks Atlantic | Karla Jones
00310 |  | M01-C05b | AQ0168 NCR M01-C05b SPL, LG REB DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-06 | Karla Jones | 2012-03-06 09:11 | 15100- Expansion Locks Atlantic | Karla Jones
00309 | Atlantic | UW-M02-F01 | AQ0169 NCR UW-M02-F01 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-06 | Karla Jones | 2012-05-02 08:50 | 15100- Expansion Locks Atlantic | Karla Jones
00308 | Pacific | MW-M10-F01 & ME-M02-F01 | PQ0141 NCR MW-M10-F01 & ME-M02-F01 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-06 | Luz Arosemena | 2012-09-05 15:13 | 15200- Expansion Locks Pacific | Luz Arosemena
00248 | Atlantic | H2W-1A-W10 | AQ0163 NCR H2W-1A-W10 SPL & lack R | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-06 | Karla Jones | 2012-03-06 11:47 | 15100- Expansion Locks Atlantic | Karla Jones
00313 | Pacific | MW-M17-F02 | PQ0152 NCR MW-M17-F02 Water Stop | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-07 | Luz Arosemena | 2012-11-30 13:57 | 15200- Expansion Locks Pacific | Luz Arosemena
00312 | Atlantic | ME-M14-F02 | AQ0171 NCR ME-M14-F02 SPL,LGT,R DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-07 | Karla Jones | 2012-04-10 20:08 | 15100- Expansion Locks Atlantic | Karla Jones
0083 |  |  | AQ0041 CAR DSG QLTY Plan IMPL A-10 | Corrective Action Request | Closed | No Ball in Court | Administrative | 2012-08-14 | Karla Jones | 2012-08-14 09:05 | 15100- Expansion Locks Atlantic | Karla Jones
00311 | Atlantic | ME-M12-F02 | AQ0170 NCR ME-M12-F02 SPL,LGT,R DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-07 | Veronica Cash | 2013-08-28 09:08 | 15100- Expansion Locks Atlantic | Karla Jones
00317 | Atlantic | ME-M13-F02 | AQ0172 NCR ME-M13-F02 SEQ of pour | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-08 | Zosimo Correa | 2012-04-04 08:31 | 15100- Expansion Locks Atlantic | Karla Jones
00316 | Atlantic | ME-M10-F01c | AQ0160 NCR ME-M10-F01c Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-08 | Karla Jones | 2012-02-23 10:27 | 15100- Expansion Locks Atlantic | Karla Jones
00315 | Atlantic | UW-M13-C04 & C03c | AQ0167 NCR UW-M13_C04 & C03c S Side | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-08 | Karla Jones | 2013-01-17 09:18 | 15100- Expansion Locks Atlantic | Karla Jones
00314 | Atlantic | H2W-3A-F06 | AQ0164 NCR H2W-3A-F06 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-08 | Karla Jones | 2012-05-14 16:19 | 15100- Expansion Locks Atlantic | Karla Jones
00323 | Atlantic | ME-M11-F01c | AQ0161 NCR ME-M11-F01c Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-09 | Karla Jones | 2012-02-23 10:35 | 15100- Expansion Locks Atlantic | Karla Jones
00322 | Atlantic | H2W-3C-F05b | AQ0176 NCR H2W-3C-F05b LCK of cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-09 | Karla Jones | 2012-03-13 11:57 | 15100- Expansion Locks Atlantic | Karla Jones
00321 | Atlantic | H2W-3C-F05b | AQ0175 NCR H2W-3C-F05 b Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-09 | Karla Jones | 2012-04-14 12:11 | 15100- Expansion Locks Atlantic | Karla Jones
00320 | Atlantic | H2E-6A-W13a&c | AQ0174 NCR H2E-6A-W13 (a & c) R DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-09 | Zosimo Correa | 2012-04-04 08:25 | 15100- Expansion Locks Atlantic | Karla Jones
00319 |  |  | AQ0173 NCR Sewage Line MHL CPT | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-09 | Karla Jones | 2013-02-04 10:12 | 15100- Expansion Locks Atlantic | Karla Jones
0082 |  |  | AQ0039 CAR HAND Hazardous MAT DEF | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2012-08-14 | Maria Ho | 2012-08-21 10:37 | 15100- Expansion Locks Atlantic | Karla Jones
00318 | Pacific | CU1-C03aN | PQ0153 NCR CU1-C03a N Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-09 | Luz Arosemena | 2012-05-05 09:00 | 15200- Expansion Locks Pacific | Luz Arosemena
00325 | Atlantic | UW-M12-F01 | AQ0178 NCR UW-M12-F01 Pouring DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-10 | Karla Jones | 2012-04-18 14:01 | 15100- Expansion Locks Atlantic | Karla Jones
00324 | Atlantic | ME-M01-F02 | AQ0177 NCR ME-M01-F02 SPL Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-10 | Karla Jones | 2012-03-06 11:30 | 15100- Expansion Locks Atlantic | Karla Jones
00333 | Atlantic | ME-M04-F01 | AQ0185 NCR ME-M04-F01 CONC Damaged | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-13 | Karla Jones | 2012-05-02 08:54 | 15100- Expansion Locks Atlantic | Karla Jones
00332 | Atlantic | ME-M10-F01 | AQ0183 NCR ME-M10-F01 KCK b LCK COV | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-13 | Karla Jones | 2012-05-15 10:23 | 15100- Expansion Locks Atlantic | Karla Jones
00331 | Atlantic | MW-M03-F01 | AQ0182 NCR MW-M03-F01 KCK b cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-13 | Karla Jones | 2012-02-24 09:33 | 15100- Expansion Locks Atlantic | Karla Jones
00330 | Atlantic | CC2-A-03a&b | AQ0181 NCR CC2-A-03a,b LCK of cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-13 | Karla Jones | 2012-03-07 13:31 | 15100- Expansion Locks Atlantic | Karla Jones
00329 | Atlantic | CC2-A-03a&b | AQ0179 NCR CC2-A-03a,b LCK of cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-13 | Karla Jones | 2012-04-17 08:57 | 15100- Expansion Locks Atlantic | Karla Jones
00328 | Pacific | H1E-1C-F03 | PQ0151 NCR H1E-1C-F03 Cracks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-13 | Luz Arosemena | 2012-11-01 15:27 | 15200- Expansion Locks Pacific | Luz Arosemena
00327 | Pacific | CC2-A-04b | PQ0149 NCR CC2-A-04b Rebar Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-13 | Luz Arosemena | 2012-10-12 14:34 | 15200- Expansion Locks Pacific | Luz Arosemena
0081 |  |  | AQ0027 CAR LACK of EVI of DSG PLANN | Corrective Action Request | Closed | NO BIC-GUPC | Administrative | 2010-05-25 | Veronica Cash | 2013-08-27 16:05 | 15100- Expansion Locks Atlantic | Maria Ho
00326 | Atlantic | ME-M15-F01 | AQ0180 NCR ME-M15-F01 K a SPL Rebar | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-13 | Karla Jones | 2012-03-07 13:15 | 15100- Expansion Locks Atlantic | Karla Jones
00335 | Atlantic | H3E-6E-F06 | AQ0186 NCR LH3E-6E-F06 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-14 | Karla Jones | 2012-05-15 10:34 | 15100- Expansion Locks Atlantic | Abdiel Santos
00338 |  | H2E-1C-F03 | NCRP0156CS H2E-1C-F03 1st St Cracks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-15 | Luz Arosemena | 2013-05-18 10:28 | 15200- Expansion Locks Pacific | Luz Arosemena
00337 | Atlantic | MW-M04-F01 | AQ0187 NCR MW-M04-F01 SPL Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-15 | Karla Jones | 2012-03-02 11:04 | 15100- Expansion Locks Atlantic | Sandeep Singh
00336 | Atlantic | MW-M04-F01 | AQ0184 NCR MW-M04-F01 SPL Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-15 | Karla Jones | 2012-03-02 10:50 | 15100- Expansion Locks Atlantic | Sandeep Singh
00334 | Pacific | H2E-2A-W12b | PQ0155 NCR H2E-2A-W12b Rebar cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-15 | Luz Arosemena | 2012-09-15 09:08 | 15200- Expansion Locks Pacific | Luz Arosemena
00001 |  |  | G62M0001 NCR BRI Superbolts Ship 1 | Nonconformance Report | Terminated | NO BIC-GUPC | Defective Materials | 2012-02-15 | Alberto Alonzo | 2014-05-21 15:44 | 15000- Expansion Locks | Juan Rivera
00342 | Atlantic | H2W-1C-W09 | AQ0190 NCR H2W-1C-W09 LCK of cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-16 | Karla Jones | 2012-04-24 17:37 | 15100- Expansion Locks Atlantic | Karla Jones
00341 | Pacific | H2E-3A-F03&F02 | PQ0148 NCR H2E-3A-F03, F02 NW | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-16 | Maria Ho | 2012-08-10 08:25 | 15200- Expansion Locks Pacific | Luz Arosemena
00340 | Atlantic | UW-M11-C04a&b | AQ0189 NCR UW-M11-C04a,b LCK cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-16 | Karla Jones | 2012-05-15 11:22 | 15100- Expansion Locks Atlantic | Karla Jones
0080 |  |  | AQ0021 CAR CERT MAT Test Laboratory | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-04-16 | Maria Ho | 2012-08-13 16:27 | 15100- Expansion Locks Atlantic | Maria Ho
00339 | Atlantic | UE-M16-F01 | AQ0188 NCR UE-M16-F01 KCK b LCK COV | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-16 | Karla Jones | 2012-03-02 13:42 | 15100- Expansion Locks Atlantic | Karla Jones
00345 | Atlantic | UW-M14-F01 | AQ0195 NCR UW-M14-F01 Pouring DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-17 | Karla Jones | 2013-01-08 09:36 | 15100- Expansion Locks Atlantic | Karla Jones
00344 | Atlantic | H3E-6E-F06 | AQ0194 NCR LH3E-6E-F06 Pouring DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-17 | Karla Jones | 2012-06-19 16:39 | 15100- Expansion Locks Atlantic | Karla Jones
00343 | Atlantic | H2W-1C-W09 | AQ0191 NCR H2W-1C-W09 SPL Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-17 | Karla Jones | 2012-03-02 10:13 | 15100- Expansion Locks Atlantic | Karla Jones
00005 |  |  | A55M0003 NCR HSH Clv Lnr Ship 2 | Nonconformance Report | Closed | NO BIC-GUPC | Defective Materials | 2012-02-17 | Alberto Alonzo | 2012-10-09 14:36 | 15100- Expansion Locks Atlantic | Juan Rivera
00346 | Atlantic | MW-M03-F01 | AQ0192 NCR MW-M03-F01 KCK b LCK COV | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-18 | Karla Jones | 2012-05-01 12:57 | 15100- Expansion Locks Atlantic | Karla Jones
00350 | Atlantic | MW-M23-F08 | AQ0197 NCR MW-M23-F08 WaterStop DEV | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-22 | Zosimo Correa | 2012-03-23 09:43 | 15100- Expansion Locks Atlantic | Karla Jones
00349 | Atlantic | ME-M16-C03a | AQ0196 NCR ME-M16-C03a SPL LGT REB | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-22 | Karla Jones | 2012-03-03 10:45 | 15100- Expansion Locks Atlantic | Karla Jones
00348 | Pacific | ME-M02-F01 | PQ0160 NCR ME-M02 Embed Plate & HC | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-22 | Javier Gutierrez | 2013-01-30 17:23 | 15200- Expansion Locks Pacific | Luz Arosemena
00347 | Pacific | ME-M02-F01 | PQ0157 NCR ME-M02-F01 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-22 | Javier Gutierrez | 2013-01-30 17:34 | 15200- Expansion Locks Pacific | Luz Arosemena
0079 |  |  | AQ0026 CAR Lack of EVID on CADD REV | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-05-25 | Maria Ho | 2012-08-13 10:56 | 15100- Expansion Locks Atlantic | Maria Ho
00359 | Atlantic | MW-M15-F01 | AQ0201 NCR MW-M15-F01 KCK a LCK COV | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-23 | Karla Jones | 2012-07-03 15:37 | 15100- Expansion Locks Atlantic | Karla Jones
00355 | Atlantic | MW-M14-F02 | AQ0200 NCR MW-M14-F02 Geometry DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-23 | Karla Jones | 2012-03-02 10:38 | 15100- Expansion Locks Atlantic | Karla Jones
00354 | Atlantic | ME-M13-F01 | AQ0199 NCR ME-M13-F01 Bend REB DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-23 | Karla Jones | 2012-03-06 10:52 | 15100- Expansion Locks Atlantic | Karla Jones
00351 | Pacific | ME-M02-F01 | PQ0165 NCR ME-M02-F01 C04b | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-24 | Luz Arosemena | 2012-11-13 11:17 | 15200- Expansion Locks Pacific | Luz Arosemena
00364 | Atlantic | H2W-3C-F03 | AQ0203 NCR H2W-3C-F03 Extracover R | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-25 | Karla Jones | 2012-06-13 11:42 | 15100- Expansion Locks Atlantic | Karla Jones
00358 | Atlantic | MW-M12-F02 | AQ0205 NCR MW-M12-F02 SPL LGT Rebar | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-25 | Larry Ohrn | 2012-05-23 08:15 | 15100- Expansion Locks Atlantic | Karla Jones
00357 | Atlantic | MW-M15-F01 | AQ0204 NCR MW-M15-F01 KCK c LCK COV | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-25 | Karla Jones | 2012-03-06 10:34 | 15100- Expansion Locks Atlantic | Karla Jones
00356 | Atlantic | MW-M09-C04 | AQ0202 NCR MW-M09-C04 Lack of Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-25 | Karla Jones | 2012-03-06 10:44 | 15100- Expansion Locks Atlantic | Karla Jones
00352 |  | MW-M09-C04c | NCRP0159CS MW-M09-C04c Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-25 | Javier Gutierrez | 2013-11-12 14:52 | 15200- Expansion Locks Pacific | Luz Arosemena
00360 | Pacific | H1E-1A-F02 | PQ0154 NCR H1E-1A-F02 WStop Out | Nonconformance Report | Closed | Ramon Cascante | Construction Deficiency | 2012-02-27 | Rick Montanari | 2013-06-18 10:31 | 15200- Expansion Locks Pacific | Luz Arosemena
0078 |  |  | AQ0037 CAR Safety Traffic Road | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-05-27 | Karla Jones | 2012-08-11 10:57 | 15100- Expansion Locks Atlantic | Karla Jones
00353 | Atlantic | ME-M10-F02 | AQ0198 NCR ME-M10-F02 SPL LGT DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-27 | Karla Jones | 2012-03-06 11:01 | 15100- Expansion Locks Atlantic | Karla Jones
00361 | Pacific | H2W-6A-W10 | PQ0167 NCR H2W-6A-W10 LOW Splice | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-28 | Luz Arosemena | 2012-05-15 10:37 | 15200- Expansion Locks Pacific | Luz Arosemena
00363 |  |  | AQ0206 NCR Mindi Disposal DSR DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-02-29 | Karla Jones | 2013-01-14 16:59 | 15100- Expansion Locks Atlantic | Karla Jones
00362 | Atlantic | MW-M12-F02 | AQ0207 MW-M12-F02 Rebar Spliced DEF | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2012-02-29 | Karla Jones | 2013-02-18 10:23 | 15100- Expansion Locks Atlantic | Karla Jones
00368 | Pacific | H2E-1C-F03 & ME-M04-C04a | PQ0158 NCR H2E-1C-F03 ME-M04-C04a | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-02 | Luz Arosemena | 2013-01-12 07:36 | 15200- Expansion Locks Pacific | Luz Arosemena
00367 | Atlantic | MW-M21-F01 | AQ0209 NCR MW-M21-F01 CONC DMGD | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-02 | Karla Jones | 2012-06-13 11:23 | 15100- Expansion Locks Atlantic | Karla Jones
00366 | Atlantic | ME-M02-F01 | AQ0208 NCR ME-M02-F01 WaterStop DEV | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-02 | Larry Ohrn | 2012-09-21 08:15 | 15100- Expansion Locks Atlantic | Karla Jones
00365 | Atlantic | MW-M14-F02 | AQ0193 NCR MW-M14-F02 SPL LGT R DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-02 | Karla Jones | 2012-06-13 13:04 | 15100- Expansion Locks Atlantic | Karla Jones
00372 |  | UE-M01-F02 | NCRP0168CS UE-M01-F02 Stirrups | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-05 | Luz Arosemena | 2014-02-05 09:15 | 15200- Expansion Locks Pacific | Luz Arosemena
00375 | Pacific | ME-M02-F01 | PQ0170 NCR ME-M02-F01 N. Water Stop | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-06 | Luz Arosemena | 2012-10-23 10:31 | 15200- Expansion Locks Pacific | Luz Arosemena
0077 |  |  | AQ0036 CAR Accident RPT Procedure F | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-09-01 | Karla Jones | 2012-08-11 10:26 | 15100- Expansion Locks Atlantic | Karla Jones
00374 | Pacific | MW-M04-F01 | PQ0166 NCR MW-M04-F01 Joint leakage | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-06 | Luz Arosemena | 2012-08-21 08:51 | 15200- Expansion Locks Pacific | Luz Arosemena
00373 | Pacific | ME-M04-C04c | PQ0172 NCR ME-M04-C04c Rebar Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-06 | Luz Arosemena | 2012-08-28 16:33 | 15200- Expansion Locks Pacific | Luz Arosemena
00376 |  | MW-M02-F02 | NCRP0173CS MW-M02-F02 Surface Irreg | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2012-03-07 | Luz Arosemena | 2013-02-06 10:11 | 15200- Expansion Locks Pacific | Luz Arosemena
00383 | Atlantic | MW-M10-F01 | AQ0215 NCR MW-M10-F01 Kck b Reb def | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-08 | Karla Jones | 2012-05-02 08:57 | 15100- Expansion Locks Atlantic | Abdiel Santos
00378 |  |  | AQ0211 NCR APPR CHAN NOT FOLLOW QMS | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-08 | Karla Jones | 2012-06-13 13:20 | 15100- Expansion Locks Atlantic | Karla Jones
00377 | Pacific | UW-M02-F02 | PQ0169 NCR UW-M02-F02 Rebar Misloc. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-08 | Luz Arosemena | 2012-10-12 14:40 | 15200- Expansion Locks Pacific | Luz Arosemena
00385 | Atlantic | UW-M02-C04 | AQ0216 NCR UW-M02-C04 Large voids | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-09 | Karla Jones | 2012-12-26 10:36 | 15100- Expansion Locks Atlantic | Karla Jones
00384 | Atlantic | UW-M09-C02 | AQ0214 NCR UW-M09-C02 Reb Insta DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-09 | Maria Ho | 2012-03-28 09:08 | 15100- Expansion Locks Atlantic | Karla Jones
00380 |  |  | AQ0213 NCR Const Def Geom out LUC | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-10 | Gloria Leguias | 2013-07-24 10:15 | 15100- Expansion Locks Atlantic | Karla Jones
00371 |  |  | AQ0026 NCR Crushing P DISCH of Mud | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-10 | Karla Jones | 2012-03-03 10:18 | 15100- Expansion Locks Atlantic | Karla Jones
0076 |  |  | AQ0034 CAR FAIL to follow HS INST | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-05-27 | Karla Jones | 2012-08-11 09:44 | 15100- Expansion Locks Atlantic | Karla Jones
00386 | Pacific | CU2-2E-12 | PQ0177 NCR CU2-2E-12 Extra cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-12 | Luz Arosemena | 2012-09-26 09:02 | 15200- Expansion Locks Pacific | Luz Arosemena
00387 | Pacific | H3E-1C-F02 | PQ0180 NCR H3E-1C-F02 Low Rebar Cov | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-14 | Luz Arosemena | 2012-11-24 10:07 | 15200- Expansion Locks Pacific | Luz Arosemena
00392 |  |  | AQ0212 NCR Approach Channel Backfil | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-16 | Karla Jones | 2012-08-27 15:18 | 15100- Expansion Locks Atlantic | Karla Jones
00391 | Atlantic | MW-M02-F01 | AQ0218 NCR MW-M02-F01 Kic b Reb Def | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-16 | Veronica Cash | 2013-08-28 09:10 | 15100- Expansion Locks Atlantic | Karla Jones
00390 | Pacific | ME-M02-F01 | PQ0174 NCR ME-M02-F01 N. Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-16 | Luz Arosemena | 2012-06-28 11:46 | 15200- Expansion Locks Pacific | Luz Arosemena
00389 | Atlantic | H2E-6E-F02 | AQ0217 NCR H2E-6E-F02 Cracks Observ | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-16 | Maria Ho | 2012-03-28 08:36 | 15100- Expansion Locks Atlantic | Karla Jones
00388 | Atlantic | UW-M03-C03b | AQ0210 NCR UW-M03-C03b Form INS DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-16 | Karla Jones | 2013-01-10 09:41 | 15100- Expansion Locks Atlantic | Karla Jones
00398 | Atlantic | ME-M15-F01 | AQ0222 NCR ME-M15-F01 Kick bars out | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-17 | Karla Jones | 2012-04-10 20:19 | 15100- Expansion Locks Atlantic | Karla Jones
00397 | Atlantic | H3W-1C-F03 | AQ0220 NCR H3W-1C-F03 Water Seepag | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-17 | Karla Jones | 2012-07-03 15:14 | 15100- Expansion Locks Atlantic | Karla Jones
00396 | Pacific | MW-M13-F02 | PQ0183 NCR MW-M13-F02 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-17 | Rick Montanari | 2012-07-27 15:32 | 15200- Expansion Locks Pacific | Luz Arosemena
0075 |  |  | PE8054-CAR Absence of Flyers in bus | Corrective Action Request | Closed | Jorge Gomez | Environmental Situation | 2012-08-31 | Tamira Baird | 2015-09-04 13:29 | 15200- Expansion Locks Pacific | Gonzalo Menendez
00395 | Atlantic | MW-M21-F01 | AQ0219 NCR MW-M21-F01 KIC c REB DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-17 | Karla Jones | 2012-07-03 15:49 | 15100- Expansion Locks Atlantic | Karla Jones
00394 | Pacific | H2W-6A-W11 | PQ0186 NCR H2W-6A-W11 Rebar Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-17 | Luz Arosemena | 2012-06-19 08:41 | 15200- Expansion Locks Pacific | Luz Arosemena
00393 | Pacific | CC2-F-05 | PQ0184 NCR CC2-F05 Rebar Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-17 | Javier Gutierrez | 2012-04-24 07:59 | 15200- Expansion Locks Pacific | Luz Arosemena
00400 | Atlantic | H3E-6D-F04 | AQ0223 NCR H3E-6D-F04 Lack REB DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-21 | Karla Jones | 2012-04-18 12:49 | 15100- Expansion Locks Atlantic | Zosimo Correa
00399 | Pacific | UW-M02-F02b | PQ0179 NCR UW-M02-F02b Voids | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-21 | Veronica Cash | 2013-08-28 09:12 | 15200- Expansion Locks Pacific | Luz Arosemena
00402 | Atlantic | H2W-3C-F04 | AQ0226 NCR H2W-3C-F04 CONC out of T | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-26 | Karla Jones | 2012-07-24 15:29 | 15100- Expansion Locks Atlantic | Zosimo Correa
00401 | Atlantic | UW-M17-F01 | AQ0221 NCR UW-M17-F01 Kicker b Lack | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-26 | Maria Ho | 2012-03-28 08:42 | 15100- Expansion Locks Atlantic | Zosimo Correa
00408 | Atlantic | ME-M22-F01 | AQ0229 NCR LMC ME-M22-F01 Lack Cov | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-27 | Karla Jones | 2012-05-02 13:14 | 15100- Expansion Locks Atlantic | Maria Ho
00406 | Pacific | UW-M11-C02 | PQ0188 NCR UW-M11-C02 Low Concrete | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-27 | Luz Arosemena | 2012-09-19 14:45 | 15200- Expansion Locks Pacific | Luz Arosemena
00405 |  |  | PQ0182 NCR Batch Plant Silica Fume | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-27 | Rick Montanari | 2012-12-12 11:05 | 15200- Expansion Locks Pacific | Luz Arosemena
0074 |  |  | AQ0033 CAR Sanitary & Safety COND | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-05-27 | Karla Jones | 2012-08-11 09:11 | 15100- Expansion Locks Atlantic | Karla Jones
00404 | Pacific | H1E-1C-W10 | PQ0193 NCR H1E-1C-W10 Low Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-27 | Luz Arosemena | 2012-05-03 11:49 | 15200- Expansion Locks Pacific | Luz Arosemena
00403 |  | UE-M21-C06a | NCRP0185CS UE-M21-C06a Honeycomb | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-27 | Javier Gutierrez | 2013-11-25 09:50 | 15200- Expansion Locks Pacific | Luz Arosemena
00379 | Atlantic | MW-M09-F01 | AQ0228 NCR LMC MW-M09-F01 LCK of CO | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-27 | Karla Jones | 2012-08-13 15:58 | 15100- Expansion Locks Atlantic | Karla Jones
00006 |  |  | A55M0004 NCR HSH Clv Lnr Ship 4 | Nonconformance Report | Closed | NO BIC-GUPC | Defective Materials | 2012-03-27 | Juan Rivera | 2012-07-30 05:27 | 15100- Expansion Locks Atlantic | Juan Rivera
00407 | Atlantic | H3W-1A-F02 | AQ0225 NCR H3W-1A-F02 Seepage OBS | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-28 | Karla Jones | 2012-06-13 11:31 | 15100- Expansion Locks Atlantic | Zosimo Correa
00001 |  |  | G62M0001 NCR MTI Defects in Coating | Nonconformance Report | Terminated | NO BIC-GUPC | Defective Materials | 2012-03-28 | Alberto Alonzo | 2014-05-21 15:51 | 15000- Expansion Locks | Maria Ho
00001 |  |  | G50M0001 NCR CIM Lack Fusion Weld | Nonconformance Report | Closed | NO BIC-GUPC | Defective Materials | 2012-03-29 | Alberto Alonzo | 2014-05-21 08:37 | 15000- Expansion Locks | Maria Ho
00411 | Atlantic | UW-M02-C04b | AQ0227 NCR UW-M02-C04b CONC out TOL | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-30 | Karla Jones | 2012-06-11 08:11 | 15100- Expansion Locks Atlantic | Zosimo Correa
00410 | Pacific | MW-M15-F01 | PQ0189 NCR MW-M15-F01 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-30 | Luz Arosemena | 2012-05-03 13:38 | 15200- Expansion Locks Pacific | Luz Arosemena
00409 |  | CU2-2E-12-A-B | NCRP0190CS CU2-2E-12A-B Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-30 | Luz Arosemena | 2014-10-15 09:41 | 15200- Expansion Locks Pacific | Luz Arosemena
0073 |  |  | AQ0032 CAR EXC Clearance RQ NCN0040 | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-06-02 | Karla Jones | 2012-08-10 15:39 | 15100- Expansion Locks Atlantic | Karla Jones
00414 |  |  | AQ0233 NCR Mirador Slop without QMS | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-03-31 | Karla Jones | 2012-07-31 09:27 | 15100- Expansion Locks Atlantic | Zosimo Correa
00413 |  |  | P55M0004 NCR FSE Valves OOT | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-03-31 | Juan Rivera | 2014-02-27 22:11 | 15200- Expansion Locks Pacific | Juan Rivera
00412 |  |  | P55M0002 NCR FSE out Tolerance | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2012-03-31 | Juan Rivera | 2014-06-03 08:39 | 15200- Expansion Locks Pacific | Juan Rivera
00416 | Pacific | H1E-3C-F04b | PQ0195 NCR HIE-3C-F04b Rebar Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-02 | Luz Arosemena | 2012-05-03 11:36 | 15200- Expansion Locks Pacific | Luz Arosemena
00415 |  |  | A55M0005 NCR FSE Valves OOT | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-04-02 | Martin Duran | 2013-07-11 11:30 | 15100- Expansion Locks Atlantic | Juan Rivera
00381 | Atlantic | H2E-6C-F02 | AQ0234 NCR H2E-6C-F02 WS Location | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-03 | Karla Jones | 2012-07-03 14:55 | 15100- Expansion Locks Atlantic | Karla Jones
00419 |  |  | A50M0002 NCR FSE Lock Gates OOT | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-04-04 | Alberto Alonzo | 2012-10-09 14:34 | 15100- Expansion Locks Atlantic | Alberto Alonzo
00418 | Atlantic | MW-M13-F01 | AQ0232 NCR MW-M13-F01 KCK b REB DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-04 | Karla Jones | 2012-07-18 16:23 | 15100- Expansion Locks Atlantic | Zosimo Correa
00417 | Atlantic | H3W-1A-F01 | AQ0238 NCR H3W-1A-F01 Rebar Moved | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-04 | Karla Jones | 2012-06-11 07:54 | 15100- Expansion Locks Atlantic | Zosimo Correa
00423 |  | H3E-1A-F02 | NCRP0191CS H3E-1A-F02 Void & Crack | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-05 | Luz Arosemena | 2013-05-28 10:38 | 15200- Expansion Locks Pacific | Luz Arosemena
0072 |  |  | AQ0031 CAR LCK Coordinate NCN 0039 | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-06-02 | Karla Jones | 2012-08-10 15:13 | 15100- Expansion Locks Atlantic | Karla Jones
00422 | Pacific | MW-M09-C04b | PQ0181 NCR MW-M09-C04 B Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-05 | Javier Gutierrez | 2012-10-29 09:49 | 15200- Expansion Locks Pacific | Luz Arosemena
00421 | Pacific | H3E-1C-F03 | PQ0171 NCR H3E-1a, 1C-F03 Voids | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-05 | Luz Arosemena | 2012-08-11 10:31 | 15200- Expansion Locks Pacific | Luz Arosemena
00420 |  | ME-M16-F01 | NCRP0164CS Honeycombs ME-M16-F01 S. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-05 | Luz Arosemena | 2013-08-23 15:23 | 15200- Expansion Locks Pacific | Luz Arosemena
00424 | Atlantic | MW-M11-C04a | AQ0235 NCR MW-M11-C04a CONC out TOL | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-09 | Karla Jones | 2013-01-29 15:29 | 15100- Expansion Locks Atlantic | Karla Jones
00425 | Atlantic | LE-M16-F01 | AQ0230 NCR LE-M16-F01 REB INST DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-12 | Karla Jones | 2012-04-18 14:47 | 15100- Expansion Locks Atlantic | Karla Jones
00003 |  |  | A62M0001 NCR BRI Superbolts Ship 1 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-04-12 | Alberto Alonzo | 2012-12-07 10:51 | 15100- Expansion Locks Atlantic | Alberto Alonzo
00002 |  |  | P62M0001 NCR BRI Superbolts Ship 1 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-12 | Juan Rivera | 2013-06-18 12:53 | 15200- Expansion Locks Pacific | Alberto Alonzo
00430 | Pacific | LE-M02-F01 | NCRP0208CS LE-M02-F01 Lack of cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-13 | Luz Arosemena | 2013-09-21 11:37 | 15200- Expansion Locks Pacific | Luz Arosemena
00429 | Pacific | H2E-2A-F01 | NCRP0199CS H2E-2A-F01 Lack of Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-13 | Luz Arosemena | 2013-05-02 11:13 | 15200- Expansion Locks Pacific | Luz Arosemena
00428 | Atlantic | H3W-3C-F06 | AQ0224 NCR H3W-3C-F06 Rebar lack & | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-13 | Karla Jones | 2012-05-21 08:48 | 15100- Expansion Locks Atlantic | Karla Jones
0071 |  |  | AQ0030 CAR Utilities Communication | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-06-02 | Karla Jones | 2012-08-10 14:24 | 15100- Expansion Locks Atlantic | Karla Jones
00427 | Pacific | ME-M09-F01 | NCRP0162CS ME-M09-F01 Voids | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-13 | Luz Arosemena | 2013-02-14 15:38 | 15200- Expansion Locks Pacific | Luz Arosemena
00426 | Pacific | ME-M15-F01 | NCRP0161CS ME-M15-F01 Voids | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-13 | Luz Arosemena | 2013-10-02 11:06 | 15200- Expansion Locks Pacific | Luz Arosemena
00432 |  | LW-M03 | NCRP0198CS LW-M03 & 05 Cracks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-16 | Javier Gutierrez | 2013-12-01 14:57 | 15200- Expansion Locks Pacific | Luz Arosemena
00003 |  |  | A62M0002 NCR MTI Defects in Coating | Nonconformance Report | Closed | No Ball in Court | Defective Materials | 2012-04-16 | Juan Rivera | 2014-06-03 08:36 | 15100- Expansion Locks Atlantic | Alberto Alonzo
00002 |  |  | P62M0002 NCR MTI Defects in Coating | Nonconformance Report | Closed | No Ball in Court | Defective Materials | 2012-04-16 | Juan Rivera | 2013-06-18 12:53 | 15200- Expansion Locks Pacific | Alberto Alonzo
00436 |  |  | AQ0241 NCR LLC Monoliths WS DEV | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-17 | Karla Jones | 2012-07-24 14:30 | 15100- Expansion Locks Atlantic | Karla Jones
00435 | Atlantic | MW-M21-F01 | AQ0243 NCR CRK in MW-M21-F01 KCK b | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-17 | Karla Jones | 2012-06-25 16:34 | 15100- Expansion Locks Atlantic | Karla Jones
00434 | Atlantic | MW-M10-C03a | AQ0242 NCR MW-M10-C03a COMPCT LCK | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-17 | Karla Jones | 2013-01-29 15:40 | 15100- Expansion Locks Atlantic | Karla Jones
00433 | Atlantic | UW-M18-C04c | AQ0244 NCR UW-M18-C04c CONC out TOL | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-17 | Karla Jones | 2012-05-09 07:39 | 15100- Expansion Locks Atlantic | Karla Jones
00438 |  |  | NCRP0202CS Curing all areas | Nonconformance Report | Terminated | Richard Van Hellemondt | Construction Deficiency | 2012-04-19 | Javier Gutierrez | 2013-03-14 11:47 | 15200- Expansion Locks Pacific | Luz Arosemena
0070 |  |  | AQ0029 CAR Eathworks OTSDE Boundary | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-05-27 | Karla Jones | 2012-08-10 13:25 | 15100- Expansion Locks Atlantic | Karla Jones
00437 | Atlantic | H3C-4A-F03 | AQ0240 NCR H3C-4A-F03 Visible Joint | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-19 | Karla Jones | 2012-05-09 07:32 | 15100- Expansion Locks Atlantic | Karla Jones
00440 | Pacific | H2E-2B-F02 | PQ0178 NCR H2E-2B-F02 Fissuring | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-20 | Luz Arosemena | 2012-10-18 11:11 | 15200- Expansion Locks Pacific | Luz Arosemena
00439 | Pacific | H1E-1A-F02 | PQ0175 NCR H1E-1A & H1E-1C F02, 03 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-20 | Luz Arosemena | 2012-10-13 11:20 | 15200- Expansion Locks Pacific | Luz Arosemena
00382 | Pacific | H3E-1A-W13 | PQ0207 NCR H3E-1A-W13 Low Cov S Fac | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-21 | Luz Arosemena | 2012-05-25 14:29 | 15200- Expansion Locks Pacific | Abdiel Santos
00442 | Pacific | H1E-1C-W09 | NCRP0209CS H1E-1C-W09 Low cover S. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-23 | Luz Arosemena | 2013-05-02 10:48 | 15200- Expansion Locks Pacific | Luz Arosemena
00441 | Atlantic | H2C-4C-F03 | AQ0239 NCR H2C-4C-F03 Visible Joint | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-23 | Karla Jones | 2012-05-09 07:13 | 15100- Expansion Locks Atlantic | Karla Jones
00446 | Atlantic | ME-M12-F01 | AQ0248 NCR ME-M12-F01KCKa Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-24 | Larry Ohrn | 2012-08-21 14:45 | 15100- Expansion Locks Atlantic | Karla Jones
00445 | Atlantic | LW-M04-F01 | AQ0249 NCR LW-M04-F01 LCK of COV DF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-24 | Karla Jones | 2012-05-02 09:04 | 15100- Expansion Locks Atlantic | Karla Jones
00444 | Atlantic | H2E-6C-W13 | AQ0246 NCR H2E-6C-W13 CONC out TOL | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-24 | Karla Jones | 2012-10-24 11:04 | 15100- Expansion Locks Atlantic | Karla Jones
00443 | Pacific | H3E-1A-F02 | PQ0187 NCR H3E-1A-F02 Water Stop | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-24 | Luz Arosemena | 2012-05-25 14:20 | 15200- Expansion Locks Pacific | Luz Arosemena
0069 |  |  | AQ0023 CAR 1939 Excavation Exceedin | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-05-04 | Maria Ho | 2012-08-10 11:32 | 15100- Expansion Locks Atlantic | Maria Ho
00447 | Pacific | MW-M02-F01 | PQ0201 NCR MW-M02-F01 Reinforcing | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-28 | Luz Arosemena | 2012-07-25 14:11 | 15200- Expansion Locks Pacific | Luz Arosemena
00001 |  |  | PQ0203 NCR Borinquen Dam Dewatering | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-04-28 | Luz Arosemena | 2012-05-25 14:56 | 15200- Expansion Locks Pacific | Luz Arosemena
00449 | Pacific | H1E-1C-F03&F02 | PQ0211 NCR H1E-1C-F03 & F02 Leaking | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-01 | Luz Arosemena | 2012-06-06 11:23 | 15200- Expansion Locks Pacific | Luz Arosemena
00448 | Pacific | H1W-6C-F03 | PQ0210 NCR H1W-6C-F03 East Crack | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-01 | Luz Arosemena | 2012-09-05 15:23 | 15200- Expansion Locks Pacific | Luz Arosemena
00002 |  |  | NCRP0200CS Disposal 12 Compaction | Nonconformance Report | Terminated | NO BIC-GUPC | Construction Deficiency | 2012-05-01 | Lorely Rivera | 2015-09-12 11:57 | 15200- Expansion Locks Pacific | Luz Arosemena
00451 | Pacific | H2E-2C-W06 | NCRP0204CS H2E-2C-W06 Concrete Pour | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-02 | Luz Arosemena | 2014-02-07 14:45 | 15200- Expansion Locks Pacific | Luz Arosemena
00450 | Pacific | H1W-6B-F02 | PQ0212 NCR H1W-6B-F02 SMC-P11-P1 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-02 | Luz Arosemena | 2013-01-23 08:30 | 15200- Expansion Locks Pacific | Luz Arosemena
00452 | Pacific | H2W-6A-W07 | PQ0219 NCR H2W-6A-W07 Formwork Move | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-03 | Rick Montanari | 2012-07-05 11:17 | 15200- Expansion Locks Pacific | Luz Arosemena
00455 |  |  | AQ0250 NCR Main B.P Sand out of TOL | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-04 | Karla Jones | 2012-05-28 07:20 | 15100- Expansion Locks Atlantic | Karla Jones
00454 | Atlantic | LE-M03-F01 | AQ0252 NCR LE-M03-F01 KCK b REB DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-04 | Karla Jones | 2012-06-26 07:46 | 15100- Expansion Locks Atlantic | Karla Jones
0068 |  |  | AQ0126 CAR S-10F,14B & 3C W/O SMPLS | Corrective Action Request | Closed | No Ball in Court | Administrative | 2011-08-12 | Karla Jones | 2012-11-01 14:23 | 15100- Expansion Locks Atlantic | Karla Jones
00453 | Atlantic | LW-M16-F01 | AQ0251 NCR LW-M16-F01 KCK b REB DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-04 | Karla Jones | 2012-07-03 15:26 | 15100- Expansion Locks Atlantic | Karla Jones
00459 | Pacific | H2E-1B-F02 | NCRP0228CS H2E-1B-F02 Water flow | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-08 | Javier Gutierrez | 2013-11-12 15:05 | 15200- Expansion Locks Pacific | Luz Arosemena
00458 |  | H2W-6B-F01 | NCRP0227CS H2W-6B-F01 Over cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-08 | Luz Arosemena | 2013-03-25 17:42 | 15200- Expansion Locks Pacific | Luz Arosemena
00457 |  | H1E-1C-W08 | NCRP0226CS H1E-1C-W08 Low Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-08 | Luz Arosemena | 2013-06-28 10:52 | 15200- Expansion Locks Pacific | Luz Arosemena
00456 | Atlantic | H2E-6B-F01 | AQ0253 NCR H2E-6B-F01 LCK of COMPCT | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-08 | Karla Jones | 2012-05-26 10:32 | 15100- Expansion Locks Atlantic | Karla Jones
00461 | Atlantic | H3W-3C-F06 | AQ0254 NCR H3W-3C-F06 KCK c REB DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-09 | Karla Jones | 2012-05-17 13:36 | 15100- Expansion Locks Atlantic | Karla Jones
00460 |  | LW-M03-C04c | NCRP0218CS LW-M03-C04c Low cover | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2012-05-09 | Luz Arosemena | 2013-02-06 10:12 | 15200- Expansion Locks Pacific | Luz Arosemena
00468 | Pacific | LW-M03-C04a&c | PQ0230 NCR LW-M03C04 a, c Chamfer | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-10 | Luz Arosemena | 2012-06-02 09:09 | 15200- Expansion Locks Pacific | Luz Arosemena
00467 |  | LW-M05 | NCRP0214CS LW-M05 N. Crack & Honeyc | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-10 | Luz Arosemena | 2013-09-21 11:43 | 15200- Expansion Locks Pacific | Luz Arosemena
00466 | Atlantic | H3W-3C-F06 | AQ0255 NCR H3W-3C-F06 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-10 | Larry Ohrn | 2012-08-21 15:07 | 15100- Expansion Locks Atlantic | Karla Jones
0067 |  |  |  | Corrective Action Request | Void | No Ball in Court |  |  | Maria Ho | 2012-08-27 08:32 | 15100- Expansion Locks Atlantic | Karla Jones
00465 | Pacific | H3E-3A-F05b | PQ0220 NCR H3E-3A-F05B Mass Concret | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-10 | Luz Arosemena | 2012-06-02 11:40 | 15200- Expansion Locks Pacific | Luz Arosemena
00464 |  | LW-M05 | NCRP0216CS LW-M05 South Crack | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-10 | Luz Arosemena | 2013-09-21 11:47 | 15200- Expansion Locks Pacific | Luz Arosemena
00463 | Pacific | LW-M03 | PQ0215 NCR LW-M03 North Crack | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-10 | Luz Arosemena | 2012-09-06 10:01 | 15200- Expansion Locks Pacific | Luz Arosemena
00462 |  |  | PQ0213 NCR Defective Rebars | Nonconformance Report | Closed | No Ball in Court | Other | 2012-05-10 | Luz Arosemena | 2012-08-21 09:00 | 15200- Expansion Locks Pacific | Luz Arosemena
00477 | Pacific | LE-M02-C04c | PQ0229 NCR LE-M02-C04c Chamfer R. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-14 | Luz Arosemena | 2012-07-16 15:41 | 15200- Expansion Locks Pacific | Luz Arosemena
00476 | Pacific | LE-M02 | PQ0225 NCR LE-M02 Water filtration | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-14 | Luz Arosemena | 2012-06-06 11:17 | 15200- Expansion Locks Pacific | Luz Arosemena
00475 | Pacific | LW-M09-F01&F02 | PQ0224 NCR LW-M09-F01/02 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-14 | Luz Arosemena | 2012-06-21 11:02 | 15200- Expansion Locks Pacific | Luz Arosemena
00474 | Pacific | LE-M04 | PQ0223 NCR LE-M04 NS Honeycombs F01 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-14 | Luz Arosemena | 2012-07-16 15:26 | 15200- Expansion Locks Pacific | Luz Arosemena
00473 | Pacific | LE-M02 | PQ0217 NCR LE-M02 South Cracks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-14 | Luz Arosemena | 2012-11-15 14:55 | 15200- Expansion Locks Pacific | Luz Arosemena
00472 | Pacific | LW-M11-F01 | PQ0221 NCR LW-M11-F01 MC less 60cm | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-14 | Luz Arosemena | 2012-07-20 11:27 | 15200- Expansion Locks Pacific | Luz Arosemena
0066 |  |  | AQ0120 CAR Rock Anchor INST & TEST | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-02-09 | Karla Jones | 2012-08-09 15:01 | 15100- Expansion Locks Atlantic | Karla Jones
00471 | Pacific | LW-M11 | PQ0176 NCR LW-M11 NS Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-14 | Luz Arosemena | 2012-06-21 15:03 | 15200- Expansion Locks Pacific | Luz Arosemena
00470 |  | MW-M17-C04b | NCRP0222CS MW-M17-C04b Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-14 | Luz Arosemena | 2013-03-20 13:46 | 15200- Expansion Locks Pacific | Luz Arosemena
00469 | Atlantic | H3W-1C-W13 | AQ0256 NCR H3W-1C-W13 REB DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-14 | Karla Jones | 2012-06-26 07:51 | 15100- Expansion Locks Atlantic | Karla Jones
00478 | Atlantic | LE-M09-F01 | AQ0257 NCR LE-M09-F01 LCK of COV | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-15 | Karla Jones | 2012-06-13 13:15 | 15100- Expansion Locks Atlantic | Karla Jones
00004 |  |  | G62M0002 NCR MTI Marine Bollards | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-05-16 | Alberto Alonzo | 2014-05-21 15:52 | 15000- Expansion Locks | Alberto Alonzo
00479 | Pacific | ME-M02-C04b | PQ0236 NCR ME-M2-C04b Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-19 | Luz Arosemena | 2012-10-12 14:55 | 15200- Expansion Locks Pacific | Luz Arosemena
00482 | Atlantic | UW-M21-C04 | AQ0260 NCR UW-M21-C04 REB INST | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-21 | Karla Jones | 2012-07-13 11:13 | 15100- Expansion Locks Atlantic | Karla Jones
00481 | Atlantic | H3W-3C-F05b | AQ0259 NCR H3W-3C-F05 b Starter Bar | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-21 | Karla Jones | 2012-06-26 07:35 | 15100- Expansion Locks Atlantic | Karla Jones
00480 | Atlantic | MW-M01-C05a | AQ0258 NCR MW-M01-C05a REB INST DEF | Nonconformance Report | Closed | Roberto Febbroni | Construction Deficiency | 2012-05-21 | Veronica Cash | 2013-08-28 09:14 | 15100- Expansion Locks Atlantic | Karla Jones
00486 | Pacific | H3E-1C-W12 | PQ0239 NCR H3E-1C-W12 Lack Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-22 | Luz Arosemena | 2012-08-04 11:42 | 15200- Expansion Locks Pacific | Luz Arosemena
0065 |  |  | AQ0012 CAR H&S Equipment Checklist | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-03-04 | Maria Ho | 2012-08-09 14:35 | 15100- Expansion Locks Atlantic | Maria Ho
00485 | Pacific | H1E-5A-F02 | PQ0235 NCR H1E-5A-F02 Water Stop | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-22 | Luz Arosemena | 2012-08-24 09:01 | 15200- Expansion Locks Pacific | Luz Arosemena
00484 | Pacific | LW-M11-F02 | NCRP0233CS LW-M11-F02 Crack | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-22 | Luz Arosemena | 2014-10-16 09:22 | 15200- Expansion Locks Pacific | Luz Arosemena
00483 | Pacific | LW-M09-F02 | PQ0232 NCR LW-M09-F02 Crack 0.50mm | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-22 | Luz Arosemena | 2012-07-16 15:50 | 15200- Expansion Locks Pacific | Luz Arosemena
00487 | Pacific | LE-M02-F01 & LE-M04-F01 | PQ0240 NCR LE-M2/M4-F01 WS Misalig | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-23 | Luz Arosemena | 2012-09-29 11:05 | 15200- Expansion Locks Pacific | Luz Arosemena
00488 |  | MW-M01-C05b | NCRP0206CS MW-M01-C05b Lack Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-24 | Luz Arosemena | 2013-05-29 11:18 | 15200- Expansion Locks Pacific | Luz Arosemena
00489 | Pacific | ME-M16-F04c | PQ0237 NCR ME-M16-F04c Honeycomb | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-25 | Luz Arosemena | 2012-09-15 09:26 | 15200- Expansion Locks Pacific | Luz Arosemena
00495 |  | LE-M11 | PQ0246 NCR LE-M11-North Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-28 | Luz Arosemena | 2012-07-20 11:35 | 15200- Expansion Locks Pacific | Luz Arosemena
00494 | Pacific | LE-M04-F01 | PQ0243 NCR LE-M04-F01 WS Misalig | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-28 | Luz Arosemena | 2012-08-22 10:11 | 15200- Expansion Locks Pacific | Luz Arosemena
00493 |  | LE-M08 | NCRP0245CS LE-M08 S Hoenycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-28 | Luz Arosemena | 2013-10-26 10:29 | 15200- Expansion Locks Pacific | Luz Arosemena
00492 |  | H3W-6B-F02 | NCRP0248CS H3W-6B-F02 Lack of cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-28 | Luz Arosemena | 2013-10-22 15:04 | 15200- Expansion Locks Pacific | Luz Arosemena
0064 |  |  | AQ0119 CAR DEPTHS & COORD_Boreholes | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-02-07 | Karla Jones | 2012-08-09 14:21 | 15100- Expansion Locks Atlantic | Karla Jones
00491 | Pacific | MW-M22-F01 | PQ0244 NCR MW-M22-F01 S. Honeycomb | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-28 | Luz Arosemena | 2012-10-13 11:27 | 15200- Expansion Locks Pacific | Luz Arosemena
00490 |  | H2E-3B-F06 Lack | NCRP0205CS H2E-3B-F06 Lack of Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-28 | Luz Arosemena | 2013-06-17 15:58 | 15200- Expansion Locks Pacific | Luz Arosemena
00498 | Pacific | LW-M05-C04a&c | PQ0242 NCR LW-M05-C04 A C Low Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-29 | Luz Arosemena | 2012-10-12 14:48 | 15200- Expansion Locks Pacific | Luz Arosemena
00497 | Atlantic | MW-M16-W08 | AQ0261 NCR MW-M16-W08 CONC out of T | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-29 | Karla Jones | 2012-08-13 16:05 | 15100- Expansion Locks Atlantic | Karla Jones
00496 |  | H1E-1C-W08 | NCRP0247CS H1E-1C-W08 Low rebar Cov | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-29 | Javier Gutierrez | 2013-02-09 10:35 | 15200- Expansion Locks Pacific | Luz Arosemena
00501 |  | LW-M05-F01 | NCRP0241CS LW-M05-F01 WS Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-30 | Luz Arosemena | 2013-09-21 11:21 | 15200- Expansion Locks Pacific | Luz Arosemena
00500 | Pacific | CC3-F-05 | PQ0249 NCR CC3-F05 Reinforcing | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-30 | Luz Arosemena | 2012-08-04 11:23 | 15200- Expansion Locks Pacific | Luz Arosemena
00499 |  | UW-M05-C04b | NCRP0238CS UW-M05-C04b Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-30 | Veronica Cash | 2013-08-28 09:17 | 15200- Expansion Locks Pacific | Luz Arosemena
00502 | Atlantic | UW-M13-C02 | AQ0263 NCR UW-M13-C02 Pipe not INST | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-05-31 | Karla Jones | 2012-11-09 11:42 | 15100- Expansion Locks Atlantic | Karla Jones
00504 |  | ME-M13-F01a | G00/UPCSOP0009 - (ME-M13-F01a) | Nonconformance Report | Void | No Ball in Court | Construction Deficiency | 2012-06-05 | Karla Jones | 2013-04-23 09:09 | 15100- Expansion Locks Atlantic | Karla Jones
0063 |  |  | AQ0117 CAR ITP for APPR GEOTECH INV | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-02-07 | Karla Jones | 2013-04-09 09:35 | 15100- Expansion Locks Atlantic | Karla Jones
00506 | Pacific | LE-M15-F03 | PQ0250 NCR LE-M15-F03-F01 Honeycomb | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-06 | Luz Arosemena | 2012-10-18 11:17 | 15200- Expansion Locks Pacific | Luz Arosemena
00505 | Atlantic | UE-M02-F01 | AQ0245 NCR UE-M02-F01 KCKc REB INST | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-06 | Karla Jones | 2013-02-18 09:57 | 15100- Expansion Locks Atlantic | Karla Jones
00513 | Atlantic | ME-M03-C03a | AQ0264 NCR ME-M03-C03aWaterStop DEV | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-08 | Karla Jones | 2012-07-31 09:36 | 15100- Expansion Locks Atlantic | Karla Jones
00512 | Pacific | LE-M11-F01 | PQ0254 NCR LE-M11-F01 Waterstop | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-08 | Rick Montanari | 2012-07-05 11:45 | 15200- Expansion Locks Pacific | Luz Arosemena
00511 | Pacific | LE-M11-F03/02 | PQ0253 NCR LE-M11-F03/02/01 Honeyco | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-08 | Javier Gutierrez | 2013-10-23 09:14 | 15200- Expansion Locks Pacific | Luz Arosemena
00510 | Atlantic | H3W-3A-F05a | AQ0265 NCR H3W-3A-F05a SOP10 IMPL | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-08 | Karla Jones | 2012-07-13 11:07 | 15100- Expansion Locks Atlantic | Karla Jones
00509 |  |  | PQ0251 NCR Low break IMC P7 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-08 | Rick Montanari | 2012-07-05 11:35 | 15200- Expansion Locks Pacific | Luz Arosemena
00508 | Pacific | ME-M14-F01 | NCRP0231CS ME-M14-F01-C04c Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-08 | Luz Arosemena | 2013-02-09 10:11 | 15200- Expansion Locks Pacific | Luz Arosemena
00507 | Atlantic | CC3-C-05 | AQ0247 NCR CC3-C-05 LCK of COV DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-08 | Karla Jones | 2012-08-13 14:47 | 15100- Expansion Locks Atlantic | Karla Jones
00503 | Atlantic | UW-M01-F01 | AQ0266 NCR UW-M01-F01 GEOM Failure | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-08 | Karla Jones | 2012-07-03 15:05 | 15100- Expansion Locks Atlantic | Karla Jones
0062 |  |  | AQ0116 CAR Slope Stabilization East | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-02-05 | Karla Jones | 2012-08-09 13:38 | 15100- Expansion Locks Atlantic | Karla Jones
00516 | Atlantic | H3E-6D-F02 | AQ0267 NCR H3E-6D-F02 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-09 | Karla Jones | 2012-06-19 16:25 | 15100- Expansion Locks Atlantic | Karla Jones
00515 | Pacific | LW-M03 F01 | PQ0256 NCR LW-M03 F01 N. Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-09 | Luz Arosemena | 2012-07-16 15:56 | 15200- Expansion Locks Pacific | Luz Arosemena
00514 | Pacific | LW-M11-F03&F01 | PQ0255 NCR LW-M11 F03-F01 Honeycomb | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-09 | Luz Arosemena | 2012-10-13 11:30 | 15200- Expansion Locks Pacific | Luz Arosemena
00518 | Pacific | H1W-6D-F03 | PQ0257 NCR H1W-6D-F03 Waterstop | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-13 | Luz Arosemena | 2012-09-21 09:56 | 15200- Expansion Locks Pacific | Luz Arosemena
00517 |  |  | NCRP0258CS AFR-01 Batch Plant Oper. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-13 | Lorely Rivera | 2014-10-08 11:54 | 15200- Expansion Locks Pacific | Luz Arosemena
00520 | Atlantic | H2W-1C-W06 | AQ0270 NCR H2W-1C-W06 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-14 | Karla Jones | 2012-06-26 08:09 | 15100- Expansion Locks Atlantic | Karla Jones
00519 | Atlantic | H2W-2A-F02 | AQ0269 NCR H2W-2A-F02 LCK of COMPCT | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-14 | Karla Jones | 2012-08-07 08:06 | 15100- Expansion Locks Atlantic | Karla Jones
00522 |  | MW-M21-C04b | NCRP0261CS MW-M21-C04b W Honeycomb | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-16 | Luz Arosemena | 2013-05-28 10:46 | 15200- Expansion Locks Pacific | Luz Arosemena
00521 | Pacific | H3E-1A-F02 | PQ0260 NCR H3E-1A-F02 W Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-16 | Luz Arosemena | 2012-09-19 14:51 | 15200- Expansion Locks Pacific | Luz Arosemena
00523 | Atlantic | H2W-1A-W06 | AQ0271 NCR H2W-1A-W06 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-18 | Karla Jones | 2012-06-26 08:01 | 15100- Expansion Locks Atlantic | Karla Jones
0061 |  |  | AQ0011 CAR Env. Inspection Forms | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-03-04 | Mayra Santos | 2016-05-31 16:14 | 15100- Expansion Locks Atlantic | Maria Ho
00524 | Pacific | H3E-3A-F06 | PQ0262 NCR H3E-3A-F06 N. Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-19 | Rick Montanari | 2012-07-06 13:31 | 15200- Expansion Locks Pacific | Luz Arosemena
00529 | Atlantic | H3E-6B-W13b | AQ0277 NCR H3E-6B-W13b Misalignment | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-20 | Karla Jones | 2012-08-06 11:37 | 15100- Expansion Locks Atlantic | Karla Jones
00528 | Atlantic | H1W-1A-F03 | AQ0276 NCR H1W-1A-F03 Seepage OBS | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-20 | Karla Jones | 2012-10-05 12:12 | 15100- Expansion Locks Atlantic | Karla Jones
00527 | Atlantic | UW-M08-C03a | AQ0275 NCR UW-M08-C03a CONC out TOL | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-20 | Karla Jones | 2013-01-14 17:17 | 15100- Expansion Locks Atlantic | Karla Jones
00526 | Atlantic | UE-M02-F01 | AQ0274 NCR UE-M02-F01 LCK of COMPCT | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-20 | Karla Jones | 2012-10-05 11:30 | 15100- Expansion Locks Atlantic | Karla Jones
00525 | Atlantic | UW-M02-W06 | AQ0272 NCR UW-M02-W06 Extra COV DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-20 | Karla Jones | 2012-06-25 16:42 | 15100- Expansion Locks Atlantic | Karla Jones
00531 | Atlantic | ME-M12-F01 | AQ0273 NCR ME-M12-F01 KCK b REB DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-21 | Karla Jones | 2012-11-09 12:11 | 15100- Expansion Locks Atlantic | Karla Jones
00530 | Atlantic | LW-M12-F02 | AQ0278 NCR LW-M12-F02 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-21 | Karla Jones | 2012-06-25 16:46 | 15100- Expansion Locks Atlantic | Karla Jones
00532 | Atlantic | LW-M14-F02 | AQ0279 NCR LW-M14-F02 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-22 | Karla Jones | 2012-08-07 08:21 | 15100- Expansion Locks Atlantic | Karla Jones
00533 | Atlantic | H2W-3C-F03 | AQ0280 NCR H2W-3C-F03 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-23 | Karla Jones | 2012-08-07 08:13 | 15100- Expansion Locks Atlantic | Karla Jones
0060 |  |  | AQ0114 CAR Renovation of Buildings | Corrective Action Request | Closed | No Ball in Court | Administrative | 2011-02-05 | Karla Jones | 2012-08-09 11:51 | 15100- Expansion Locks Atlantic | Karla Jones
00534 | Pacific | LE-M15-F02 | PQ0263 NCR LE-M15-F02 NS Honeycom | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-25 | Maria Ho | 2013-02-13 14:57 | 15200- Expansion Locks Pacific | Luz Arosemena
00536 | Atlantic | H3W-1B-W13 | AQ0282 NCR H3W-1B-W13 Rebar Lack | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-27 | Karla Jones | 2012-07-24 14:54 | 15100- Expansion Locks Atlantic | Karla Jones
00535 | Atlantic | H3C-4C-F03 | AQ0281 NCR H3C-4C-F03 Rebar Lack | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-27 | Karla Jones | 2012-09-26 17:04 | 15100- Expansion Locks Atlantic | Karla Jones
00538 | Atlantic | CC2-E-03b & CC2-E-03c | AQ0283 NCR CC2-E-03b & CC2-E-03c | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-28 | Karla Jones | 2012-07-03 15:44 | 15100- Expansion Locks Atlantic | Karla Jones
00537 | Pacific | CC4-G-05 | PQ0196 NCR CC4-G-05 Honeycombing | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-28 | Luz Arosemena | 2012-07-31 11:37 | 15200- Expansion Locks Pacific | Luz Arosemena
00539 | Pacific | MW-M02-F01 | PQ0264 NCR MW-M02-F01 Reinf PL | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-06-29 | Luz Arosemena | 2012-08-28 16:40 | 15200- Expansion Locks Pacific | Luz Arosemena
00541 |  |  | AQ0268 NCR CONC Operation Main B.P. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-07-03 | Karla Jones | 2013-08-22 07:42 | 15100- Expansion Locks Atlantic | Karla Jones
00540 | Atlantic | H2W-3A-F03 | AQ0284 NCR H2W-3A-F03 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-07-03 | Karla Jones | 2012-07-13 10:58 | 15100- Expansion Locks Atlantic | Karla Jones
00542 | Pacific | UW-M22-C02 | PQ0266 NCR UW-M22-C02 Low rebar cov | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-07-04 | Luz Arosemena | 2012-09-26 08:54 | 15200- Expansion Locks Pacific | Luz Arosemena
00543 | Atlantic | LE-M10-F01 | AQ0285 NCR LE-M10-F01 KCK b REB DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-07-07 | Karla Jones | 2012-08-31 11:14 | 15100- Expansion Locks Atlantic | Karla Jones
0059 |  |  | AQ0112 CAR Slope Stabilization CU1 | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2011-01-11 | Karla Jones | 2012-11-01 14:01 | 15100- Expansion Locks Atlantic | Karla Jones
00544 | Pacific | H3E-2A-F01 | PQ0163 NCR H3E-2A-F01 Over cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-07-11 | Luz Arosemena | 2012-08-04 11:31 | 15200- Expansion Locks Pacific | Luz Arosemena
00545 | Pacific | CC3-F05 | PQ0259 NCR CC3-F05 Rebar Misslocate | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-07-12 | Luz Arosemena | 2012-11-13 10:44 | 15200- Expansion Locks Pacific | Luz Arosemena
00547 |  | LE-M04-F01 | NCRP0265CS LE-M04-F01 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-07-14 | Javier Gutierrez | 2013-12-23 14:47 | 15200- Expansion Locks Pacific | Luz Arosemena
00546 |  | CC3-F-05 | NCRP0270CS CC3-F05 Unsound Concrete | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-07-14 | Luz Arosemena | 2015-06-11 15:58 | 15200- Expansion Locks Pacific | Luz Arosemena
00549 | Atlantic | H4C-6A-F04 | AQ0287 NCR H4C-6A-F04 Rebar Lack | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-07-16 | Karla Jones | 2012-08-06 11:24 | 15100- Expansion Locks Atlantic | Karla Jones
00548 |  |  | AQ0286 NCR LCK of Weather PROTECT | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-07-16 | Karla Jones | 2012-11-16 14:47 | 15100- Expansion Locks Atlantic | Karla Jones
00552 | Atlantic | UE-M12-F01 | AQ0288 NCR UE-M12-F01 Kck c REB LCK | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-07-19 | Karla Jones | 2012-08-07 08:27 | 15100- Expansion Locks Atlantic | Karla Jones
00582 |  |  | NCRP0006CS Bld Concrete Block cut | Nonconformance Report | Superseded | NO BIC-GUPC | Construction Deficiency | 2016-02-17 | Lorely Rivera | 2016-07-11 12:11 | 15200- Expansion Locks Pacific | Karla Jones
00551 | Pacific | UE-M10-W05 | PQ0252 NCR UE-M10-W05 Missing Rebar | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-07-19 | Luz Arosemena | 2012-10-29 08:13 | 15200- Expansion Locks Pacific | Luz Arosemena
00550 | Pacific | UW-M10-W06 | PQ0268 NCR UW-M10-W06 Missing Rebar | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-07-19 | Luz Arosemena | 2012-10-13 11:24 | 15200- Expansion Locks Pacific | Luz Arosemena
0058 |  |  | AQ0010 CAR Safe Work Plan | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-03-04 | Maria Ho | 2012-08-09 11:28 | 15100- Expansion Locks Atlantic | Maria Ho
00553 | Pacific | LE-M13-F02 | PQ0273 NCR LE-M13-F02 S. Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-07-20 | Luz Arosemena | 2012-10-23 10:35 | 15200- Expansion Locks Pacific | Luz Arosemena
00554 | Atlantic | UE-M05-F02 | AQ0289 NCR UE-M05-F02 Formwork COND | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-07-24 | Karla Jones | 2012-08-01 16:47 | 15100- Expansion Locks Atlantic | Karla Jones
00556 | Atlantic | H2W-1A-W06 | AQ0292 NCR H2W-1A-W06 Rebar INSTALL | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-07-30 | Karla Jones | 2012-08-31 11:23 | 15100- Expansion Locks Atlantic | Karla Jones
00555 | Atlantic | CC1-G-05 | AQ0262 NCR CC1-G-05 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-07-30 | Karla Jones | 2012-08-06 10:02 | 15100- Expansion Locks Atlantic | Karla Jones
00558 | Pacific | ME-M22-F05 | PQ0274 NCR ME-M22-F05 Missing Bars | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-07-31 | Luz Arosemena | 2012-08-28 16:49 | 15200- Expansion Locks Pacific | Javier Gutierrez
00557 | Atlantic | LE-M16-F01 | AQ0293 NCR LE-M16-F01 KCK b REB DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-07-31 | Larry Ohrn | 2012-11-12 15:59 | 15100- Expansion Locks Atlantic | Karla Jones
00561 | Atlantic | CC1-H-05 | AQ0295 NCR CC1-H-05 REB DEF_LCK COV | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-03 | Karla Jones | 2012-08-13 14:41 | 15100- Expansion Locks Atlantic | Karla Jones
00560 | Atlantic | H1W-3C-F06 | AQ0291 NCR H1W-3C-F06 Water STP LOC | Nonconformance Report | Closed | Jose Dorantes | Construction Deficiency | 2012-08-03 | Karla Jones | 2013-06-07 13:07 | 15100- Expansion Locks Atlantic | Karla Jones
00559 | Atlantic | MW-M05-F02 | AQ0294 NCR MW-M05-F02 TEMP out of T | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-03 | Karla Jones | 2012-08-21 07:31 | 15100- Expansion Locks Atlantic | Karla Jones
00564 |  |  | P55M0006 NCR FSE OOT UE-M03 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-08-06 | Juan Rivera | 2015-07-21 16:06 | 15200- Expansion Locks Pacific | Alberto Alonzo
0057 |  |  | PQ0080 CAR QMS Process BDam Fill | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-08-09 | Luz Arosemena | 2013-10-09 11:31 | 15200- Expansion Locks Pacific | Luz Arosemena
00563 |  |  | P55M0005 NCR FSE OOT UE-M02 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-08-06 | Juan Rivera | 2014-02-27 21:49 | 15200- Expansion Locks Pacific | Alberto Alonzo
00562 |  | H1W-6B-W10b | NCRP0275CS H1W-6B-W10b Rebar | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-06 | Luz Arosemena | 2013-03-22 13:52 | 15200- Expansion Locks Pacific | Luz Arosemena
00568 |  |  | P50M0001 NCR LH1 RG1 Seismic Hook | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-08-08 | Juan Rivera | 2015-10-19 09:52 | 15200- Expansion Locks Pacific | Alberto Alonzo
00566 | Pacific | UE-M17-C04b | PQ0276 NCR UE-M17-C04b Cracks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-08 | Luz Arosemena | 2012-08-25 08:05 | 15200- Expansion Locks Pacific | Luz Arosemena
00570 | Pacific | UE-M17-C03c | PQ0277 NCR UE-M17-C03c Out of Toler | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-09 | Luz Arosemena | 2012-10-29 08:14 | 15200- Expansion Locks Pacific | Luz Arosemena
00569 | Pacific | UE-M13-C030c | PQ0269 NCR UE-M13-C030c Rebar Inst. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-09 | Luz Arosemena | 2012-11-24 10:47 | 15200- Expansion Locks Pacific | Luz Arosemena
00574 | Atlantic | LW-M01-F01 | AQ0296 NCR LW-M01-F01 CONSLD DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-11 | Karla Jones | 2013-03-01 10:50 | 15100- Expansion Locks Atlantic | Karla Jones
00576 | Atlantic | ME-M15-W04 | AQ0298 NCR ME-M15-W04 CONC DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-13 | Karla Jones | 2013-07-08 14:09 | 15100- Expansion Locks Atlantic | Karla Jones
00575 |  |  | AQ0297 NCR ADD Water During Steel T | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-13 | Karla Jones | 2013-03-26 08:08 | 15100- Expansion Locks Atlantic | Karla Jones
00580 |  | LW-M15-C04b | NCRP0281CS LW-M15-C04b Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-17 | Luz Arosemena | 2013-09-16 11:19 | 15200- Expansion Locks Pacific | Luz Arosemena
0056 |  |  | AQ0110 CAR Earthworks OutSide EXCV | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-12-16 | Karla Jones | 2012-08-09 11:06 | 15100- Expansion Locks Atlantic | Karla Jones
00579 |  |  | PQ0279 NCR 1939 Fill Gradation | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-17 | Luz Arosemena | 2012-09-07 09:29 | 15200- Expansion Locks Pacific | Luz Arosemena
00578 | Pacific | MW-M17-F01 | PQ0271 NCR MW-M17-F01 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-17 | Luz Arosemena | 2012-12-01 10:42 | 15200- Expansion Locks Pacific | Luz Arosemena
00577 |  | H3E-1B-W13 | NCRP0280CS H3E-1B-W13 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-17 | Luz Arosemena | 2013-10-22 15:08 | 15200- Expansion Locks Pacific | Luz Arosemena
00001 |  |  | PQ0278 NCR Dam 1W Material Removal | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-17 | Luz Arosemena | 2012-11-30 14:12 | 15200- Expansion Locks Pacific | Luz Arosemena
00581 | Atlantic | H3W-2C-F01 | AQ0290 NCR H3W-2C-F01 Consolidation | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-20 | Karla Jones | 2012-10-24 10:15 | 15100- Expansion Locks Atlantic | Karla Jones
00583 | Atlantic | CC1-D-05 | AQ0299 NCR CC1-D-05 KCK a Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-21 | Karla Jones | 2012-08-27 15:06 | 15100- Expansion Locks Atlantic | Karla Jones
00584 |  | Rebar | AQ0300 NCR Rebar Installation DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-22 | Karla Jones | 2012-10-01 11:28 | 15100- Expansion Locks Atlantic | Karla Jones
00585 |  |  | AQ0301 NCR H4E-6C-F03 Cracks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-24 | Karla Jones | 2012-09-26 12:31 | 15100- Expansion Locks Atlantic | Karla Jones
00007 |  |  |  | Nonconformance Report | Closed | NO BIC-GUPC | Errors and Omissions | 2012-08-25 | Alberto Alonzo | 2012-10-27 11:18 | 15100- Expansion Locks Atlantic | Alberto Alonzo
00586 |  |  | PQ0284 NCR Dam 1W Dental Con.Test | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-27 | Luz Arosemena | 2012-11-13 11:22 | 15200- Expansion Locks Pacific | Luz Arosemena
0055 |  |  | PQ0079 CAR QMS Process Vert. Anchor | Corrective Action Request | Closed | Maria Baz | Quality Mgt Sys | 2012-08-09 | Martin Morales | 2016-08-22 15:13 | 15200- Expansion Locks Pacific | Luz Arosemena
00588 |  | UW-M03-C03b | NCRP0283CS UW-M03-C03b Honeycombs | Nonconformance Report | Closed | Lorely Rivera | Construction Deficiency | 2012-08-28 | Luz Arosemena | 2015-01-02 15:02 | 15200- Expansion Locks Pacific | Luz Arosemena
00587 | Atlantic | UW-M23-F01 | AQ0303 NCR UW-M23-F01 KCK b REB DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-28 | Karla Jones | 2012-09-26 13:13 | 15100- Expansion Locks Atlantic | Karla Jones
00591 | Atlantic | H1E-6A-F03 | AQ0305 NCR H1E-6A-F03 Water STP DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-30 | Karla Jones | 2012-11-09 13:01 | 15100- Expansion Locks Atlantic | Karla Jones
00590 | Atlantic | LE-M10-F01 | AQ0302 NCR LE-M10-F01 KCKa CONC DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-30 | Karla Jones | 2012-12-04 15:10 | 15100- Expansion Locks Atlantic | Karla Jones
00589 | Atlantic | H3E-6E-W10 | AQ0304 NCR H3E-6E-W10 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-30 | Karla Jones | 2012-09-28 15:14 | 15100- Expansion Locks Atlantic | Karla Jones
00592 | Atlantic | H4E-6A-W13 | AQ0306 NCR H4E-6A-W13 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-08-31 | Karla Jones | 2012-12-10 11:52 | 15100- Expansion Locks Atlantic | Karla Jones
00593 | Atlantic | LW-M10-C01 | AQ0308 NCR LW-M10-C01CONC Pour DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-09-01 | Gloria Leguias | 2013-07-27 11:12 | 15100- Expansion Locks Atlantic | Gloria Leguias
00594 | Pacific | H3W-6A-W13a | PQ0286 NCR H3W-6A-W13a Rebar Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-09-04 | Luz Arosemena | 2012-11-20 10:18 | 15200- Expansion Locks Pacific | Luz Arosemena
00008 |  |  | G55M0005 NCR HSH SSE Handl Damage | Nonconformance Report | Closed | NO BIC-GUPC | Errors and Omissions | 2012-09-04 | Alberto Alonzo | 2014-05-21 15:36 | 15000- Expansion Locks | Alberto Alonzo
00597 |  |  | P55M0010 NCR FSE OOT UE-M09 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-09-05 | Martin Duran | 2013-07-13 08:37 | 15200- Expansion Locks Pacific | Alberto Alonzo
0054 |  |  | AQ0009 CAR Fire Hazards Inspection | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-03-04 | Maria Ho | 2012-08-09 11:28 | 15100- Expansion Locks Atlantic | Maria Ho
00596 |  |  | P55M0009 NCR FSE OOT UW-M03 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-09-05 | Martin Duran | 2013-07-13 08:33 | 15200- Expansion Locks Pacific | Alberto Alonzo
00595 |  |  | P55M0008 NCR FSE OOT UW-M02 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-09-05 | Juan Rivera | 2015-07-21 16:10 | 15200- Expansion Locks Pacific | Alberto Alonzo
00599 | Atlantic | H4E-6E-F03 | AQ0307 NCR H4E-6E-F03 Rebar LACK OF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-09-06 | Marta Small | 2015-09-02 13:24 | 15100- Expansion Locks Atlantic | Zosimo Correa
00598 | Atlantic | CC1-D-05 | AQ0309 NCR CC1-D-05 KCK c REB INST | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-09-06 | Karla Jones | 2012-09-28 16:04 | 15100- Expansion Locks Atlantic | Zosimo Correa
00601 |  | LW-M01-F01a | NCRP0288CS LW-M01-F01a Finishing | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-09-08 | Luz Arosemena | 2013-04-11 08:03 | 15200- Expansion Locks Pacific | Luz Arosemena
00600 |  | LE-M04-F01 | NCRP0285CS LE-M04-F01 Water stop | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-09-08 | Luz Arosemena | 2013-10-02 11:18 | 15200- Expansion Locks Pacific | Luz Arosemena
00602 | Atlantic | CC1-D-05 | AQ0310 NCR CC1-D-05 REB instal DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-09-10 | Marta Small | 2015-09-02 13:25 | 15000- Expansion Locks | Zosimo Correa
00603 | Pacific | ME-M14-C03a | PQ0287 NCR ME-M14-C03a Formwork | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-09-11 | Luz Arosemena | 2012-10-18 11:24 | 15200- Expansion Locks Pacific | Luz Arosemena
00606 | Pacific | CC1-A-03 | PQ0289 NCR CC1-A-03S Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-09-12 | Luz Arosemena | 2012-10-23 10:42 | 15200- Expansion Locks Pacific | Luz Arosemena
00605 |  |  | P55M0012 NCR FSE OOT UW-M04 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-09-12 | Martin Duran | 2013-07-13 09:00 | 15200- Expansion Locks Pacific | Alberto Alonzo
0053 |  |  | AQ0007 CAR Daily Report Compliance | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-03-04 | Maria Ho | 2012-08-09 11:28 | 15100- Expansion Locks Atlantic | Maria Ho
00604 |  |  | P55M0011 NCR FSE OOT UW-M09 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-09-12 | Martin Duran | 2013-07-13 08:47 | 15200- Expansion Locks Pacific | Alberto Alonzo
00624 |  |  | P55M0013 NCR FSE OOT UW-M12 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-09-13 | Martin Duran | 2013-07-13 09:05 | 15200- Expansion Locks Pacific | Maria Ho
00609 | Pacific | H3W-6B-F03 | PQ0291 NCR H3W-6B-F03 Missing Rebar | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-09-15 | Luz Arosemena | 2012-10-29 08:12 | 15200- Expansion Locks Pacific | Luz Arosemena
00608 | Pacific | H3E-3B-F06 | PQ0290 NCR H3E-3B-F06 Liner | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-09-15 | Luz Arosemena | 2012-11-02 14:08 | 15200- Expansion Locks Pacific | Luz Arosemena
00607 |  | UW-M21-C01&C02 | NCRP0282CS UW-M21-C01&C02 Crack | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-09-15 | Luz Arosemena | 2013-04-04 09:56 | 15200- Expansion Locks Pacific | Luz Arosemena
00009 |  |  | P55M0007 NCR SSE Bearing Jamb TSC | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-09-18 | Luz Arosemena | 2015-05-27 11:30 | 15200- Expansion Locks Pacific | Alberto Alonzo
00611 | Atlantic | H4E-6A-F02 | AQ0312 NCR H4E-6A-F02 Wall DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-09-20 | Karla Jones | 2012-11-09 14:06 | 15100- Expansion Locks Atlantic | Karla Jones
00610 | Atlantic | UW-M08-C04b | AQ0313 NCR UW-M08-C04b CNSLD DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-09-20 | Karla Jones | 2013-03-04 08:33 | 15100- Expansion Locks Atlantic | Karla Jones
00612 |  |  | NCRP0292CS 1939 Deficiencies | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-09-21 | Luz Arosemena | 2014-10-15 09:50 | 15200- Expansion Locks Pacific | Luz Arosemena
00613 | Atlantic | LE-M11-C04c | AQ0314 NCR LE-M11-C04c Pouring DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-09-24 | Karla Jones | 2012-10-24 10:29 | 15100- Expansion Locks Atlantic | Karla Jones
0052 |  |  | AQ0005 CAR Oil and Diesel Spill | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-02-22 | Maria Ho | 2012-08-09 11:26 | 15100- Expansion Locks Atlantic | Maria Ho
00614 | Atlantic | H2W-1A-W04 | AQ0315 NCR H2W-1A-W04 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-09-25 | Karla Jones | 2012-11-16 14:27 | 15100- Expansion Locks Atlantic | Karla Jones
00616 | Atlantic | H3E-6E-W11 | AQ0316 NCR H3E-6E-W11 CNSLDT DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-01 | Karla Jones | 2013-05-21 07:21 | 15100- Expansion Locks Atlantic | Karla Jones
00615 | Atlantic | H1W-3A-F04 & F05 | AQ0317 NCR H1W-3A-F04 & F05 CNSLD D | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-01 | Karla Jones | 2012-12-11 06:55 | 15100- Expansion Locks Atlantic | Karla Jones
00618 | Atlantic | H1E-6C-F01 | AQ0311 NCR H1E-6C-F01 WS not INST | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-02 | Karla Jones | 2012-12-05 08:10 | 15100- Expansion Locks Atlantic | Karla Jones
00617 | Pacific | H3E-1A-W11 | PQ0294 NCR H3E-1A-W11 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-02 | Luz Arosemena | 2012-11-02 14:11 | 15200- Expansion Locks Pacific | Luz Arosemena
00620 |  | LW-M11-C04b | NCRP0297CS LW-M11-C04b Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-03 | Luz Arosemena | 2013-10-11 11:52 | 15200- Expansion Locks Pacific | Luz Arosemena
00619 |  | LW-M03-C04b | NCRP0295CS LW-M03-C04b Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-03 | Luz Arosemena | 2013-09-16 11:22 | 15200- Expansion Locks Pacific | Luz Arosemena
00010 |  |  | A55M0008 NCR SSE Bearing Jamb TSC | Nonconformance Report | Closed | NO BIC-GUPC | Defective Materials | 2012-10-03 | Martin Duran | 2014-01-29 10:18 | 15100- Expansion Locks Atlantic | Alberto Alonzo
00622 | Atlantic | LW-M04-F01 | AQ0322 NCR LW-M04-F01 KCK c REB DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-05 | Karla Jones | 2012-10-25 11:25 | 15100- Expansion Locks Atlantic | Karla Jones
00621 | Atlantic | LW-M03-F01 | AQ0319 NCR LW-M03-F01 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-05 | Karla Jones | 2012-11-27 14:16 | 15100- Expansion Locks Atlantic | Karla Jones
0051 |  |  | AQ0108 CAR PREP DOCS MTE Lirio D | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-11-26 | Karla Jones | 2012-08-08 16:14 | 15100- Expansion Locks Atlantic | Karla Jones
00623 | Atlantic | H4E-6B-F03 | AQ0323 NCR H4E-6B-F03 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-06 | Karla Jones | 2012-10-25 08:23 | 15100- Expansion Locks Atlantic | Karla Jones
00625 | Atlantic | UE-M20-F01 | AQ0324 NCR UE-M20-F01 REB LCK of C | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-10 | Karla Jones | 2012-10-25 08:31 | 15100- Expansion Locks Atlantic | Karla Jones
00626 | Atlantic | H3E-6E-W09 | AQ0320 NCR H3E-6E-W09 CNSLD DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-11 | Marta Small | 2015-09-02 13:25 | 15100- Expansion Locks Atlantic | Karla Jones
00005 |  |  | G62M0003 NCR MTI Marine Bollards | Nonconformance Report | Closed | NO BIC-GUPC | Defective Materials | 2012-10-15 | Alberto Alonzo | 2014-05-21 15:55 | 15000- Expansion Locks | Alberto Alonzo
00627 | Atlantic | ME-M12-C04b | AQ0327 NCR ME-M12-C04 b CNSLD DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-16 | Karla Jones | 2013-02-20 09:19 | 15100- Expansion Locks Atlantic | Karla Jones
00630 | Atlantic | H4E-6E-F01 | AQ0325 NCR H4E-6E-F01 KCK b REB DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-17 | Karla Jones | 2012-12-11 15:38 | 15100- Expansion Locks Atlantic | Karla Jones
00629 | Atlantic | H2W-1C-W03c | AQ0326 NCR H2W-1C-W03c REB LCK of C | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-17 | Karla Jones | 2012-11-09 11:13 | 15100- Expansion Locks Atlantic | Karla Jones
00628 |  |  | A55M0009 NCR FSE OOT ME-M15 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-10-17 | Martin Duran | 2013-06-12 11:57 | 15100- Expansion Locks Atlantic | Alberto Alonzo
00632 | Pacific | MW-M15-C03b | PQ0300 NCR MW-M15-C03b Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-19 | Luz Arosemena | 2012-11-15 15:01 | 15200- Expansion Locks Pacific | Luz Arosemena
00631 | Pacific | MW-M15-C02 | PQ0298 NCR MW-M15-C02 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-19 | Luz Arosemena | 2012-11-15 14:58 | 15200- Expansion Locks Pacific | Luz Arosemena
0050 |  |  | AQ0107 CAR DYKNG & FILL Works ML D | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-11-26 | Karla Jones | 2012-08-08 15:49 | 15100- Expansion Locks Atlantic | Karla Jones
00634 | Pacific | H3W-6D-F02 | PQ0303 NCR H3W-6D-F02 Misplaced Reb | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-22 | Luz Arosemena | 2013-02-04 11:57 | 15200- Expansion Locks Pacific | Luz Arosemena
00633 |  | H3W-6D-W14b | NCRP0302CS H3W-6D-W14b Form Failure | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-22 | Luz Arosemena | 2013-06-28 10:57 | 15200- Expansion Locks Pacific | Luz Arosemena
00635 |  | TRF-2-SL-10 | NCRP0299CS TRF-2-SL-10 IMC P9 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-10-23 | Yissel Wong | 2013-04-25 08:08 | 15200- Expansion Locks Pacific | Luz Arosemena
00636 |  |  | PQ0304 NCR Dam 1W Inboard | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-24 | Luz Arosemena | 2013-02-04 11:56 | 15200- Expansion Locks Pacific | Luz Arosemena
00637 |  |  | NCRP0305CS Grout Sample BDam 1W | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-27 | Luz Arosemena | 2013-07-15 11:12 | 15200- Expansion Locks Pacific | Luz Arosemena
00639 | Atlantic | H1E-6C-F02 | AQ0329 NCR H1E-6C-F02 REB LCK of C | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-31 | Karla Jones | 2012-11-23 11:33 | 15100- Expansion Locks Atlantic | Karla Jones
00638 | Atlantic | H1W-1C-W06 | AQ0328 NCR H1W-1C-W06 REB LCK of CO | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-10-31 | Karla Jones | 2012-11-23 11:59 | 15100- Expansion Locks Atlantic | Karla Jones
00641 |  | H3W-6B-F02 | NCRP0293CS H3W-6B-F02 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-11-01 | Luz Arosemena | 2013-03-25 17:50 | 15200- Expansion Locks Pacific | Luz Arosemena
00640 | Pacific | LW-M05-W05 | PQ0306 NCR LW-M05-W05 Missing Rebar | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-11-01 | Luz Arosemena | 2012-11-24 10:17 | 15200- Expansion Locks Pacific | Luz Arosemena
00642 | Atlantic | MW-M17-F02 | AQ0331 NCR MW-M17-F02 Cold Joint | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-11-02 | Karla Jones | 2012-11-09 13:34 | 15100- Expansion Locks Atlantic | Karla Jones
0049 |  |  | AQ0106 CAR Cement Silos Columns | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2012-08-08 | Karla Jones | 2012-08-08 15:22 | 15100- Expansion Locks Atlantic | Karla Jones
00644 | Atlantic | UE-M05-C04a | AQ0332 NCR UE-M05-C04a CONC out TOL | Nonconformance Report | Closed | Jose Dorantes | Construction Deficiency | 2012-11-06 | Karla Jones | 2013-02-04 10:35 | 15100- Expansion Locks Atlantic | Karla Jones
00643 | Atlantic | LE-M03-C01 | AQ0330 NCR LE-M03-C01 REB INST DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-11-06 | Karla Jones | 2013-08-22 07:51 | 15100- Expansion Locks Atlantic | Karla Jones
00645 | Atlantic | SF-U-07G | AQ0333 NCR SF-U-07G Finishing DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-11-13 | Karla Jones | 2012-12-11 07:10 | 15100- Expansion Locks Atlantic | Karla Jones
00646 |  | H1W-6C-W10b | NCRP0307CS H1W-6C-W10b Stakeout | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-11-15 | Luz Arosemena | 2014-10-16 09:25 | 15200- Expansion Locks Pacific | Luz Arosemena
00647 | Atlantic | UW-M07-F01 | AQ0335 NCR UW-M07-F01 KCK b REB DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-11-16 | Karla Jones | 2013-02-26 08:56 | 15100- Expansion Locks Atlantic | Karla Jones
00648 | Atlantic | H1E-6A-F01 | AQ0334 NCR H1E-6A-F01 Concrete DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-11-19 | Karla Jones | 2013-07-15 14:13 | 15100- Expansion Locks Atlantic | Karla Jones
00649 | Atlantic | CC6-B-05 | AQ0336 NCR CC6-B-05 KCK b Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-11-20 | Karla Jones | 2012-12-10 07:46 | 15100- Expansion Locks Atlantic | Karla Jones
00650 |  | H1E-1B-W09 | NCRP0309CS H1E-1B-W09 Reb Low Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-11-23 | Luz Arosemena | 2013-06-22 11:42 | 15200- Expansion Locks Pacific | Luz Arosemena
00651 | Pacific | UW-M23 | PQ0310 NCR UW-M23 Missing Rebars | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-11-27 | Luz Arosemena | 2013-02-04 11:57 | 15200- Expansion Locks Pacific | Luz Arosemena
00654 | Atlantic | UW-M01-C03b | AQ0341 NCR UW-M01-C03b REB INST DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-12-05 | Karla Jones | 2013-01-17 10:16 | 15100- Expansion Locks Atlantic | Karla Jones
0048 |  |  | AQ0004 CAR DEF. Close Circuit Calib | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-02-24 | Maria Ho | 2012-08-08 15:03 | 15100- Expansion Locks Atlantic | Maria Ho
00653 | Atlantic | H1W-1B-F01 | AQ0338 NCR H1W-1B-F01 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-12-05 | Karla Jones | 2012-12-26 08:51 | 15100- Expansion Locks Atlantic | Karla Jones
00652 | Atlantic | CC3-B-04b | AQ0340 NCR CC3-B-04b Pouring DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-12-05 | Karla Jones | 2013-06-27 15:34 | 15100- Expansion Locks Atlantic | Karla Jones
00657 | Atlantic | LW-M03-C04c | AQ0342 NCR LW-M03-C04c SPL REB DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-12-06 | Karla Jones | 2012-12-26 11:08 | 15100- Expansion Locks Atlantic | Karla Jones
00656 | Atlantic | LE-M02-W11 | PQ0312 NCR LE-M02-W11 Extra Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-12-06 | Luz Arosemena | 2013-01-23 08:39 | 15200- Expansion Locks Pacific | Luz Arosemena
00655 |  |  | NCRP0311CS Wing Wall - Grout Mix | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-12-06 | Luz Arosemena | 2014-09-22 15:36 | 15200- Expansion Locks Pacific | Luz Arosemena
00661 |  |  | A55M0012 NCR FSE OOT LW-M10 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-12-07 | Martin Duran | 2013-06-12 12:13 | 15100- Expansion Locks Atlantic | Alberto Alonzo
00660 |  |  | A55M0011 NCR FSE OOT LE-M04 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-12-07 | Martin Duran | 2013-06-12 12:09 | 15100- Expansion Locks Atlantic | Alberto Alonzo
00659 |  |  | A55M0010 NCR FSE OOT ME-M14 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-12-07 | Martin Duran | 2013-06-12 12:02 | 15100- Expansion Locks Atlantic | Alberto Alonzo
00658 |  |  | A50M0003 NCR FSE OOT RG | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-12-07 | Juan Rivera | 2014-02-27 22:34 | 15100- Expansion Locks Atlantic | Alberto Alonzo
00662 | Atlantic | H4W-3C-F04b REB | AQ0321 NCR H4W-3C-F04b REB INST DEF | Nonconformance Report | Closed | Jose Dorantes | Construction Deficiency | 2012-12-10 | Karla Jones | 2012-12-13 14:34 | 15100- Expansion Locks Atlantic | Karla Jones
0047 |  |  | AQ0124 CAR GUPC Production QC DOCS | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-08-06 | Karla Jones | 2012-08-06 16:08 | 15100- Expansion Locks Atlantic | Karla Jones
00004 |  |  | G62M0004 NCR BRI Fender Fab | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2012-12-10 | Alberto Alonzo | 2014-05-21 15:46 | 15000- Expansion Locks | Alberto Alonzo
00663 |  | H2E-1B-W04 | NCRP0314CS H2E-1B-W04 Rebars | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-12-13 | Luz Arosemena | 2013-10-02 11:24 | 15200- Expansion Locks Pacific | Luz Arosemena
00664 |  | H3C-5C-F07/6/5/4 | NCRP0313CS H3C-5C-F07/6/5/4 WS Loc | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-12-15 | Rick Montanari | 2013-05-14 14:00 | 15200- Expansion Locks Pacific | Luz Arosemena
00665 | Atlantic | CU3-1E-03c N & S | AQ0337 NCR CU3-1E-03c N & S REB DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-12-17 | Abdiel Santos | 2013-09-19 10:32 | 15100- Expansion Locks Atlantic | Karla Jones
00666 |  | H3W-6D-F01 | NCRP0308CS H3W-6D-F01 Missing Rebar | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2012-12-27 | Luz Arosemena | 2013-03-22 14:15 | 15200- Expansion Locks Pacific | Luz Arosemena
00668 | Atlantic | LE-M12-F01 | AQ0339 NCR LE-M12-F01 KCKc REB DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-01-02 | Karla Jones | 2013-01-29 15:35 | 15100- Expansion Locks Atlantic | Karla Jones
00667 |  | Main B.P Coarse Out | AQ0343 NCR Main B.P Coarse Out of T | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-01-02 | Karla Jones | 2013-01-22 08:52 | 15100- Expansion Locks Atlantic | Karla Jones
00669 |  | ME-M11 | PQ0296 NCR ME-M11-C03b Cracks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-01-04 | Veronica Cash | 2013-08-28 09:22 | 15200- Expansion Locks Pacific | Luz Arosemena
00675 |  | LE-M23-C02 Pipe | AQ0345 NCR LE-M23-C02 Pipe not INST | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-01-08 | Karla Jones | 2013-01-17 10:48 | 15100- Expansion Locks Atlantic | Karla Jones
00674 |  | Coarse | PQ0318 NCR Coarse Aggregate 75mm | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2013-01-08 | Luz Arosemena | 2013-02-05 16:18 | 15200- Expansion Locks Pacific | Luz Arosemena
0046 |  |  | AQ0115 CAR ENV Follow up GEOTECH IN | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-08-06 | Karla Jones | 2012-08-06 15:22 | 15100- Expansion Locks Atlantic | Karla Jones
00673 |  | Coarse Aggregate | PQ0317 NCR Coarse Aggregate 37.5mm | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2013-01-08 | Luz Arosemena | 2013-02-05 16:13 | 15200- Expansion Locks Pacific | Luz Arosemena
00672 |  | Coarse | NCRP0316CS Coarse Aggregate 19mm | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2013-01-08 | Luz Arosemena | 2013-02-25 07:38 | 15200- Expansion Locks Pacific | Luz Arosemena
00671 |  | H3W-6D-F01 & | NCRP0315CS H3W-6D-F01 & W14b WS | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-01-08 | Luz Arosemena | 2013-10-11 11:58 | 15200- Expansion Locks Pacific | Luz Arosemena
00670 |  | H1C-5A-F02 | AQ0344 NCR H1C-5A-F02 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-01-08 | Karla Jones | 2013-01-29 16:16 | 15100- Expansion Locks Atlantic | Karla Jones
00677 |  | H3W-3C-F02 CONC | AQ0346 NCR H3W-3C-F02 CONC out TOL | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-01-12 | Karla Jones | 2013-02-20 09:24 | 15100- Expansion Locks Atlantic | Karla Jones
00676 |  | Disposal 12 | NCRP0319CS Disposal 12 Dike Design | Nonconformance Report | Terminated | NO BIC-GUPC | Construction Deficiency | 2013-01-12 | Lorely Rivera | 2015-09-12 11:52 | 15200- Expansion Locks Pacific | Luz Arosemena
00678 |  | MW-M13-C04a | NCRP0320CS MW-M13-C04a Form failure | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-01-21 | Javier Gutierrez | 2013-12-01 15:31 | 15200- Expansion Locks Pacific | Luz Arosemena
00679 |  | UOMS without | AQ0348 NCR UOMS without Approved WS | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-01-22 | Abdiel Santos | 2013-09-09 16:56 | 15100- Expansion Locks Atlantic | Karla Jones
00680 |  | ME-M12 | NCRP0321CS ME-M12-C03a Extracover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-01-26 | Luz Arosemena | 2013-02-25 07:46 | 15200- Expansion Locks Pacific | Luz Arosemena
00681 |  | LH1 Backfill | AQ0347 NCR LH1 Backfill area DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-01-29 | Karla Jones | 2013-02-04 10:24 | 15100- Expansion Locks Atlantic | Karla Jones
0045 |  |  | GQ0088 CAR INCOR Shop DWR REV PROCE | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2012-08-03 | Maria Ho | 2012-10-10 12:09 | 15000- Expansion Locks | Maria Ho
00684 |  | LW-M09-C04c | NCRP0323CS LW-M09-C04c Surface out | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-01-31 | Luz Arosemena | 2013-07-20 10:03 | 15200- Expansion Locks Pacific | Javier Gutierrez
00683 |  | MW-M23-C04a | AQ0350 NCR MW-M23-C04a CNSLD DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-01-31 | Karla Jones | 2013-03-02 11:47 | 15100- Expansion Locks Atlantic | Karla Jones
00682 |  | UW-M15-F01 KCK b | AQ0349 NCR UW-M15-F01 KCK b CNSLD D | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-01-31 | Karla Jones | 2013-03-11 16:11 | 15100- Expansion Locks Atlantic | Karla Jones
00685 |  | BOR | NCRP0322CS BOR Mix Changed | Nonconformance Report | Terminated | Mark Van Asten | Construction Deficiency | 2013-02-01 | Javier Gutierrez | 2013-02-28 14:58 | 15200- Expansion Locks Pacific | Maria Ho
00002 |  | BOR | NCRP0324CS BOR IMPR Compaction | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-02-01 | Luz Arosemena | 2013-02-14 15:57 | 15200- Expansion Locks Pacific | Maria Ho
00688 |  | H3W-2A-W03 REB | AQ0352 NCR H3W-2A-W03 REB LCK DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-02-06 | Karla Jones | 2013-02-18 17:12 | 15100- Expansion Locks Atlantic | Karla Jones
00687 |  | H4W-1B-F02 REB | AQ0351 NCR H4W-1B-F02 REB INST DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-02-06 | Karla Jones | 2013-04-01 15:46 | 15100- Expansion Locks Atlantic | Karla Jones
00686 |  | LE | NCRP0327CS LE-M15 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-02-06 | Luz Arosemena | 2015-05-18 16:23 | 15200- Expansion Locks Pacific | Luz Arosemena
00691 |  | Unapproved Mix | NCRP0326CS Unapproved Mix SMC P56 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-02-07 | Luz Arosemena | 2013-03-09 11:30 | 15200- Expansion Locks Pacific | Luz Arosemena
00690 |  | Unapproved Mix | NCRP0325CS Unapproved Mix IMC P14 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-02-07 | Luz Arosemena | 2013-03-01 10:59 | 15200- Expansion Locks Pacific | Luz Arosemena
0044 |  |  | AQ0147 CAR Fall Line LAB_AFR01 | Corrective Action Request | Closed | No Ball in Court | Administrative | 2012-07-18 | Karla Jones | 2012-07-18 13:46 | 15100- Expansion Locks Atlantic | Karla Jones
00689 |  | H4W-6A | NCRP0328CS H4W-6A-W12b Honeycombs | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-02-07 | Veronica Cash | 2013-08-28 09:24 | 15200- Expansion Locks Pacific | Luz Arosemena
00692 |  | CC5I-05 | NCRP0329CS CC5I-05 Water Stop | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-02-08 | Luz Arosemena | 2013-03-01 11:06 | 15200- Expansion Locks Pacific | Luz Arosemena
00694 |  | Disposal | NCRP0331CS Disposal 12 Compaction | Nonconformance Report | Terminated | NO BIC-GUPC | Construction Deficiency | 2013-02-14 | Lorely Rivera | 2015-09-12 11:50 | 15200- Expansion Locks Pacific | Luz Arosemena
00693 |  | Unapproved Mix | NCRP0332CS Unapproved Mix IMC P18 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-02-14 | Luz Arosemena | 2013-03-09 11:36 | 15200- Expansion Locks Pacific | Luz Arosemena
00695 |  | H1E-1B | NCRP0336CS H1E-1B-W03 Rebar | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-02-21 | Luz Arosemena | 2013-03-25 17:55 | 15200- Expansion Locks Pacific | Luz Arosemena
00001 |  | UE-M18-W09-08 | NCRP0335CS UE-M18-W09-08-07 #14bars | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-02-21 | Yissel Wong | 2013-04-25 08:09 | 15200- Expansion Locks Pacific | Luz Arosemena
00001 |  |  |  | Nonconformance Report | Void | No Ball in Court |  | 2013-02-26 | Luz Arosemena | 2013-02-26 11:27 | 15200- Expansion Locks Pacific | Luz Arosemena
00697 |  | Dam | NCRP0337CS Dam 1W Gradation | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-03-07 | Luz Arosemena | 2013-05-01 10:30 | 15200- Expansion Locks Pacific | Luz Arosemena
00696 |  | H2W-6D | NCRP0301CS H2W-6D-F02 Honeycombs | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-03-07 | Yissel Wong | 2013-04-25 08:09 | 15200- Expansion Locks Pacific | Luz Arosemena
00698 |  | WSB T1 & T2 | NCRP0333CS WSB T1 & T2 07-F01 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-03-09 | Luz Arosemena | 2013-07-27 10:23 | 15200- Expansion Locks Pacific | Luz Arosemena
0043 |  |  | PE8053-CAR Lack of Env. Induction. | Corrective Action Request | Closed | Jorge Gomez | Environmental Situation | 2012-08-31 | Martin Morales | 2016-08-19 10:35 | 15200- Expansion Locks Pacific | Eliza Florendo
00699 |  | ME-M23-F08 | NCRP0330CS ME-M23-F08 Ramp Level | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-03-14 | Luz Arosemena | 2013-05-11 11:17 | 15200- Expansion Locks Pacific | Luz Arosemena
00011 |  | NCR Rust valv | P55M0039 NCR Rust valv. wheel 1st | Nonconformance Report | Closed | NO BIC-GUPC | Unforeseen Conditions | 2013-03-15 | Juan Rivera | 2014-02-25 17:02 | 15200- Expansion Locks Pacific | Juan Rivera
00700 |  | H3W-2C-W06 Pipe | AQ0354 NCR H3W-2C-W06 Pipe not INST | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-03-20 | Larry Ohrn | 2014-06-06 16:30 | 15100- Expansion Locks Atlantic | Karla Jones
00012 |  | NCR Rust valv | A55M0017 NCR Rust valv. wheel 1st | Nonconformance Report | Closed | NO BIC-GUPC | Unforeseen Conditions | 2013-04-02 | Juan Rivera | 2014-02-27 22:09 | 15100- Expansion Locks Atlantic | Juan Rivera
00703 |  | VS 1 & 2 | AQ0356 NCR VS 1 & 2 missing WS | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-04-04 | Karla Jones | 2013-08-06 07:57 | 15100- Expansion Locks Atlantic | Nayubel Cordoba
00013 |  | NCR Hydraulic | P55M0040 NCR Hydraulic cyl. leak | Nonconformance Report | Closed | NO BIC-GUPC | Unforeseen Conditions | 2013-04-12 | Juan Rivera | 2014-02-25 16:11 | 15200- Expansion Locks Pacific | Juan Rivera
00714 |  | WSB T1 C03 | NCRP0344CS WSB T1 C03 10 F01 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-04-15 | Luz Arosemena | 2013-07-09 15:32 | 15200- Expansion Locks Pacific | Martin Duran
000002 |  | rinquen | NCRP0347 Borinquen Dams Drainage | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-04-23 | Luz Arosemena | 2013-06-28 11:02 | 15200- Expansion Locks Pacific | Yissel Wong
000001 |  | Borinquen | NCRP0346 CS Borinquen Dam Core | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-04-23 | Javier Gutierrez | 2013-11-26 14:32 | 15200- Expansion Locks Pacific | Yissel Wong
000003 |  | H3C-5C | NCRP0341CS H3C-5C-F01 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-04-30 | Luz Arosemena | 2013-09-21 11:03 | 15200- Expansion Locks Pacific | Yissel Wong
0042 |  |  | AE8041 MindiCamp WWTP Discharge | Corrective Action Request | Closed | Jose Pelaez | Environmental Situation | 2012-07-12 | Marta Small | 2015-09-02 13:30 | 15100- Expansion Locks Atlantic | Adrian Lee
00003 |  | E Core | NCRP0355 Dam 2E Core Water runoff | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-05-24 | Luz Arosemena | 2013-06-28 11:07 | 15200- Expansion Locks Pacific | Luz Arosemena
000004 |  | MW-M23 | NCRP0357CS MW-M23-C04b Cracks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-05-24 | Luz Arosemena | 2013-06-22 11:30 | 15200- Expansion Locks Pacific | Luz Arosemena
00004 |  | W | NCRP0358 BDAM 1W Dewatering Oper | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-05-25 | Luz Arosemena | 2013-06-22 12:00 | 15200- Expansion Locks Pacific | Luz Arosemena
00702 |  | TRF1-SL-05A & B | AQ0355 NCR TRF1-SL-05A & B REB DEF | Nonconformance Report | Closed | Jose Pelaez | Construction Deficiency | 2013-05-27 | Nayubel Cordoba | 2013-05-27 16:55 | 15100- Expansion Locks Atlantic | Nayubel Cordoba
00701 |  | Vila | A00-UPCNCR50001_Vila Plano | Nonconformance Report | Void | Ariel Soto del Solar |  | 2013-05-27 | Nayubel Cordoba | 2013-05-27 16:47 |  | Nayubel Cordoba
00733 |  | H3W-3A-W06 | AQ0371 NCR H3W-3A-W06 CONC outline | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-03 | Karla Jones | 2013-06-27 15:26 | 15100- Expansion Locks Atlantic | Martin Duran
00705 |  | Vilaplano | AS5001-NCR Vilaplano Deficiencies | Nonconformance Report | Closed | No Ball in Court |  | 2013-06-03 | Tammie Stover | 2015-10-12 14:09 | 15100- Expansion Locks Atlantic | Nayubel Cordoba
00704 |  | OE-M02 | NCRP0342CS OE-M02-F02 Voids | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-03 | Luz Arosemena | 2013-06-17 15:55 | 15200- Expansion Locks Pacific | Nayubel Cordoba
00004 |  | NCR CIM Def of | G50M0004 NCR CIM Def of Gates C | Nonconformance Report | Closed | Erick Briceno | Construction Deficiency | 2013-06-03 | Alberto Alonzo | 2014-05-21 08:53 | 15000- Expansion Locks | Alberto Alonzo
00003 |  | NCR CIM Def of | G50M0003 NCR CIM Def of Gates B | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-06-03 | Alberto Alonzo | 2014-05-21 08:47 | 15000- Expansion Locks | Alberto Alonzo
0041 |  |  | PE8046 CAR Inadq handling med waste | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2012-04-10 | Marta Small | 2015-09-02 13:32 | 15200- Expansion Locks Pacific | Eliza Florendo
00002 |  | NCR CIM End Bracing | G50M0002 NCR CIM End Bracing Gate C | Nonconformance Report | Terminated | NO BIC-GUPC | Construction Deficiency | 2013-06-03 | Alberto Alonzo | 2014-05-21 08:44 | 15000- Expansion Locks | Alberto Alonzo
000005 |  | MW-M15 | NCRP0334CS MW-M15-C03b Honeycomb | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-03 | Luz Arosemena | 2013-10-11 12:01 | 15200- Expansion Locks Pacific | Luz Arosemena
000007 |  | UE-M17 | NCRP0350CS UE-M17-C03b Honeycombs | Nonconformance Report | Closed | Javier Gutierrez | Construction Deficiency | 2013-06-06 | Luz Arosemena | 2013-09-09 11:32 | 15200- Expansion Locks Pacific | Luz Arosemena
000006 |  | TRF-3-SL10 | NCRP0351CS TRF-3-SL10 Rain Event | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-06 | Javier Gutierrez | 2013-12-01 15:46 | 15200- Expansion Locks Pacific | Luz Arosemena
00732 |  | IW-M06 | NCRP0353CS IW-M06-F01 Rebar | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-07 | Luz Arosemena | 2013-06-22 11:35 | 15200- Expansion Locks Pacific | Martin Duran
00731 |  | H3W-3C-W05 CONC out | AQ0368 NCR H3W-3C-W05 CONC out of T | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-07 | Karla Jones | 2013-06-13 11:39 | 15100- Expansion Locks Atlantic | Martin Duran
00730 |  | UW-M02-C01 | NCRP0354CS UW-M02-C01 Water Filt | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-07 | Luz Arosemena | 2013-10-11 08:50 | 15200- Expansion Locks Pacific | Martin Duran
00729 |  | TRF2-SL-05A&C | AQ0367 NCR TRF2-SL-05A&C and 04A&C | Nonconformance Report | Closed | Jose Pelaez | Construction Deficiency | 2013-06-07 | Martin Duran | 2013-06-10 10:50 | 15100- Expansion Locks Atlantic | Martin Duran
00728 |  | ME-M13 | NCRP0352CS ME-M13-C02&C01b Pipe | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-07 | Luz Arosemena | 2013-06-22 12:04 | 15200- Expansion Locks Pacific | Martin Duran
00727 |  | ME-M19-C03a &ME | AQ0366 NCR ME-M19-C03a &ME-M19-C03c | Nonconformance Report | Closed | Jose Pelaez | Construction Deficiency | 2013-06-07 | Martin Duran | 2013-06-10 10:53 | 15100- Expansion Locks Atlantic | Martin Duran
0040 |  |  | AE8040 Mindi Disposal Erosion Ctrl | Corrective Action Request | Closed | Jose Pelaez | Environmental Situation | 2012-07-09 | Marta Small | 2015-09-02 13:34 | 15100- Expansion Locks Atlantic | Adrian Lee
00726 |  | IW-M05-F03b | AQ0365 NCR IW-M05-F03b CONC Poured | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-07 | Karla Jones | 2013-06-28 15:15 | 15100- Expansion Locks Atlantic | Martin Duran
00725 |  | LH3 | AQ0360 NCR LH3 Backfill Deficiency | Nonconformance Report | Closed | Jose Pelaez | Construction Deficiency | 2013-06-07 | Martin Duran | 2013-06-10 10:54 | 15100- Expansion Locks Atlantic | Martin Duran
00724 |  | H3E-6E-W06 | AQ0364 NCR H3E-6E-W06 IDQ Formwork | Nonconformance Report | Closed | Jose Pelaez | Construction Deficiency | 2013-06-07 | Martin Duran | 2013-06-10 10:55 | 15100- Expansion Locks Atlantic | Martin Duran
00723 |  | OW-M05-F02,F01 | AQ0362 NCR OW-M05-F02,F01 CNSLD DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-07 | Abdiel Santos | 2013-11-02 10:09 | 15100- Expansion Locks Atlantic | Martin Duran
00722 |  | TRF1-SL-04 & 03 | AQ0363 NCR TRF1-SL-04 & 03 REB DEF | Nonconformance Report | Closed | Jose Pelaez | Construction Deficiency | 2013-06-07 | Juan Rivera | 2013-06-14 16:53 | 15100- Expansion Locks Atlantic | Martin Duran
00721 |  | UW-M01-C01 | NCRP0348CS UW-M01-C01 Water Filtrat | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-07 | Luz Arosemena | 2013-10-11 08:19 | 15200- Expansion Locks Pacific | Martin Duran
00720 |  | H1W-3A-W10 | AQ0361 NCR H1W-3A-W10 Rebar DEF | Nonconformance Report | Closed | Jose Pelaez | Construction Deficiency | 2013-06-07 | Martin Duran | 2013-06-10 11:01 | 15100- Expansion Locks Atlantic | Martin Duran
00719 |  | CONC Operation Main | AQ0359 NCR CONC Operation Main B P | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-07 | Abdiel Santos | 2014-04-14 14:52 | 15100- Expansion Locks Atlantic | Martin Duran
00718 |  | H2E-2B | NCRP0345CS H2E-2B-W08 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-07 | Luz Arosemena | 2013-07-09 15:32 | 15200- Expansion Locks Pacific | Martin Duran
00717 |  | H1E-6B-F01 KCK b | AQ0358 NCR H1E-6B-F01 KCK b REB DEF | Nonconformance Report | Closed | Jose Pelaez | Construction Deficiency | 2013-06-07 | Martin Duran | 2013-06-10 11:03 | 15100- Expansion Locks Atlantic | Martin Duran
00716 |  | CONC Operation Main | AQ0353 NCR CONC Operation Main B.P. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-07 | Abdiel Santos | 2014-03-10 14:04 | 15100- Expansion Locks Atlantic | Martin Duran
00715 |  | ME-M12-C01a | NCRP0343CS ME-M12-C01a Mass Conc | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-07 | Luz Arosemena | 2013-07-20 10:36 | 15200- Expansion Locks Pacific | Martin Duran
00713 |  | NCR FSE OOT | A55M0016 NCR FSE OOT ME-M08 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-06-07 | Abdiel Santos | 2015-07-21 10:31 | 15100- Expansion Locks Atlantic | Martin Duran
00712 |  | NCR FSE OOT | A55M0015 NCR FSE OOT ME-M09 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-06-07 | Martin Duran | 2013-06-12 11:47 | 15100- Expansion Locks Atlantic | Martin Duran
00711 |  | NCR FSE OOT | A55M0014 NCR FSE OOT ME-M21 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-06-07 | Martin Duran | 2013-06-12 11:43 | 15100- Expansion Locks Atlantic | Martin Duran
00710 |  | NCR FSE | A55M0007 NCR FSE Valves OOT | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-06-07 | Martin Duran | 2013-06-12 11:30 | 15100- Expansion Locks Atlantic | Martin Duran
00709 |  | H1W-2B-F01 | AQ0357 NCR H1W-2B-F01 Rebar DEF | Nonconformance Report | Closed | Jose Pelaez | Construction Deficiency | 2013-06-07 | Martin Duran | 2013-06-10 11:07 | 15100- Expansion Locks Atlantic | Martin Duran
00708 |  | H4E-3A | NCRP0340CS H4E-3A-F05a Honeycombs | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-06-07 | Luz Arosemena | 2015-06-03 10:45 | 15200- Expansion Locks Pacific | Martin Duran
00707 |  | H4E-3C | NCRP0339CS H4E-3C-F05b Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-07 | Luz Arosemena | 2014-10-15 09:51 | 15200- Expansion Locks Pacific | Martin Duran
00706 |  | H4C-4A-F03 | NCRP0338CS H4C-4A-F03/02 Waterstop | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-07 | Luz Arosemena | 2013-07-27 10:33 | 15200- Expansion Locks Pacific | Martin Duran
00735 |  | ME-M07-C01 & MW | AQ0372 NCR ME-M07-C01 & MW-M07-C01 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-11 | Abdiel Santos | 2013-09-19 10:50 | 15100- Expansion Locks Atlantic | Karla Jones
00734 |  | H1E-6B-W11b CONC | AQ0370 NCR H1E-6B-W11b CONC out TOL | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-11 | Abdiel Santos | 2013-12-03 16:30 | 15100- Expansion Locks Atlantic | Karla Jones
000009 |  | H1E-3A | NCRP0360CS H1E-3A-W03 Rebar | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-12 | Luz Arosemena | 2013-07-20 10:55 | 15200- Expansion Locks Pacific | Luz Arosemena
000008 |  | H1E-2A | NCRP0359CS H1E-2A-W03 Rebar | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-12 | Luz Arosemena | 2013-07-20 10:45 | 15200- Expansion Locks Pacific | Luz Arosemena
00736 |  | UW-M19-C04b LCK | AQ0369 NCR UW-M19-C04b LCK of CMPCT | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-13 | Gloria Leguias | 2013-07-24 10:26 | 15100- Expansion Locks Atlantic | Karla Jones
00737 |  | H3C-5B-F02 | NCRP0361CS H3C-5B-F02/01 WS | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-20 | Luz Arosemena | 2013-07-20 11:03 | 15200- Expansion Locks Pacific | Nayubel Cordoba
00739 |  | NCR FSE OOT | P55M0018 NCR FSE OOT UE-M15 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-06-25 | Juan Rivera | 2013-11-06 08:26 | 15200- Expansion Locks Pacific | Martin Duran
00738 |  | NCR FSE OOT | P55M0017 NCR FSE OOT UE-M14 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-06-25 | Martin Duran | 2013-07-13 09:57 | 15200- Expansion Locks Pacific | Martin Duran
00014 |  | NCR HSH | G55M0006 NCR HSH HPU FAT | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-06-25 | Alberto Alonzo | 2014-05-21 15:37 | 15000- Expansion Locks | Alberto Alonzo
00370 |  |  | AQ0027 NCR HAZMAT Handling | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-04-14 | Karla Jones | 2012-03-03 10:23 | 15100- Expansion Locks Atlantic | Karla Jones
00369 |  |  | AQ0021 NCR Monte Lirio Disposal INS | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-02-14 | Karla Jones | 2012-03-03 10:20 | 15100- Expansion Locks Atlantic | Karla Jones
00005 |  | NCR CIM Def of | G50M0005 NCR CIM Def of Gates B | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-06-25 | Alberto Alonzo | 2014-05-21 08:54 | 15000- Expansion Locks | Alberto Alonzo
00741 |  | NCR FSE OOT | P55M0021 NCR FSE OOT UW-M15 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-06-26 | Martin Duran | 2013-07-13 10:10 | 15200- Expansion Locks Pacific | Martin Duran
00740 |  | NCR FSE OOT | P55M0020 NCR FSE OOT UW-M14 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-06-26 | Martin Duran | 2013-07-13 10:04 | 15200- Expansion Locks Pacific | Martin Duran
00744 |  | Low Strength | NCRP0356CS Low Strength Concrete S. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-06-27 | Luz Arosemena | 2013-08-23 14:27 | 15200- Expansion Locks Pacific | Luz Arosemena
00743 |  | NCR FSE OOT | P55M0023 NCR FSE OOT UW-M17 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-06-27 | Martin Duran | 2013-07-13 10:25 | 15200- Expansion Locks Pacific | Martin Duran
00742 |  | NCR FSE OOT | P55M0022 NCR FSE OOT UW-M16 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-06-27 | Martin Duran | 2013-07-13 10:15 | 15200- Expansion Locks Pacific | Martin Duran
00746 |  | NCR FSE OOT | P55M0027 NCR FSE OOT ME-M15 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-06-28 | Martin Duran | 2013-07-13 10:35 | 15200- Expansion Locks Pacific | Martin Duran
00745 |  | NCR FSE OOT | P55M0025 NCR FSE OOT UW-M20 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-06-28 | Martin Duran | 2013-07-13 10:30 | 15200- Expansion Locks Pacific | Martin Duran
00749 |  | NCR FSE OOT | P55M0031 NCR FSE OOT LW-M04 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-07-01 | Martin Duran | 2013-07-13 11:01 | 15200- Expansion Locks Pacific | Martin Duran
00748 |  | H4E-3B | NCRP0363CS H4E-3B-F05 Rebars | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-07-01 | Luz Arosemena | 2013-07-27 10:39 | 15200- Expansion Locks Pacific | Luz Arosemena
00747 |  | NCR FSE OOT | P55M0030 NCR FSE OOT MW-M16 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-07-01 | Martin Duran | 2013-07-13 10:51 | 15200- Expansion Locks Pacific | Martin Duran
00751 |  | NCR FSE OOT | P55M0033 NCR FSE OOT LW-M03 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-07-02 | Martin Duran | 2013-07-13 11:20 | 15200- Expansion Locks Pacific | Martin Duran
00750 |  | NCR FSE OOT | P55M0032 NCR FSE OOT LW-M05 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-07-02 | Martin Duran | 2013-07-13 11:13 | 15200- Expansion Locks Pacific | Martin Duran
00755 |  | NCR FSE OOT | P55M0036 NCR FSE OOT LE-M02 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-07-03 | Martin Duran | 2013-07-13 11:55 | 15200- Expansion Locks Pacific | Martin Duran
00754 |  | NCR FSE OOT | P55M0035 NCR FSE OOT LE-M10 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-07-03 | Martin Duran | 2013-08-28 15:48 | 15200- Expansion Locks Pacific | Martin Duran
00753 |  | NCR FSE OOT | P55M0034 NCR FSE OOT LE-M15 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-07-03 | Martin Duran | 2013-07-13 11:45 | 15200- Expansion Locks Pacific | Martin Duran
00752 |  | CU2 | NCRP0364CS CU2 Seepage | Nonconformance Report | In Progress | Lorely Rivera | Construction Deficiency | 2013-07-03 | Luz Arosemena | 2014-07-23 13:44 | 15200- Expansion Locks Pacific | Luz Arosemena
00148 |  |  | A-Industrial Park Effluent | Noncompliance Notice | Closed | No Ball in Court | Environmental Situation | 2011-07-22 | Larry Ohrn | 2011-12-06 14:04 | 15100- Expansion Locks Atlantic | Mercedes Peters
00149 |  |  | P – Start Work Block MW-M9 Outside | Noncompliance Notice | Closed | Rick Montanari | Quality Mgt Sys | 2011-08-05 | Rick Montanari | 2012-06-01 16:29 | 15200- Expansion Locks Pacific | Marisol Fabrega
00761 |  | H1W-6E | NCRP0365CS H1W-6E-W10c Chamfer | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-07-05 | Luz Arosemena | 2013-10-11 12:07 | 15200- Expansion Locks Pacific | Luz Arosemena
00760 |  | MW-M22 | NCRP0371CS MW-M22-C04b Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-07-05 | Luz Arosemena | 2013-09-28 11:47 | 15200- Expansion Locks Pacific | Luz Arosemena
00150 |  |  | VOID - | Noncompliance Notice | Void | No Ball in Court | Quality Mgt Sys | 2011-08-12 | Lorri Cullivan | 2011-08-15 08:28 |  | Lorri Cullivan
00759 |  | H3E-1A | NCRP0369CS H3E-1A-W13 Honeycombs | Nonconformance Report | Closed | Javier Gutierrez | Construction Deficiency | 2013-07-05 | Luz Arosemena | 2013-09-09 11:36 | 15200- Expansion Locks Pacific | Luz Arosemena
00153 |  |  | A-Excavation in Atlantic Ocean Entr | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2011-08-15 | Larry Ohrn | 2011-11-23 08:37 | 15100- Expansion Locks Atlantic | Tamira Baird
00152 |  |  | A-Concrete placing & finishing | Noncompliance Notice | Closed | Mario L. Montemayor | Quality Mgt Sys | 2011-08-15 | Tamira Baird | 2012-03-01 08:01 | 15100- Expansion Locks Atlantic | Tamira Baird
00758 |  | H1W-6D | NCRP0366CS H1W-6D-W09a&c Chamfer | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-07-05 | Luz Arosemena | 2014-01-07 11:03 | 15200- Expansion Locks Pacific | Luz Arosemena
00151 |  |  | A-Failed perform in house inspectio | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2011-08-15 | Larry Ohrn | 2011-12-28 08:34 | 15100- Expansion Locks Atlantic | Tamira Baird
00757 |  | H4E-3A | NCRP0368CS H4E-3A-F03 Rebars | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-07-05 | Luz Arosemena | 2013-07-27 10:49 | 15200- Expansion Locks Pacific | Luz Arosemena
8003 |  |  | VOID | Noncompliance Notice | Void | Antonio Betti | Construction Deficiency | 2011-08-17 | Cecilia Ung | 2011-08-24 14:40 | 15200- Expansion Locks Pacific | Cecilia Ung
00756 |  | CC6-B-04-a+b | NCRP0362CS CC6-B-04-a+b+c Deviation | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-07-05 | Luz Arosemena | 2014-03-12 10:31 | 15200- Expansion Locks Pacific | Luz Arosemena
00154 |  |  | A-ER Audit-Handl/Storage Conc Mats | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2011-08-18 | John Lopacki | 2011-11-15 14:14 | 15100- Expansion Locks Atlantic | Lorri Cullivan
00762 |  | MW-M09 | NCRP0370CS MW-M09-C04b Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-07-09 | Luz Arosemena | 2013-08-23 15:03 | 15200- Expansion Locks Pacific | Luz Arosemena
00156 | Pacific | CU2-2W-14 | P–Struct Concrete for UOM CU2-2W-14 | Noncompliance Notice | Closed | Juan H Wong | Construction Deficiency | 2011-08-25 | Javier Gutierrez | 2011-12-06 14:47 | 15200- Expansion Locks Pacific | Cecilia Ung
00763 |  | H4W-6D | NCRP0372CS H4W-6D-F01 Rebars | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-07-13 | Luz Arosemena | 2015-01-02 15:06 | 15200- Expansion Locks Pacific | Luz Arosemena
00155 |  |  | P-1939 Excavation Fill | Noncompliance Notice | Closed | No Ball in Court | Construction Deficiency | 2011-08-25 | Javier Gutierrez | 2012-06-04 15:44 | 15200- Expansion Locks Pacific | Cecilia Ung
00766 |  | H4W-3B-F05 | AQ0375 NCR H4W-3B-F05 Pouring DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-07-15 | Karla Jones | 2013-08-12 07:48 | 15100- Expansion Locks Atlantic | Karla Jones
00157 |  |  | P- QMS Doc Fill 1939 South Lagoon | Noncompliance Notice | Closed | Javier Gutierrez | Construction Deficiency | 2011-09-06 | Rick Montanari | 2011-12-14 07:37 | 15200- Expansion Locks Pacific | Cecilia Ung
00765 |  | H2W-3C-W04 REB | AQ0374 NCR H2W-3C-W04 REB INST DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-07-15 | Zosimo Correa | 2015-06-10 14:23 | 15100- Expansion Locks Atlantic | Karla Jones
00158 | Pacific | CU2-2W-13B | P–GUPC Strut Conc UOM CU2-2W-13B | Noncompliance Notice | Closed | Javier Gutierrez | Construction Deficiency | 2011-09-12 | Rick Montanari | 2012-05-11 13:41 | 15200- Expansion Locks Pacific | Cecilia Ung
00764 |  | H3W-3A-W04b | AQ0373 NCR H3W-3A-W04b Pouring DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-07-15 | Abdiel Santos | 2013-09-03 09:43 | 15100- Expansion Locks Atlantic | Karla Jones
00159 |  |  | P–GUPC Lack of Effective Curing | Noncompliance Notice | Closed | Gustavo Rivas Sr. | Construction Deficiency | 2011-09-13 | Gustavo Rivas | 2012-06-20 13:13 | 15200- Expansion Locks Pacific | Cecilia Ung
00001 |  | NCR SMC | G68M0001 NCR SMC Spool OOT | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-07-19 | Alberto Alonzo | 2014-05-21 16:01 | 15000- Expansion Locks | Alberto Alonzo
00767 |  | NCR FSE OOT | P55M0029 NCR FSE OOT MW-M22 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-07-22 | Lorely Rivera | 2015-03-28 15:09 | 15200- Expansion Locks Pacific | Martin Duran
00163 |  |  | P-HOLD of Defective Work QMS Proc | Noncompliance Notice | Closed | Juan H Wong | Quality Mgt Sys | 2011-09-20 | Rick Montanari | 2012-03-28 11:06 | 15200- Expansion Locks Pacific | Cecilia Ung
00162 | Pacific | CU2-2W-13A | P-Struc Conc for UOM CU2-2W-13A | Noncompliance Notice | Closed | Hernando Ibañez Kam | Construction Deficiency | 2011-09-20 | Lorena Jethmal | 2013-01-15 15:47 | 15200- Expansion Locks Pacific | Cecilia Ung
00769 |  | UE-M12 | NCRP0367CS UE-M12-F01 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-07-24 | Luz Arosemena | 2013-08-23 14:50 | 15200- Expansion Locks Pacific | Luz Arosemena
00768 |  | TRF1-SL-04&03 | AQ0376 NCR TRF1-SL-04&03 REB DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-07-24 | Marta Small | 2015-08-28 10:07 | 15100- Expansion Locks Atlantic | Gloria Leguias
00161 | Pacific | UW-M09-F02 | P-Stuc Conc UOM UW-M09-F02 | Noncompliance Notice | Closed | Rick Montanari | Construction Deficiency | 2011-09-20 | Lorena Jethmal | 2012-10-02 14:34 | 15200- Expansion Locks Pacific | Cecilia Ung
00772 |  | MW-M05-C01 | NCRP0375CS MW-M05-C01/02 Crack | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-07-25 | Luz Arosemena | 2013-09-16 11:32 | 15200- Expansion Locks Pacific | Luz Arosemena
00160 | Pacific | UW-M21-F02 | P-Struct Conc UOM UW-M21-F02 | Noncompliance Notice | Closed | No Ball in Court | Construction Deficiency | 2011-09-20 | Rick Montanari | 2012-06-28 16:29 | 15200- Expansion Locks Pacific | Cecilia Ung
00166 | Pacific | UE-M23-F06 | P–WIRCS0749 UE-M23-F06 Conc Repair | Noncompliance Notice | Closed | Antonio Pelusi | Construction Deficiency | 2011-09-30 | Javier Gutierrez | 2013-07-04 14:18 | 15200- Expansion Locks Pacific | Cecilia Ung
00771 |  | MW-M12 | NCRP0374CS MW-M12-W09 Voids | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-07-25 | Luz Arosemena | 2013-08-23 14:47 | 15200- Expansion Locks Pacific | Luz Arosemena
00770 |  | MW-M14 | NCRP0373CS MW-M14-W09 Voids | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-07-25 | Luz Arosemena | 2013-08-23 14:35 | 15200- Expansion Locks Pacific | Luz Arosemena
00165 |  |  | P–Thermocouples Installation Plan | Noncompliance Notice | Closed | Javier Gutierrez | Construction Deficiency | 2011-09-30 | Marisol Fabrega | 2012-01-12 14:29 | 15200- Expansion Locks Pacific | Cecilia Ung
00773 |  | TRF2-SL-03 Ext | AQ0377 NCR TRF2-SL-03 Ext Cover DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-07-29 | Marta Small | 2015-08-28 10:05 | 15100- Expansion Locks Atlantic | Gloria Leguias
00164 |  |  | P–Size of Aggr Concr Spacers | Noncompliance Notice | Closed | Juan H Wong | Construction Deficiency | 2011-09-30 | Javier Gutierrez | 2012-03-29 15:16 | 15200- Expansion Locks Pacific | Cecilia Ung
00167 |  |  | A – Steel Trowel Finishing | Noncompliance Notice | Closed | Jose Pelaez | Quality Mgt Sys | 2011-10-05 | Karla Jones | 2012-10-23 11:38 | 15100- Expansion Locks Atlantic | Tamira Baird
00774 |  | MB-BF-3 & MB-BF | AQ0378 NCR MB-BF-3 & MB-BF-4 CONC | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-07-31 | Abdiel Santos | 2013-10-21 12:26 | 15100- Expansion Locks Atlantic | Karla Jones
00169 | Pacific | CU2-1W-04 | P–Lack Imp QMS Proc UOM CU2-1W-04 | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2011-10-13 | Javier Gutierrez | 2012-05-29 07:25 | 15200- Expansion Locks Pacific | Cecilia Ung
00776 |  | NCR Super Bolts OOT | P62M0003 NCR Super Bolts OOT H2E-3C | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-08-06 | Luz Arosemena | 2015-06-23 15:25 | 15200- Expansion Locks Pacific | Martin Duran
00168 |  |  | P-Inadequate Poll Prev Meas SONOMA | Noncompliance Notice | Closed | Lisbeth K. Vergara | Environmental Situation | 2011-10-13 | Marisol Fabrega | 2012-03-09 07:44 | 15200- Expansion Locks Pacific | Cecilia Ung
00777 |  | MRB1-RW-1 | NCRP0377CS MRB1-RW-1-F01 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-08-07 | Luz Arosemena | 2013-09-21 11:27 | 15200- Expansion Locks Pacific | Luz Arosemena
00170 | Pacific | UW-M10-F02 | P–Struc Conc UOM UW-M10-F02 & F02 | Noncompliance Notice | Closed | Rick Montanari | Construction Deficiency | 2011-10-14 | Lorena Jethmal | 2012-10-09 07:45 | 15200- Expansion Locks Pacific | Cecilia Ung
00002 |  | MG-02-W03b | NCRP0381CS MG-02-W03b Electrical G. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-08-08 | Luz Arosemena | 2014-01-13 10:49 | 15200- Expansion Locks Pacific | Luz Arosemena
00171 | Pacific | UE-M10-F01 & F02 | P-Strut Conc UOM UE-M10-F01 & F02 | Noncompliance Notice | Closed | Javier Gutierrez | Construction Deficiency | 2011-10-22 | Rick Montanari | 2012-10-09 09:17 | 15200- Expansion Locks Pacific | Cecilia Ung
00001 |  | MB1-2D | NCRP0380CS MB1-2D Column Anchoring | Nonconformance Report | Void | No Ball in Court | Construction Deficiency | 2013-08-08 | Javier Gutierrez | 2013-12-01 16:00 | 15200- Expansion Locks Pacific | Luz Arosemena
00173 |  |  | A–Tower Cranes used to support Conc | Noncompliance Notice | Closed | No Ball in Court | Safety & Health Issue | 2011-10-24 | Tamira Baird | 2012-05-24 13:35 | 15100- Expansion Locks Atlantic | Tamira Baird
00778 |  | Low Strenght | NCRP0379CS Low Strenght Concrete R. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-08-09 | Javier Gutierrez | 2013-11-12 14:22 | 15200- Expansion Locks Pacific | Luz Arosemena
00172 |  |  | P – GUPC Structural Concrete Finish | Noncompliance Notice | Closed | Antonio Pelusi | Quality Mgt Sys | 2011-10-24 | Marta Small | 2013-07-04 14:12 | 15200- Expansion Locks Pacific | Vielka Walters
00780 |  | CC5-J | NCRP0383CS CC5-J-04 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-08-12 | Luz Arosemena | 2014-05-09 10:41 | 15200- Expansion Locks Pacific | Luz Arosemena
00779 |  | ME-M12 | NCRP0378CS ME-M12-W09 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-08-12 | Luz Arosemena | 2013-09-21 11:11 | 15200- Expansion Locks Pacific | Luz Arosemena
00174 | Pacific | UE-M16-F01 | P – Struc Concrete - UOM UE-M16-F01 | Noncompliance Notice | Closed | Rick Montanari | Quality Mgt Sys | 2011-10-25 | Rick Montanari | 2012-07-10 09:50 | 15200- Expansion Locks Pacific | Vielka Walters
00176 | Pacific | UW-M21-F01 | P – Struct Concrete UOM UW-M21 F01 | Noncompliance Notice | Closed | Javier Gutierrez | Quality Mgt Sys | 2011-11-07 | Rick Montanari | 2012-05-11 13:42 | 15200- Expansion Locks Pacific | Vielka Walters
00781 |  | H2E-1A-W02 Lack | NCRP0349CS H2E-1A-W02 Lack of Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-08-14 | Luz Arosemena | 2013-10-10 14:06 | 15200- Expansion Locks Pacific | Luz Arosemena
00175 | Pacific | CU2-C-04 | P – Struct Concrete UOM CU2-0C-04 | Noncompliance Notice | Closed | Rick Montanari | Quality Mgt Sys | 2011-11-07 | Lorena Jethmal | 2012-10-02 14:40 | 15200- Expansion Locks Pacific | Vielka Walters
00783 |  | LE-M21-W06 REB | AQ0381 NCR LE-M21-W06 REB INST DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-08-15 | Abdiel Santos | 2013-11-15 15:46 | 15100- Expansion Locks Atlantic | Karla Jones
00782 |  | Seepage Barrier | NCRP0382CS Seepage Barrier 3 Fill | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-08-15 | Luz Arosemena | 2013-09-27 11:26 | 15200- Expansion Locks Pacific | Luz Arosemena
00177 |  |  | A–Constructing on Non-conforming Wo | Noncompliance Notice | Closed | Maria Baz | Quality Mgt Sys | 2011-11-23 | Tamira Baird | 2012-01-20 13:53 | 15100- Expansion Locks Atlantic | Tamira Baird
00784 |  | NCR FSE OOT | P55M0028 NCR FSE OOT MW-M15 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-08-19 | Lorely Rivera | 2015-03-28 14:51 | 15200- Expansion Locks Pacific | Martin Duran
00178 | Pacific | H2E-3A-F05 | P – Struct Concrete UOM H2E-3A-F05 | Noncompliance Notice | Closed | Samuel Cohen | Quality Mgt Sys | 2011-12-01 | Lorena Jethmal | 2013-01-18 15:07 | 15200- Expansion Locks Pacific | Vielka Walters
00179 |  |  | A – QMS Failure: Lockhead 2 | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2011-12-07 | Tamira Baird | 2012-05-24 13:34 | 15100- Expansion Locks Atlantic | Tamira Baird
00775 |  | NCR FSE OOT | P55M0019 NCR FSE OOT UE-M17 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-08-19 | Lorely Rivera | 2015-03-28 13:41 | 15200- Expansion Locks Pacific | Martin Duran
00181 |  |  | P – Protective Dev Barriers Exc Wks | Noncompliance Notice | Closed | Carlos Reyes | Safety & Health Issue | 2011-12-12 | Ernesto Hugues | 2012-07-10 08:59 | 15200- Expansion Locks Pacific | Vielka Walters
00787 |  | MW-M11-MC | AQ0384 NCR MW-M11-MC-CTJ Seepage | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-08-20 | Abdiel Santos | 2013-10-21 16:05 | 15100- Expansion Locks Atlantic | Karla Jones
00180 |  |  | P – Unsafe Access/Egress Work Front | Noncompliance Notice | Closed | Ernesto Hugues | Safety & Health Issue | 2011-12-12 | Lorena Jethmal | 2012-10-03 13:24 | 15200- Expansion Locks Pacific | Vielka Walters
00786 |  | NCR FSE OOT | P55M0037 NCR FSE OOT LW-M10 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-08-20 | Lorely Rivera | 2015-03-28 14:59 | 15200- Expansion Locks Pacific | Martin Duran
00183 |  |  | P – GUPC Incomplete QMS Doc Process | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2011-12-15 | Lorena Jethmal | 2012-08-17 13:46 | 15200- Expansion Locks Pacific | Vielka Walters
00785 |  | NCR FSE OOT | P55M0026 NCR FSE OOT UW-M22 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-08-20 | Lorely Rivera | 2015-03-28 14:39 | 15200- Expansion Locks Pacific | Martin Duran
00790 |  | UE-M22-SC | AQ0382 NCR UE-M22-SC-CTJ Seepage | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-08-21 | Abdiel Santos | 2013-10-21 15:58 | 15100- Expansion Locks Atlantic | Karla Jones
00182 |  |  | P – Vegetation at Disposal Site N4 | Noncompliance Notice | Closed | Lisbeth K. Vergara | Environmental Situation | 2011-12-15 | Alicia Villalobos | 2014-09-10 14:06 | 15200- Expansion Locks Pacific | Vielka Walters
00789 |  | MW-M12-MC | AQ0385 NCR MW-M12-MC-CTJ Seepage | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-08-21 | Abdiel Santos | 2013-10-21 16:10 | 15100- Expansion Locks Atlantic | Karla Jones
00184 |  |  | A–Sedimentation Discharge from West | Noncompliance Notice | Closed | Jose E. Reyes | Environmental Situation | 2011-12-28 | Tamira Baird | 2012-05-21 08:10 | 15100- Expansion Locks Atlantic | Tamira Baird
00185 |  |  | A – Monte Lirio Lagoon – Control | Noncompliance Notice | Closed | Luis Castaneda | Environmental Situation | 2012-01-04 | Alicia Villalobos | 2012-04-04 10:30 | 15100- Expansion Locks Atlantic | Tamira Baird
00788 |  | H1W-3C-W04 a | AQ0379 NCR H1W-3C-W04 a CONC DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-08-21 | Abdiel Santos | 2014-01-31 15:22 | 15100- Expansion Locks Atlantic | Karla Jones
00793 |  | NCR FSE OOT | P55M0016 NCR FSE OOT UW-M15 | Nonconformance Report | Closed | Juan Arturo Rivera | Construction Deficiency | 2013-08-22 | Lorely Rivera | 2015-05-19 18:00 | 15200- Expansion Locks Pacific | Martin Duran
00186 |  |  | G-Gate FAB without SUB of shop DWG | Noncompliance Notice | Closed | No Ball in Court | Contract Term | 2012-01-10 | John Lopacki | 2012-02-28 06:56 | 15004- Expansion Locks Design | Mercedes Peters
00188 | Atlantic | CC2-B-04b | A – CC2-B-04b Geometric Deviations | Noncompliance Notice | Closed | Jose E. Reyes | Construction Deficiency | 2012-01-19 | Tamira Baird | 2012-02-17 13:42 | 15100- Expansion Locks Atlantic | Tamira Baird
00792 |  | NCR FSE OOT | P55M0024 NCR FSE OOT UE-M21 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-08-22 | Lorely Rivera | 2015-03-28 14:28 | 15200- Expansion Locks Pacific | Martin Duran
00187 | Atlantic | CC2-B-04a | A – CC2-B-04a Geometric Deviations | Noncompliance Notice | Closed | Jose E. Reyes | Construction Deficiency | 2012-01-19 | Tamira Baird | 2012-02-17 13:42 | 15100- Expansion Locks Atlantic | Tamira Baird
00791 |  | MW-M10-MC | AQ0383 NCR MW-M10-MC-CTJ Seepage | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-08-22 | Abdiel Santos | 2013-10-21 16:02 | 15100- Expansion Locks Atlantic | Karla Jones
00190 |  |  | G-Doc Control As-Built Drawings | Noncompliance Notice | Closed | No Ball in Court | Administrative | 2012-01-24 | John Lopacki | 2014-01-20 11:05 | 15000- Expansion Locks | Mercedes Peters
00794 |  | UE-M13 | NCRP0391CS UE-M13-W06 Rebars | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-08-24 | Luz Arosemena | 2013-09-28 11:51 | 15200- Expansion Locks Pacific | Luz Arosemena
00189 |  |  | G-Doc Control Submittal Register | Noncompliance Notice | Closed | No Ball in Court | Administrative | 2012-01-24 | John Lopacki | 2012-04-18 09:46 | 15000- Expansion Locks | Mercedes Peters
00799 |  | ME-M11-SC | AQ0389 NCR ME-M11-SC-CTJ Seepage | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-08-30 | Marta Small | 2015-08-28 09:56 | 15100- Expansion Locks Atlantic | Abdiel Santos
00798 |  | UW-M03-SC | AQ0388 NCR UW-M03-SC-CTJ Seepage | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-08-30 | Marta Small | 2015-08-28 09:57 | 15100- Expansion Locks Atlantic | Abdiel Santos
00191 |  |  | P–Dust Control at the PAC Work Site | Noncompliance Notice | Closed | No Ball in Court | Safety & Health Issue | 2012-02-08 | Carlos Reyes | 2012-11-24 09:39 | 15200- Expansion Locks Pacific | Marisol Fabrega
00001 |  |  |  | Noncompliance Notice | Void | Juan Arturo Rivera | Defective Materials | 2012-02-17 | Juan Rivera | 2012-02-17 11:27 |  | Juan Rivera
00797 |  | MW-M23 | NCRP0392CS MW-M23-C04b Cracks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-08-30 | Luz Arosemena | 2013-10-11 09:00 | 15200- Expansion Locks Pacific | Luz Arosemena
00796 |  | H2E-6A | AQ0387 NCR H2E-6A - East-Seepage | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-08-30 | Marta Small | 2015-08-28 10:02 | 15100- Expansion Locks Atlantic | Abdiel Santos
00193 |  |  | G-Lack of Timely Pub Disc of Equip | Noncompliance Notice | Closed | Jorge de la Guardia | Environmental Situation | 2012-02-24 | Lil Torres | 2012-05-15 11:25 | 15000- Expansion Locks | Mercedes Peters
00795 |  | H2E-6A | AQ0386 NCR H2E-6A - West-Seepage | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-08-30 | Marta Small | 2015-08-28 10:03 | 15100- Expansion Locks Atlantic | Abdiel Santos
00192 |  |  | G-Failure to impl incid investn pro | Noncompliance Notice | Closed | Eduardo Shaw | Safety & Health Issue | 2012-02-24 | Brittania Diez | 2012-08-08 07:25 | 15000- Expansion Locks | Mercedes Peters
00802 |  | LW-M11-SC | AQ0392 NCR LW-M11-SC-CTJ Seepage | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-08-31 | Abdiel Santos | 2013-12-10 14:32 | 15100- Expansion Locks Atlantic | Abdiel Santos
00195 |  |  | P-Fail Follow Design SMC IMC | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2012-02-28 | Rick Montanari | 2012-07-27 14:55 | 15200- Expansion Locks Pacific | Mercedes Peters
00194 |  |  | A-Failure to Implement an Effective | Noncompliance Notice | Closed | Jose Pelaez | Safety & Health Issue | 2012-02-28 | Carlos Reyes | 2012-07-03 09:11 | 15100- Expansion Locks Atlantic | Tamira Baird
00801 |  | LW-M09-MC | AQ0391 NCR LW-M09-MC-CTJ Seepage | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-08-31 | Abdiel Santos | 2013-12-10 14:31 | 15100- Expansion Locks Atlantic | Abdiel Santos
00800 |  | ME-M14-MC | AQ0390 NCR ME-M14-MC-CTJ Seepage | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-08-31 | Abdiel Santos | 2013-12-10 14:30 | 15100- Expansion Locks Atlantic | Abdiel Santos
00197 |  |  | P-Failure Overbreak Design Works | Noncompliance Notice | Closed | Rick Montanari | Construction Deficiency | 2012-03-02 | Rick Montanari | 2012-06-01 16:35 | 15200- Expansion Locks Pacific | Cecilia Ung
00810 |  | UE-M14-MC CTJ | NCRP0394CS UE-M14-MC CTJ MOR Jul | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-09-02 | Javier Gutierrez | 2013-10-16 17:23 | 15200- Expansion Locks Pacific | Luz Arosemena
00196 |  |  | G - Use Non Certified Equipment BTB | Noncompliance Notice | Closed | No Ball in Court | Safety & Health Issue | 2012-03-02 | Carlos Reyes | 2012-11-24 09:40 | 15200- Expansion Locks Pacific | Cecilia Ung
00809 |  | MW-M09-SC CTJ | NCRP0390CS MW-M09-SC CTJ MOR Jun | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-09-02 | Javier Gutierrez | 2013-10-16 16:20 | 15200- Expansion Locks Pacific | Luz Arosemena
00200 |  |  | P-Work Proc with OPN NCR orHOLD Con | Noncompliance Notice | Closed | Rick Montanari | Quality Mgt Sys | 2012-03-09 | Gustavo Rivas | 2012-07-27 16:11 | 15200- Expansion Locks Pacific | Mercedes Peters
00808 |  | UW-M10-SC | NCRP0389CS UW-M10-SC CTJ MORJun&Jul | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-09-02 | Javier Gutierrez | 2013-10-16 16:35 | 15200- Expansion Locks Pacific | Luz Arosemena
00199 |  |  | P-Insuff Reinf Steel Concrete Cover | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2012-03-09 | Rick Montanari | 2012-07-27 15:02 | 15200- Expansion Locks Pacific | Mercedes Peters
00198 |  |  | G-Failure to implement Gen Mgmt. Pr | Noncompliance Notice | Open | Carlos Reyes | Safety & Health Issue | 2012-03-09 | Brittania Diez | 2014-11-18 08:43 | 15000- Expansion Locks | Tamira Baird
00807 |  | UE-M12-SC CTJ | NCRP0387CS UE-M12-SC CTJ MOR Jul | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-09-02 | Javier Gutierrez | 2013-10-16 16:55 | 15200- Expansion Locks Pacific | Luz Arosemena
00806 |  | UE-M14-SC CTJ | NCRP0386CS UE-M14-SC CTJ MOR Jun | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-09-02 | Javier Gutierrez | 2013-10-16 17:02 | 15200- Expansion Locks Pacific | Luz Arosemena
00203 |  |  | P-Work Proceeding with OPN NCR Hold | Noncompliance Notice | Void | Antonio Pelusi | Quality Mgt Sys | 2012-03-16 | Mercedes Peters | 2012-03-20 09:42 | 15200- Expansion Locks Pacific | Mercedes Peters
00202 |  |  | P–Start Work Disposal N1 Lack QMdoc | Noncompliance Notice | Closed | Javier Gutierrez | Quality Mgt Sys | 2012-03-16 | Rick Montanari | 2012-05-24 16:50 | 15200- Expansion Locks Pacific | Mercedes Peters
00805 |  | LW-M05-SC CTJ | NCRP0385CS LW-M05-SC CTJ MOR Jun | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-09-02 | Javier Gutierrez | 2013-10-16 15:21 | 15200- Expansion Locks Pacific | Luz Arosemena
00201 |  |  | P-Concrete Waste Disposal PAC Locks | Noncompliance Notice | Closed | Gustavo Rivas Sr. | Environmental Situation | 2012-03-16 | Lorena Jethmal | 2012-07-05 12:59 | 15200- Expansion Locks Pacific | Mercedes Peters
00804 |  | LW-M04-SC CTJ | NCRP0384CS LW-M04-SC CTJ MORJun/Jul | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-09-02 | Javier Gutierrez | 2013-10-16 17:14 | 15200- Expansion Locks Pacific | Luz Arosemena
00803 |  | UW-M12-SC CTJ | NCRP0376CS UW-M12-SC CTJ MOR JUN | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-09-02 | Javier Gutierrez | 2013-10-16 16:10 | 15200- Expansion Locks Pacific | Luz Arosemena
00204 |  |  | P–Crack Monolith Lack Cont Improve | Noncompliance Notice | Closed | Ramon Cascante | Quality Mgt Sys | 2012-03-19 | Lorena Jethmal | 2013-03-22 14:26 | 15200- Expansion Locks Pacific | Mercedes Peters
00811 |  | H4W-1C-W04 | AQ0393 NCR H4W-1C-W04 Rebar DEF. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-09-03 | Abdiel Santos | 2013-12-10 14:39 | 15100- Expansion Locks Atlantic | Abdiel Santos
00209 |  |  | P-Tower Crane Proximity Control | Noncompliance Notice | Closed | Carlos Reyes | Safety & Health Issue | 2012-03-22 | Ernesto Hugues | 2012-07-04 10:24 | 15200- Expansion Locks Pacific | Mercedes Peters
00814 |  | UE-M08-MC CTJ | NCRP0399CS UE-M08-MC CTJ MOR Aug | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-09-04 | Javier Gutierrez | 2013-10-16 15:19 | 15200- Expansion Locks Pacific | Luz Arosemena
00208 |  |  | A – Use of Unsafe Ladders and Stepl | Noncompliance Notice | Closed | Eduardo Shaw | Safety & Health Issue | 2012-03-22 | Carlos Reyes | 2012-07-03 09:07 | 15100- Expansion Locks Atlantic | Tamira Baird
00207 |  |  | A – Safe Access to Working Surfaces | Noncompliance Notice | Closed | Eduardo Shaw | Safety & Health Issue | 2012-03-22 | Carlos Reyes | 2012-07-03 09:00 | 15100- Expansion Locks Atlantic | Tamira Baird
00813 |  | UE-M11-MC CTJ | NCRP0398CS UE-M11-MC CTJ MOR Aug | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-09-04 | Javier Gutierrez | 2013-10-16 17:19 | 15200- Expansion Locks Pacific | Luz Arosemena
00206 |  |  | A – Inspection and Documentation of | Noncompliance Notice | Closed | Eduardo Shaw | Safety & Health Issue | 2012-03-22 | Carlos Reyes | 2012-07-03 09:09 | 15100- Expansion Locks Atlantic | Tamira Baird
00812 |  | MW-M16-SC CTJ | NCRP0388CS MW-M16-SC CTJ MOR Jun | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-09-04 | Javier Gutierrez | 2013-10-16 16:29 | 15200- Expansion Locks Pacific | Luz Arosemena
00816 |  | ME-M13 | NCRP0397CS ME-M13-C02 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-09-10 | Luz Arosemena | 2014-01-07 10:58 | 15200- Expansion Locks Pacific | Luz Arosemena
00205 |  |  | A – Fall Prevenetion Program Atlant | Noncompliance Notice | Closed | Carlos Reyes | Safety & Health Issue | 2012-03-22 | Tamira Baird | 2012-10-15 15:14 | 15100- Expansion Locks Atlantic | Tamira Baird
00815 |  | MW-M13 | NCRP0396CS MW-M13-C02 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-09-10 | Luz Arosemena | 2014-12-22 15:03 | 15200- Expansion Locks Pacific | Luz Arosemena
00210 |  |  | A – Tower Crane Proximity Control | Noncompliance Notice | Closed | Wally Pena | Safety & Health Issue | 2012-03-26 | Tamira Baird | 2012-10-15 15:21 | 15100- Expansion Locks Atlantic | Tamira Baird
00214 |  |  | P-Appropriate ladder for activity | Noncompliance Notice | Closed | Carlos Reyes | Safety & Health Issue | 2012-03-28 | Ernesto Hugues | 2012-07-10 09:10 | 15200- Expansion Locks Pacific | Mercedes Peters
00817 |  | ME-M04 | NCRP0393CS ME-M04-C04c Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-09-12 | Luz Arosemena | 2013-09-28 11:54 | 15200- Expansion Locks Pacific | Luz Arosemena
00818 |  | VS4-C03 | NCRP0402CS VS4-C03-B1 Alignment | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-09-14 | Luz Arosemena | 2013-10-03 15:24 | 15200- Expansion Locks Pacific | Luz Arosemena
00213 |  |  | P-Inspection of Guardrails | Noncompliance Notice | Closed | Carlos Reyes | Safety & Health Issue | 2012-03-28 | Ernesto Hugues | 2012-07-17 10:42 | 15200- Expansion Locks Pacific | Mercedes Peters
00212 |  |  | P-Ladder pre-use check | Noncompliance Notice | Closed | Antonio Pelusi | Safety & Health Issue | 2012-03-28 | Ernesto Hugues | 2012-07-10 09:11 | 15200- Expansion Locks Pacific | Mercedes Peters
00819 |  | IE-M02-F01 | NCRP0405CS IE-M02-F01 Concrete Void | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-09-16 | Luz Arosemena | 2013-09-28 11:58 | 15200- Expansion Locks Pacific | Luz Arosemena
00820 |  | CC6-D | NCRP0406CS CC6-D-02 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-09-17 | Luz Arosemena | 2013-10-03 15:30 | 15200- Expansion Locks Pacific | Luz Arosemena
00211 |  |  | P-Safe Use of Ladders and Stairs | Noncompliance Notice | Closed | Ernesto Hugues | Safety & Health Issue | 2012-03-28 | Jose Gonzalez | 2012-09-24 11:34 | 15200- Expansion Locks Pacific | Mercedes Peters
00215 |  |  | A – Atlantic Approach Channel | Noncompliance Notice | Closed | Jose Pelaez | Quality Mgt Sys | 2012-03-30 | Karla Jones | 2012-09-26 16:49 | 15100- Expansion Locks Atlantic | Tamira Baird
00821 |  | Mn Wrkshp Illgl | AE8040 NcR Mn Wrkshp Illgl Rep Area | Nonconformance Report | Closed | No Ball in Court | Environmental Situation | 2013-09-25 | Marta Small | 2015-08-28 09:55 | 15100- Expansion Locks Atlantic | Adrian Lee
00822 |  | OE-M06-F01 | NCRP0407CS OE-M06-F01 Water Filtrat | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-09-27 | Luz Arosemena | 2013-10-26 10:20 | 15200- Expansion Locks Pacific | Luz Arosemena
00216 |  |  | P-Ina Mgmt of Haz Waste Exc Area | Noncompliance Notice | Closed | Gustavo Rivas Sr. | Environmental Situation | 2012-04-05 | Lorena Jethmal | 2012-07-09 12:16 | 15200- Expansion Locks Pacific | Mercedes Peters
00823 |  | MRB2-EG02-W01 | AQ0394 NCR -MRB2-EG02-W01 Rebar_DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-09-30 | Abdiel Santos | 2013-12-10 14:41 | 15100- Expansion Locks Atlantic | Abdiel Santos
00217 |  |  | A – Inlet Wing Wall Excavation | Noncompliance Notice | Closed | Jose Pelaez | Quality Mgt Sys | 2012-04-12 | Karla Jones | 2012-08-03 08:05 | 15100- Expansion Locks Atlantic | Tamira Baird
00218 |  |  | A – Adding Water During Steel Trowe | Noncompliance Notice | Closed | Jose Pelaez | Quality Mgt Sys | 2012-05-15 | Karla Jones | 2013-03-01 15:32 | 15100- Expansion Locks Atlantic | Tamira Baird
00824 |  | Bld MB-SBP | NCRP0409CS Bld MB-SBP Anchor Bolt | Nonconformance Report | Void | No Ball in Court | Construction Deficiency | 2013-10-02 | Lorely Rivera | 2016-03-03 08:29 | 15200- Expansion Locks Pacific | Luz Arosemena
00825 |  | UE-M17-SC | NCRP0404CS UE-M17-SC-CTJ Seepage | Nonconformance Report | Terminated | Javier Gutierrez | Construction Deficiency | 2013-10-03 | Jonathan Gonzalez | 2013-10-17 14:58 | 15200- Expansion Locks Pacific | Luz Arosemena
00219 |  |  | P- Failure Follow WPR & ENP Disp 12 | Noncompliance Notice | Closed | No Ball in Court | Construction Deficiency | 2012-05-19 | Marco Villarreal | 2014-10-29 08:52 | 15200- Expansion Locks Pacific | Donald Espino
00826 |  | MW-M17-C04b | NCRP0408CS MW-M17-C04b SC Honeycomb | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-10-04 | Luz Arosemena | 2013-10-22 15:11 | 15200- Expansion Locks Pacific | Luz Arosemena
00220 |  |  | A – Condition of Concrete Formwork | Noncompliance Notice | Closed | Roberto Febbroni | Quality Mgt Sys | 2012-06-06 | Karla Jones | 2012-10-18 11:32 | 15100- Expansion Locks Atlantic | Tamira Baird
00221 |  |  | A – Mindi Camp Wastewater Effluent | Noncompliance Notice | Closed | Jose E. Reyes | Environmental Situation | 2012-07-05 | Gene Rodríguez | 2012-09-24 09:23 | 15100- Expansion Locks Atlantic | Tamira Baird
00827 |  | MRB3-EG02-F01 | AQ0380 NCR MRB3-EG02-F01 POUR DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-10-05 | Abdiel Santos | 2014-01-13 16:36 | 15100- Expansion Locks Atlantic | Abdiel Santos
00222 |  |  | P-Disp N4 Constr Not As DesignSpec | Noncompliance Notice | Closed | Javier Gutierrez | Quality Mgt Sys | 2012-07-18 | Rick Montanari | 2012-10-02 14:58 | 15200- Expansion Locks Pacific | Lorena Jethmal
00830 |  | UE-M17-C04c | NCRP0412CS UE-M17-C04c MC Honeycomb | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-10-07 | Javier Gutierrez | 2013-12-23 14:29 | 15200- Expansion Locks Pacific | Luz Arosemena
00223 |  |  | G-Failure to Prov Updated Dwg List | Noncompliance Notice | Closed | No Ball in Court | Contract Term | 2012-08-03 | Mercedes Peters | 2016-07-20 15:35 | 15000- Expansion Locks | Lorena Jethmal
00829 |  | UW-M01-WA | NCRP0411CS UW-M01-WA MC Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-10-07 | Javier Gutierrez | 2013-12-19 08:40 | 15200- Expansion Locks Pacific | Luz Arosemena
00828 |  | UE-M16-C04c | NCRP0410CS UE-M16-C04c MC Honeycomb | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-10-07 | Javier Gutierrez | 2013-11-12 14:22 | 15200- Expansion Locks Pacific | Luz Arosemena
00224 |  |  | A – Unsafe Rigging Practice | Noncompliance Notice | Closed | Jose E. Reyes | Unsafe conditions | 2012-08-07 | Tamira Baird | 2013-06-04 11:08 | 15100- Expansion Locks Atlantic | Tamira Baird
00833 |  | H1W-6D-W08 | NCRP0403CS H1W-6D-W08 Roof Seepage | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-10-11 | Javier Gutierrez | 2013-10-16 16:40 | 15200- Expansion Locks Pacific | Luz Arosemena
00225 |  |  | A – Concrete Temperature Monitoring | Noncompliance Notice | Closed | Jose Pelaez | Quality Mgt Sys | 2012-08-09 | Gene Rodríguez | 2012-09-07 09:52 | 15100- Expansion Locks Atlantic | Tamira Baird
00227 |  |  | A-Implementation of the Lockout/Tag | Noncompliance Notice | Closed | No Ball in Court | Safety & Health Issue | 2012-08-21 | Carlos Reyes | 2012-11-24 09:56 | 15100- Expansion Locks Atlantic | Tamira Baird
00832 |  | ME-M04-SC | NCRP0401CS ME-M04-SC CTL Seepage | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-10-11 | Javier Gutierrez | 2013-10-16 15:47 | 15200- Expansion Locks Pacific | Luz Arosemena
00226 |  |  | P-Lack Sedim Ctrl Measures for Exca | Noncompliance Notice | Closed | Gustavo Rivas Sr. | Environmental Situation | 2012-08-21 | Marta Small | 2013-07-26 14:32 | 15200- Expansion Locks Pacific | Lorena Jethmal
00831 |  | ME-M02-SC | NCRP0400CS ME-M02-SC CTJ Seepage | Nonconformance Report | Terminated | No Ball in Court | Construction Deficiency | 2013-10-11 | Javier Gutierrez | 2013-10-16 15:22 | 15200- Expansion Locks Pacific | Luz Arosemena
00228 |  |  | P-Lack SWP Implement Clear Grub | Noncompliance Notice | Closed | Ernesto Hugues | Safety & Health Issue | 2012-08-22 | Lorena Jethmal | 2012-10-03 13:30 | 15200- Expansion Locks Pacific | Lorena Jethmal
00015 |  | HSH | GM2509 CAR HSH MQP Cylinders | Nonconformance Report | Closed | NO BIC-GUPC | Quality Mgt Sys | 2013-10-19 | Gene Williams | 2015-09-04 15:11 | 15004- Expansion Locks Design | Alberto Alonzo
00229 |  |  | VOID | Noncompliance Notice | Void | Gonzalo Menendez |  | 2012-08-28 | Marisol Fabrega | 2012-08-28 15:53 |  | Ymelda Smith Martínez
00834 |  | H3E-3B-W12 | NCRP0415CS H3E-3B-W12 Valve Slot | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-10-24 | Luz Arosemena | 2014-03-12 10:43 | 15200- Expansion Locks Pacific | Luz Arosemena
00835 |  | H4W-1C/3C-W04 | AQ0395 NCR H4W-1C/3C-W04 Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-10-28 | Abdiel Santos | 2013-12-03 11:16 | 15100- Expansion Locks Atlantic | Abdiel Santos
00232 |  |  | P-Accident Investigate Haul Operate | Noncompliance Notice | Closed | Antonio Pelusi | Safety & Health Issue | 2012-08-30 | Lorena Jethmal | 2012-10-24 11:41 | 15200- Expansion Locks Pacific | Lorena Jethmal
00231 |  |  | P-Accident Incident Conc Operations | Noncompliance Notice | Closed | Antonio Pelusi | Unsafe conditions | 2012-08-30 | Lorena Jethmal | 2012-10-24 08:19 | 15200- Expansion Locks Pacific | Lorena Jethmal
00836 |  | T1-C2-07-F01b | AQ0397 NCR T1-C2-07-F01b Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-10-29 | Abdiel Santos | 2013-12-10 14:42 | 15100- Expansion Locks Atlantic | Abdiel Santos
00230 |  |  | P- Placing Concrete Mix No ACP RVW | Noncompliance Notice | Closed | Gustavo Rivas Sr. | Quality Mgt Sys | 2012-08-30 | Lorena Jethmal | 2012-10-03 11:32 | 15200- Expansion Locks Pacific | Lorena Jethmal
00841 |  | ME-M09-F01 | NCRP0420CS ME-M09-F01 MC Cracks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-10-31 | Luz Arosemena | 2014-01-07 15:10 | 15200- Expansion Locks Pacific | Luz Arosemena
00234 |  |  | P-Lack of Mobile Cranes Daily Insp | Noncompliance Notice | Closed | No Ball in Court | Safety & Health Issue | 2012-09-12 | Carlos Reyes | 2012-11-24 09:57 | 15200- Expansion Locks Pacific | Lorena Jethmal
00006 |  | NCR CIM Anodes C1 | G50M0007 NCR CIM Anodes C1 & C2 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-10-31 | Alberto Alonzo | 2014-05-20 16:24 | 15000- Expansion Locks | Alberto Alonzo
00838 |  | T2-C3-04-03-F01 | AQ0399 NCR T2-C3-04-03-F01 Class IX | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-11-12 | Abdiel Santos | 2014-01-13 16:43 | 15100- Expansion Locks Atlantic | Abdiel Santos
00233 |  |  | P-Cranes Operators Qualification | Noncompliance Notice | Void | Antonio Pelusi | Errors and Omissions | 2012-09-12 | Lorena Jethmal | 2012-09-13 14:46 | 15200- Expansion Locks Pacific | Lorena Jethmal
00235 |  |  | P-Cranes Operators Qualification | Noncompliance Notice | Closed | No Ball in Court | Safety & Health Issue | 2012-09-13 | Carlos Reyes | 2012-11-24 10:00 | 15200- Expansion Locks Pacific | Lorena Jethmal
00837 |  | T1-C3-F01 Class | AQ0398 NCR T1-C3-F01 Class IX break | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-11-12 | Abdiel Santos | 2014-02-11 09:25 | 15100- Expansion Locks Atlantic | Abdiel Santos
00016 |  | NCR HSH | G55M0007 NCR HSH Cylinder Supports | Nonconformance Report | Terminated | NO BIC-GUPC | Construction Deficiency | 2013-11-14 | Alberto Alonzo | 2014-05-21 15:43 | 15000- Expansion Locks | Alberto Alonzo
00236 |  |  | A–Effluent from Industrial Park D | Noncompliance Notice | Open | Ramon Porcell | Environmental Situation | 2012-09-17 | Ymelda Smith Martínez | 2016-09-20 10:50 | 15100- Expansion Locks Atlantic | Gene Rodríguez
00007 |  | NCR CIM | G50M0008 NCR CIM Recess Closure | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-11-14 | Alberto Alonzo | 2014-05-21 09:00 | 15000- Expansion Locks | Alberto Alonzo
00237 |  |  | P-Inapprop Mgmnt Scrap-Used Tires | Noncompliance Notice | Closed | Gustavo Rivas Sr. | Environmental Situation | 2012-10-01 | Alicia Villalobos | 2013-02-25 11:28 | 15200- Expansion Locks Pacific | Lorena Jethmal
00001 |  | NCR | G83M0001 NCR SEL Cabinets | Nonconformance Report | Closed | NO BIC-GUPC | Errors and Omissions | 2013-11-14 | Alberto Alonzo | 2014-05-21 16:03 | 15000- Expansion Locks | Alberto Alonzo
00240 |  |  | P-Lack temp erosion control disp 5 | Noncompliance Notice | Closed | Gustavo Rivas Sr. | Environmental Situation | 2012-11-01 | Lorena Jethmal | 2013-03-25 09:19 | 15200- Expansion Locks Pacific | Lorena Jethmal
00239 |  |  | P-Lack temp erosion control disp 2 | Noncompliance Notice | Closed | Luis Isaza | Environmental Situation | 2012-11-01 | Marta Small | 2016-03-23 13:44 | 15200- Expansion Locks Pacific | Lorena Jethmal
00839 |  | BLD MB Slab | NCRP0395CS BLD MB Slab Steel Fram | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-11-15 | Lorely Rivera | 2016-07-11 11:56 | 15200- Expansion Locks Pacific | Javier Gutierrez
00238 |  |  | P-Use of Non Certified Equipment | Noncompliance Notice | Closed | Ernesto Hugues | Safety & Health Issue | 2012-11-01 | Lorena Jethmal | 2012-12-26 08:40 | 15200- Expansion Locks Pacific | Lorena Jethmal
00840 |  | Backfill LMC | AQ0396 NCR Backfill LMC Geo. Inst. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-11-18 | Zosimo Correa | 2015-06-03 10:42 | 15100- Expansion Locks Atlantic | Abdiel Santos
00842 |  | ME-M03 | NCRP0416CS ME-M03-MC Cracks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-11-20 | Javier Gutierrez | 2013-12-23 14:34 | 15200- Expansion Locks Pacific | Luz Arosemena
00242 |  |  | G-Concrete Placing Temp Ctrl Monit | Noncompliance Notice | Closed | No Ball in Court | Administrative | 2012-12-04 | Francisco Fong | 2013-09-26 10:13 | 15000- Expansion Locks | Lorena Jethmal
00845 |  | MRB1-EG02-W01d | AQ0401 NCR MRB1-EG02-W01d HC_DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-11-23 | Abdiel Santos | 2014-05-27 10:38 | 15100- Expansion Locks Atlantic | Abdiel Santos
00241 |  |  | G-Concrete Placing Temp Ctrl Monit | Noncompliance Notice | Closed | No Ball in Court | Administrative | 2012-12-04 | John Lopacki | 2013-09-02 14:46 | 15000- Expansion Locks | Lorena Jethmal
00844 |  | NCR LH2 RG3 URail | P50M0003 NCR LH2 RG3 URail Bolts US | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-11-23 | Juan Rivera | 2015-10-19 09:54 | 15200- Expansion Locks Pacific | Martin Duran
00243 |  |  | A00/UPCCAR5027 Ice Plant | Noncompliance Notice | Void | Peterjan Versteele |  | 2012-12-12 | Marta Small | 2015-09-02 13:38 | 15100- Expansion Locks Atlantic | Jianey Abrahams
00843 |  | NCR LH2 RG2 URail | P50M0002 NCR LH2 RG2 URail Bolts DS | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2013-11-23 | Juan Rivera | 2015-10-19 09:51 | 15200- Expansion Locks Pacific | Martin Duran
00244 |  |  | P-Inadeq Waste Mgmt at Waste Center | Noncompliance Notice | Closed | Gustavo Rivas Sr. | Environmental Situation | 2012-12-21 | Alicia Villalobos | 2013-03-19 13:56 | 15200- Expansion Locks Pacific | Lorena Jethmal
00245 |  |  | P-Failure to Comply QMT Super Dispo | Noncompliance Notice | Closed | Luis Isaza | Quality Mgt Sys | 2013-01-14 | Marta Small | 2016-05-04 14:25 | 15200- Expansion Locks Pacific | Lorena Jethmal
00846 |  | DW-U04d-W02 North | AQ0402 NCR DW-U04d-W02 North WS_DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-11-25 | Zosimo Correa | 2015-03-24 16:50 | 15100- Expansion Locks Atlantic | Abdiel Santos
00847 |  | NCR CIM MAT | A50M0004 NCR CIM MAT Reception DEF | Nonconformance Report | Closed | No Ball in Court | Defective Materials | 2013-11-29 | Abdiel Santos | 2014-09-26 10:09 | 15100- Expansion Locks Atlantic | Karla Jones
00246 |  |  | A – Failure to perform Internal Ins | Noncompliance Notice | Closed | Jose Pelaez | Quality Mgt Sys | 2013-01-22 | Karla Jones | 2013-05-16 11:32 | 15100- Expansion Locks Atlantic | Tamira Baird
00247 |  |  | G-Failure to provide Design and SDR | Noncompliance Notice | Closed | No Ball in Court | Contract Term | 2013-02-04 | John Lopacki | 2013-09-26 08:52 | 15000- Expansion Locks | Lorena Jethmal
00849 |  | NCR No Certified | A50M0006 NCR No Certified Welder DF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-11-30 | Zosimo Correa | 2015-03-02 14:02 | 15100- Expansion Locks Atlantic | Karla Jones
00848 |  | NCR TEMP WELD | A50M0005 NCR TEMP WELD HRZ Embeds | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-11-30 | Zosimo Correa | 2015-02-27 10:11 | 15100- Expansion Locks Atlantic | Karla Jones
00248 |  |  | P-Wastewater Treatment Plant 2a | Noncompliance Notice | Closed | Antonio Pelusi | Environmental Situation | 2013-04-18 | Alicia Villalobos | 2013-09-24 10:29 | 15200- Expansion Locks Pacific | Lorena Jethmal
00853 |  | MRB3 Concrete | AQ0404 NCR - MRB3 Concrete Out DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-12-03 | Abdiel Santos | 2014-04-15 13:58 | 15100- Expansion Locks Atlantic | Abdiel Santos
00002 |  |  | VOID - GENERATED IN ERROR | Noncompliance Notice | Void | NO BIC-GUPC |  | 2013-04-24 | Nayubel Cordoba | 2013-09-12 11:27 |  | Veronica Cash
00852 |  | LE-M13-SC | NCRP0417CS LE-M13-SC+MC Cracks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-12-03 | Luz Arosemena | 2015-05-18 16:44 | 15200- Expansion Locks Pacific | Luz Arosemena
00001 |  |  | GQ0104 CAR Back Up Procedures | Noncompliance Notice | Closed | Martin Ellis | Quality Mgt Sys | 2013-04-24 | Gene Williams | 2015-09-04 14:22 | 15004- Expansion Locks Design | Veronica Cash
00249 |  |  | P-Disp N4 Drain Pipe Installation | Noncompliance Notice | Closed | Rick Montanari | Field Conditions | 2013-04-26 | Marta Small | 2013-05-31 10:13 | 15200- Expansion Locks Pacific | Lorena Jethmal
00851 |  | LW-M06 | NCRP0414CS LW-M06-C04b Alignment | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-12-03 | Javier Gutierrez | 2014-01-03 16:16 | 15200- Expansion Locks Pacific | Luz Arosemena
00850 |  | UE-M03-C04a | AQ0403 NCR UE-M03-C04a Consol. DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-12-03 | Abdiel Santos | 2014-06-16 15:23 | 15100- Expansion Locks Atlantic | Abdiel Santos
00250 |  |  | A-Effective QMS and Inspection | Noncompliance Notice | Closed | Jose Pelaez | Quality Mgt Sys | 2013-05-27 | Tamira Baird | 2013-08-09 10:32 | 15100- Expansion Locks Atlantic | Gene Williams
00253 |  |  | P-Borinquen Dam 2E Lack Dewatering | Noncompliance Notice | Closed | Gustavo Rivas Sr. | Field Conditions | 2013-06-06 | Lorena Jethmal | 2013-07-23 10:21 | 15200- Expansion Locks Pacific | Marta Small
00854 |  | LH2 Upp Rail G4 | AQ0405 NCR LH2 Upp Rail G4-3B North | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-12-10 | Zosimo Correa | 2014-11-24 10:31 | 15100- Expansion Locks Atlantic | Abdiel Santos
00008 |  | NCR CIM Fab Gate | G50M0006 NCR CIM Fab Gate Type B | Nonconformance Report | Closed | NO BIC-GUPC | Administrative | 2013-12-10 | Alberto Alonzo | 2014-05-21 08:55 | 15000- Expansion Locks | Alberto Alonzo
00252 |  |  | P-Borinquen Dam 2W Lack Dewatering | Noncompliance Notice | Closed | Gustavo Rivas Sr. | Field Conditions | 2013-06-06 | Lorena Jethmal | 2013-07-23 10:17 | 15200- Expansion Locks Pacific | Marta Small
00251 |  |  | P-Borinquen Dam 1W Lack Dewatering | Noncompliance Notice | Closed | Gustavo Rivas Sr. | Field Conditions | 2013-06-06 | Lorena Jethmal | 2013-07-23 10:11 | 15200- Expansion Locks Pacific | Marta Small
00856 |  | IE-M05-C02 | AQ0408 NCR IE-M05-C02 Concrete DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-12-16 | Abdiel Santos | 2014-07-15 08:07 | 15100- Expansion Locks Atlantic | Abdiel Santos
8005 |  |  | PQ0092 CAR Concealed Defective Work | Noncompliance Notice | Void | Rafael Sarmiento |  | 2013-06-10 | Javier Gutierrez | 2013-06-10 08:09 | 15200- Expansion Locks Pacific | Javier Gutierrez
00855 |  | T2-C3-04-03-F01 | AQ0406 NCR T2-C3-04-03-F01 Class IX | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-12-16 | Abdiel Santos | 2014-08-25 16:49 | 15100- Expansion Locks Atlantic | Abdiel Santos
00254 |  |  | Lack Temp Erosion Control Disp N3 | Noncompliance Notice | Closed | Marta Small | Environmental Situation | 2013-06-14 | Alicia Villalobos | 2016-05-24 14:31 | 15200- Expansion Locks Pacific | Lorena Jethmal
00857 |  | MRB1-EG01-W01b | AQ0409 NCR MRB1-EG01-W01b Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-12-17 | Abdiel Santos | 2014-03-24 15:45 | 15100- Expansion Locks Atlantic | Abdiel Santos
00860 |  | Sorguz | AE8042 NcR Sorguz Parking Area | Nonconformance Report | Closed | No Ball in Court | Other | 2013-12-18 | Abdiel Santos | 2014-04-15 14:15 | 15100- Expansion Locks Atlantic | Yira Mootoo
00255 |  |  | Start Work WSB 1 and 2 Prior to RFC | Noncompliance Notice | Closed | Antonio Pelusi | Contract Term | 2013-06-17 | Marco Villarreal | 2013-09-13 08:37 | 15200- Expansion Locks Pacific | Lorena Jethmal
00256 |  |  | P-Grout Curtain Water Source Clear | Noncompliance Notice | Closed | Gustavo Rivas Sr. | Quality Mgt Sys | 2013-07-10 | Marco Villarreal | 2014-07-03 07:49 | 15200- Expansion Locks Pacific | Lorena Jethmal
00859 |  | Concrete Wash | AE08041 NCR Concrete Wash out Pit | Nonconformance Report | Closed | No Ball in Court |  | 2013-12-18 | Abdiel Santos | 2014-03-17 16:46 | 15100- Expansion Locks Atlantic | Yira Mootoo
00858 |  | OE-M02-P2-02 | NCRP0423CS OE-M02-P2-02+01 Honeycom | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2013-12-20 | Luz Arosemena | 2016-08-31 14:54 | 15200- Expansion Locks Pacific | Javier Gutierrez
00257 |  |  | P-Failure to Follow QMS Process H3E | Noncompliance Notice | Closed | Gustavo Rivas Sr. | Quality Mgt Sys | 2013-07-23 | Javier Gutierrez | 2013-10-01 14:57 | 15200- Expansion Locks Pacific | Lorena Jethmal
00862 |  | MB Slab A3, D3 | NCRP0424CS MB Slab A3, D3, A7, D7 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2014-01-07 | Lorely Rivera | 2016-06-17 18:25 | 15200- Expansion Locks Pacific | Luz Arosemena
00259 |  |  | P–Lack Root Cause Analysis NCRP0362 | Noncompliance Notice | Closed | Marta Small | Quality Mgt Sys | 2013-07-29 | Javier Gutierrez | 2014-03-31 14:37 | 15200- Expansion Locks Pacific | Marta Small
00258 |  |  | P-Failure to Comply with MGP0015 | Noncompliance Notice | Closed | Gustavo Rivas Sr. | Quality Mgt Sys | 2013-07-29 | Marco Villarreal | 2013-10-11 11:12 | 15200- Expansion Locks Pacific | Lorena Jethmal
00861 |  | Backfill LUC | AQ0407 NCR Backfill LUC Geocomp DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-01-07 | Zosimo Correa | 2015-06-03 11:25 | 15100- Expansion Locks Atlantic | Abdiel Santos
00260 |  |  | P– Failure Follow Manufacturer Inst | Noncompliance Notice | Open | Luis Isaza | Safety & Health Issue | 2013-08-09 | Lorely Rivera | 2016-09-01 10:34 | 15200- Expansion Locks Pacific | Marta Small
00863 |  | ME-M13 | NCRP0421CS ME-M13-F02 Cracks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-01-10 | Luz Arosemena | 2015-05-11 11:29 | 15200- Expansion Locks Pacific | Luz Arosemena
00864 |  | MB Anchor | NCRP0427CS MB Anchor Bolts Misalign | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-01-14 | Luz Arosemena | 2014-04-15 14:25 | 15200- Expansion Locks Pacific | Luz Arosemena
00261 |  |  | A-Sub Standard Procedure | Noncompliance Notice | Closed | Jose E. Reyes | Unsafe conditions | 2013-08-12 | Tamira Baird | 2014-11-24 14:44 | 15100- Expansion Locks Atlantic | Tamira Baird
00262 |  |  | P–Inadequate Disposal Solid Waste V | Noncompliance Notice | Closed | Antonio Pelusi | Environmental Situation | 2013-08-16 | Marco Villarreal | 2014-04-01 16:01 | 15200- Expansion Locks Pacific | Lorena Jethmal
00865 |  | Low Strenght | NCRP0413CS Low Strenght Concrete R. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-01-16 | Luz Arosemena | 2014-02-05 09:20 | 15200- Expansion Locks Pacific | Luz Arosemena
8006 |  |  | VOID | Noncompliance Notice | Void | No Ball in Court |  | 2013-08-19 | Nayubel Cordoba | 2013-08-19 10:14 | 00000- Other | Martin Duran
00869 |  | Backfill | AQ0411 NCR Backfill LMC MaterialDEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-01-17 | Abdiel Santos | 2014-08-04 16:32 | 15100- Expansion Locks Atlantic | Abdiel Santos
00868 |  | Backfill LUC | AQ0400 NCR - Backfill LUC Geoc. DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-01-17 | Zosimo Correa | 2015-06-03 10:54 | 15100- Expansion Locks Atlantic | Abdiel Santos
00263 |  |  | P-Maintenance Building Start Work O | Noncompliance Notice | Closed | Marco A. Villarreal | Quality Mgt Sys | 2013-08-22 | Marco Villarreal | 2014-04-01 15:35 | 15200- Expansion Locks Pacific | Lorena Jethmal
00264 |  |  | P-SS Spare Parts Storage Building | Noncompliance Notice | Closed | Marco A. Villarreal | Quality Mgt Sys | 2013-08-30 | Marco Villarreal | 2014-04-01 15:44 | 15200- Expansion Locks Pacific | Marco Villarreal
00866 |  | NCR LH1 RG2 LTW PL 3 | P50M0005 NCR LH1 RG2 LTW PL 3 & 4 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2014-01-17 | Juan Rivera | 2015-10-19 10:08 | 15200- Expansion Locks Pacific | Martin Duran
00001 |  | NCR Supports | P66M0001 NCR Supports for DIP | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-01-17 | Luz Arosemena | 2015-03-03 11:41 | 15200- Expansion Locks Pacific | Martin Duran
00265 |  |  | A- Oil Leaks and Soil Contamination | Noncompliance Notice | Closed | Ymelda Smith | Environmental Situation | 2013-09-27 | Tamira Baird | 2015-03-26 11:31 | 15100- Expansion Locks Atlantic | Gene Williams
00266 |  |  | P-pH Level Non Comply Betonwash | Noncompliance Notice | Closed | Rick Montanari | Environmental Situation | 2013-10-07 | Alicia Villalobos | 2015-03-27 15:00 | 15200- Expansion Locks Pacific | Marco Villarreal
00867 |  | NCR LH1 RG1 URail | P50M0006 NCR LH1 RG1 URail Bolts US | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-01-18 | Juan Rivera | 2015-10-19 09:59 | 15200- Expansion Locks Pacific | Martin Duran
00267 |  |  | P–Disposal N4 Const not according | Noncompliance Notice | Closed | Tomas Edghill | Construction Deficiency | 2013-10-17 | Marta Small | 2015-08-25 09:33 | 15200- Expansion Locks Pacific | Marco Villarreal
00018 |  | NCR Sill's | A55M0018 NCR Sill's Conduit Valve | Nonconformance Report | Closed | No Ball in Court | Defective Materials | 2014-01-18 | Zosimo Correa | 2014-10-20 15:53 | 15100- Expansion Locks Atlantic | Martin Duran
00017 |  | NCR Conduit | P55M0041 NCR Conduit Valve W01 | Nonconformance Report | Closed | NO BIC-GUPC | Defective Materials | 2014-01-18 | Luz Arosemena | 2015-06-08 09:13 | 15200- Expansion Locks Pacific | Martin Duran
00268 |  |  | TEST - TEST - TEST | Noncompliance Notice | Void | No Ball in Court |  | 2013-10-18 | Tamira Baird | 2013-10-24 11:17 | 15100- Expansion Locks Atlantic | Gene Williams
00269 |  |  | A–Use of Safety Glasses | Noncompliance Notice | Closed | Jose E. Reyes | Safety & Health Issue | 2013-11-28 | Tamira Baird | 2013-12-30 14:01 | 15100- Expansion Locks Atlantic | Tamira Baird
00001 |  | NCR | P75M0001 NCR Crane's Damages | Nonconformance Report | Closed | NO BIC-GUPC | Defective Materials | 2014-01-18 | Luz Arosemena | 2015-11-02 09:48 | 15200- Expansion Locks Pacific | Martin Duran
00870 |  | TRF4-SL1 to 4 | NCRP0419CS TRF4-SL1 to 4 Lack Cover | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-01-21 | Luz Arosemena | 2015-01-06 09:47 | 15200- Expansion Locks Pacific | Luz Arosemena
00270 |  |  | A – Accident Reporting | Noncompliance Notice | Closed | Jose E. Reyes | Safety & Health Issue | 2013-12-03 | Tamira Baird | 2014-01-07 15:44 | 15100- Expansion Locks Atlantic | Gene Williams
00871 |  | MRB1-EG | NCRP0426CS MRB1-EG- Drain Pipe | Nonconformance Report | Approved | Juan Arturo Rivera | Construction Deficiency | 2014-01-22 | Lorely Rivera | 2015-08-24 10:10 | 15200- Expansion Locks Pacific | Luz Arosemena
8007 |  |  | AQ0407 NCR Backfill LUC Geocomp DEF | Noncompliance Notice | Void | Jose Pelaez | Construction Deficiency | 2013-12-16 | Abdiel Santos | 2014-01-07 08:24 | 15100- Expansion Locks Atlantic | Abdiel Santos
00874 |  | Low | NCRP0430CS Low Strenght Results | Nonconformance Report | Closed | Juan Arturo Rivera | Construction Deficiency | 2014-01-28 | Jonathan Gonzalez | 2015-06-17 15:18 | 15200- Expansion Locks Pacific | Luz Arosemena
00271 |  |  | P–Failure Implement Rain Event Plan | Noncompliance Notice | Closed | Marta Small | Quality Mgt Sys | 2013-12-19 | Javier Gutierrez | 2014-03-31 14:39 | 15200- Expansion Locks Pacific | Marco Villarreal
00873 |  | Low | NCRP0429CS Low Strenght Results | Nonconformance Report | Closed | Juan Arturo Rivera | Construction Deficiency | 2014-01-28 | Jonathan Gonzalez | 2015-06-17 15:13 | 15200- Expansion Locks Pacific | Luz Arosemena
00272 |  |  | P–Lack Enforcement Use Safety Glass | Noncompliance Notice | Closed | Antonio Pelusi | Safety & Health Issue | 2013-12-30 | Marco Villarreal | 2014-10-01 08:47 | 15200- Expansion Locks Pacific | Marco Villarreal
00273 |  |  | Test GArias NCN | Noncompliance Notice | Void | Bernardo Gonzalez |  | 2014-01-04 | Gladys Arias | 2014-01-31 13:16 |  | Gladys Arias
00872 |  | IE-M03 | NCRP0425CS IE-M03-C01 Formwork | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-01-28 | Luz Arosemena | 2014-08-09 11:34 | 15200- Expansion Locks Pacific | Luz Arosemena
00274 |  |  | A – Lack of Effective Fall Protecti | Noncompliance Notice | Closed | Greg Ohrn | Safety & Health Issue | 2014-01-31 | Tamira Baird | 2014-08-05 14:04 | 15100- Expansion Locks Atlantic | Tamira Baird
00875 |  | T2-C3-W02 Trash | AQ0410 NCR T2-C3-W02 Trash Rack Def | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-02-03 | Zosimo Correa | 2014-10-14 09:36 | 15100- Expansion Locks Atlantic | Abdiel Santos
00877 |  | H2E | NCRP0434CS H2E PVC Pipe | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-02-05 | Luz Arosemena | 2015-01-02 15:19 | 15200- Expansion Locks Pacific | Luz Arosemena
00275 |  |  | A–Failure-Measures to ctrl vector | Noncompliance Notice | Closed | Greg Ohrn | Safety & Health Issue | 2014-04-21 | Tamira Baird | 2014-06-26 14:45 | 15100- Expansion Locks Atlantic | Tamira Baird
00876 |  | Bld Anchor | NCRP0422CS Bld Anchor Bolts Maint | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2014-02-05 | Lorely Rivera | 2016-07-27 08:33 | 15200- Expansion Locks Pacific | Luz Arosemena
00276 |  |  | A–Affectation Stilson's Pond | Noncompliance Notice | Closed | Jose Pelaez | Environmental Situation | 2014-05-14 | Tamira Baird | 2014-11-20 11:01 | 15100- Expansion Locks Atlantic | Tamira Baird
00880 |  | MRB2 | NCRP0436CS MRB2-MG Waterproofing | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-02-07 | Luz Arosemena | 2014-09-22 16:26 | 15200- Expansion Locks Pacific | Luz Arosemena
00277 |  |  | P-Permeability Design 3A BOR Dam | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2014-05-28 | Marco Villarreal | 2014-10-28 13:43 | 15200- Expansion Locks Pacific | Marta Small
00879 |  | MRB1 | NCRP0435CS MRB1-MG Waterproofing | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-02-07 | Luz Arosemena | 2014-09-22 15:40 | 15200- Expansion Locks Pacific | Luz Arosemena
00278 |  |  | P-Outlet Structure Start Work Out | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2014-06-02 | Marco Villarreal | 2014-10-30 11:06 | 15200- Expansion Locks Pacific | Marta Small
00279 |  |  | A–Station Oil Recovery System Drain | Noncompliance Notice | Open | Ramon Porcell | Construction Deficiency | 2014-06-23 | Karla Jones | 2017-01-25 10:52 | 15100- Expansion Locks Atlantic | Tamira Baird
00878 |  | Low Strength | NCRP0433CS Low Strength Class IX | Nonconformance Report | Closed | Rick Montanari | Construction Deficiency | 2014-02-07 | Ramon Cascante | 2016-07-08 15:14 | 15200- Expansion Locks Pacific | Luz Arosemena
00881 |  | Thermocoup | NCRP0418CS Thermocouples - Cracks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-02-11 | Luz Arosemena | 2015-05-04 15:12 | 15200- Expansion Locks Pacific | Luz Arosemena
00280 |  |  | P–Lack QMS Uncontrolled Substitutio | Noncompliance Notice | Closed | Luis Isaza |  | 2014-06-24 | Marta Small | 2016-05-04 14:17 | 15200- Expansion Locks Pacific | Marco Villarreal
00282 |  |  | A – Deficient Mechanical Equipment | Noncompliance Notice | Closed | Jose Pelaez | Quality Mgt Sys | 2014-06-26 | Zosimo Correa | 2014-10-13 08:38 | 15100- Expansion Locks Atlantic | Tamira Baird
00884 |  | Thermocoup | NCRP0439CS Thermocouples | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-02-12 | Luz Arosemena | 2014-09-22 15:49 | 15200- Expansion Locks Pacific | Luz Arosemena
00281 |  |  | A – Deficient Fire Fighting System | Noncompliance Notice | Closed | Greg Ohrn | Quality Mgt Sys | 2014-06-26 | Tamira Baird | 2014-08-11 12:01 | 15100- Expansion Locks Atlantic | Tamira Baird
00883 |  | Thermocoup | NCRP0438CS Thermocouples - Cracks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-02-12 | Luz Arosemena | 2015-05-18 16:42 | 15200- Expansion Locks Pacific | Luz Arosemena
00882 |  | Thermocoup | NCRP0437CS Thermocouples | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-02-12 | Luz Arosemena | 2014-09-22 15:32 | 15200- Expansion Locks Pacific | Luz Arosemena
8008 |  |  |  | Noncompliance Notice | Void | No Ball in Court | Construction Deficiency | 2014-07-12 | Zosimo Correa | 2014-07-21 10:09 | 15100- Expansion Locks Atlantic | Abdiel Santos
00885 |  | IMC A14 - Low | AQ0412 NCR IMC A14 - Low Breaks Re | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-02-15 | Mayra Santos | 2016-05-13 10:52 | 15100- Expansion Locks Atlantic | Abdiel Santos
00284 |  |  | P–NCRP0425CS Repair Work Proceeded | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2014-07-21 | Marco Villarreal | 2014-10-29 09:41 | 15200- Expansion Locks Pacific | Marco Villarreal
00887 |  | UE-M09 | AQ0414 NCR UE-M09 SC - Cracks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-03-08 | Zosimo Correa | 2015-06-03 14:51 | 15100- Expansion Locks Atlantic | Abdiel Santos
00285 |  |  | A–Masonry Walls in MRB2 and MRB3 | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2014-08-01 | Mercedes Peters | 2017-01-23 13:43 | 15100- Expansion Locks Atlantic | Tamira Baird
00286 |  |  | A – Use of Non-UL List Conduit | Noncompliance Notice | Closed | Jose Pelaez | Quality Mgt Sys | 2014-08-05 | Tamira Baird | 2015-03-04 09:09 | 15100- Expansion Locks Atlantic | Tamira Baird
00886 |  | H3E-6B East | AQ0413 NCR H3E-6B East West Cracks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-03-08 | Abdiel Santos | 2014-06-24 07:56 | 15100- Expansion Locks Atlantic | Abdiel Santos
00287 |  |  | P-Protection Care of Works Potable | Noncompliance Notice | Closed | Antonio Pelusi | Quality Mgt Sys | 2014-08-08 | Marco Villarreal | 2014-12-24 07:37 | 15200- Expansion Locks Pacific | Marco Villarreal
00888 |  | T5-C3-11-F01a | AQ0415 NCR T5-C3-11-F01a Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-03-13 | Abdiel Santos | 2014-03-25 09:02 | 15100- Expansion Locks Atlantic | Abdiel Santos
00889 |  | CC2-A | NCRP0442CS CC2-A-05 Crack | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-03-15 | Luz Arosemena | 2014-08-05 16:45 | 15200- Expansion Locks Pacific | Luz Arosemena
00288 |  |  | P-Test FAIL Filter Dam 2E 3A Fines | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2014-08-21 | Marco Villarreal | 2014-10-29 07:51 | 15200- Expansion Locks Pacific | Marco Villarreal
00289 |  |  | P–Test FAIL Filter Dam 1W 3A Fines | Noncompliance Notice | Closed | Juan Arturo Rivera | Quality Mgt Sys | 2014-08-27 | Marco Villarreal | 2014-10-13 14:15 | 15200- Expansion Locks Pacific | Marco Villarreal
00890 |  | ME-M10-W05 | NCRP0443CS ME-M10-W05 Low Strength | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-03-19 | Luz Arosemena | 2014-09-23 15:48 | 15200- Expansion Locks Pacific | Luz Arosemena
00891 |  | UE-M13 | NCRP0444CS UE-M13-F02 Cracks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-03-21 | Luz Arosemena | 2015-03-03 11:30 | 15200- Expansion Locks Pacific | Luz Arosemena
00291 |  |  | P–Grouting Chamber Floor Start Work | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2014-09-02 | Marco Villarreal | 2014-10-29 08:18 | 15200- Expansion Locks Pacific | Marco Villarreal
00892 |  | Low Streng | NCRP0445CS Low Strength | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-03-25 | Luz Arosemena | 2014-09-23 15:55 | 15200- Expansion Locks Pacific | Luz Arosemena
00290 |  |  | P–INLET Approach Structure Start Wo | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2014-09-02 | Marco Villarreal | 2014-10-29 08:57 | 15200- Expansion Locks Pacific | Marco Villarreal
00893 |  | CB-C13 | AQ0417 NCR - CB-C13 (II) Honeycomb | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-03-26 | Abdiel Santos | 2014-04-21 16:30 | 15100- Expansion Locks Atlantic | Abdiel Santos
00292 |  |  | A-Insulated Metal Paneling for Bldg | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2014-09-29 | Abdiel Santos | 2014-10-31 15:05 | 15100- Expansion Locks Atlantic | Gene Williams
00293 |  |  | A–QA System Failure in Gate Manufac | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2014-12-02 | Mercedes Peters | 2017-01-23 13:49 | 15100- Expansion Locks Atlantic | Tamira Baird
00894 |  | MRB1-EG-03-W01b | NCRP0448CS MRB1-EG-03-W01b H.C. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-03-27 | Luz Arosemena | 2014-08-20 11:25 | 15200- Expansion Locks Pacific | Luz Arosemena
00895 |  | TRF3-SL02&01 L | AQ0418 NCR TRF3-SL02&01 L.Void DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-03-29 | Abdiel Santos | 2014-07-15 08:14 | 15100- Expansion Locks Atlantic | Abdiel Santos
00294 |  |  | P-Lack RFC Drawings For Use Conditi | Noncompliance Notice | Closed | Luis Isaza | Quality Mgt Sys | 2014-12-04 | Marta Small | 2016-11-16 10:34 | 15200- Expansion Locks Pacific | Marco Villarreal
00295 |  |  | A-Deficiencies in Confined Spaces | Noncompliance Notice | Closed | Jose Pelaez | Unsafe conditions | 2014-12-15 | Tamira Baird | 2015-02-23 15:41 | 15100- Expansion Locks Atlantic | Tamira Baird
00896 |  | Con. DEF Pipes | AQ0416 NCR Con. DEF Pipes not Inst. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-04-01 | Abdiel Santos | 2016-12-05 14:36 | 15100- Expansion Locks Atlantic | Abdiel Santos
00296 |  |  | P-WSB Sub Drainage System Lack 3 | Noncompliance Notice | Closed | Luis Isaza | Quality Mgt Sys | 2014-12-18 | Marta Small | 2016-02-17 09:54 | 15200- Expansion Locks Pacific | Marco Villarreal
00897 |  | MRB3 Beam & | AQ0419 NCR MRB3 Beam & Column Def. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-04-02 | Zosimo Correa | 2014-11-13 10:14 | 15100- Expansion Locks Atlantic | Abdiel Santos
00297 |  |  | A–QMS for Water Saving Basin Subd | Noncompliance Notice | Closed | Ramon Porcell | Quality Mgt Sys | 2014-12-23 | Richard Barrow | 2016-02-16 15:12 | 15100- Expansion Locks Atlantic | Tamira Baird
00898 |  | UW-M02-C04 | NCRP0449CS UW-M02-C04/C03 Honeycomb | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-04-04 | Luz Arosemena | 2015-01-08 14:54 | 15200- Expansion Locks Pacific | Luz Arosemena
00899 |  | Low Strength | NCRP0428CS Low Strength May-June | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2014-04-07 | Lorely Rivera | 2015-07-04 09:39 | 15200- Expansion Locks Pacific | Luz Arosemena
00298 |  |  | A Lack of QMS for Building Finishes | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2014-12-24 | Mercedes Peters | 2017-01-23 13:53 | 15100- Expansion Locks Atlantic | Tamira Baird
00020 |  | NCR HSH | P55M0042 NCR HSH CYL SUPPORT | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-04-08 | Luz Arosemena | 2015-05-29 14:21 | 15200- Expansion Locks Pacific | Alberto Alonzo
00299 |  |  | A–Lack of QMS documentation/Gates | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2015-01-06 | Mercedes Peters | 2017-01-23 13:56 | 15100- Expansion Locks Atlantic | Tamira Baird
00019 |  | NCR Cylinder | A55M0019 NCR Cylinder support mat | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-04-08 | Abdiel Santos | 2014-08-25 15:17 | 15100- Expansion Locks Atlantic | Alberto Alonzo
00300 |  |  | A–Damaged Equipment for Drive Mech | Noncompliance Notice | Open | Ramon Porcell | Quality Mgt Sys | 2015-01-08 | Maylin Moreno | 2016-02-17 13:05 | 15100- Expansion Locks Atlantic | Tamira Baird
00903 |  | NCR Seismic Hook | A50M0007 NCR Seismic Hook Inst. DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-04-21 | Zosimo Correa | 2015-02-19 10:40 | 15100- Expansion Locks Atlantic | Abdiel Santos
00301 |  |  | A-QMS Failure-Repairs to Upper Rail | Noncompliance Notice | Closed | Greg Ohrn | Quality Mgt Sys | 2015-01-13 | Tamira Baird | 2015-07-10 07:48 | 15100- Expansion Locks Atlantic | Gene Williams
00902 |  | MRB1-EG | NCRP0453CS MRB1-EG-01 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-04-21 | Luz Arosemena | 2014-08-20 11:22 | 15200- Expansion Locks Pacific | Luz Arosemena
00302 |  |  | P-Lack QC Inspect WSB Fill | Noncompliance Notice | Closed | Luis Isaza | Quality Mgt Sys | 2015-01-14 | Rick Montanari | 2016-05-11 09:17 | 15200- Expansion Locks Pacific | Marco Villarreal
00901 |  | MRB1 | NCRP0452CS MRB1 Honeycombs | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-04-21 | Luz Arosemena | 2014-10-16 09:10 | 15200- Expansion Locks Pacific | Luz Arosemena
00305 |  |  | P-Start Work Duct HVAC Installation | Noncompliance Notice | Closed | Luis Isaza | Quality Mgt Sys | 2015-01-20 | Marta Small | 2016-05-04 14:05 | 15200- Expansion Locks Pacific | Marco Villarreal
00190 |  |  | GQ0087 CAR Lack Evid of Desgr Invol | Corrective Action Request | Closed | No Ball in Court | Administrative | 2012-06-21 | Veronica Cash | 2013-04-08 15:38 | 24006- Cofferdam | Maria Ho
00304 |  |  | P-Start Work Micro Pile Rock Anchor | Noncompliance Notice | Closed | Luis Isaza | Quality Mgt Sys | 2015-01-20 | Marta Small | 2015-04-06 13:31 | 15200- Expansion Locks Pacific | Marco Villarreal
00189 |  |  | PECAR8023 Oil spill at Borinqn Road | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2011-05-16 | Marta Small | 2015-09-02 13:43 | 15200- Expansion Locks Pacific | Josimar Torrero
00900 |  | Low Strenght UW | NCRP0446CS Low Strenght UW-M07-W07 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-04-21 | Luz Arosemena | 2014-11-26 11:01 | 15200- Expansion Locks Pacific | Luz Arosemena
00188 |  |  | AE8034 CAR Handling of 55gal hazmat | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2012-06-18 | Marta Small | 2015-09-02 13:44 | 15100- Expansion Locks Atlantic | Abed Camarena
00303 |  |  | A–QMS for WSB Geomembrane Liner | Noncompliance Notice | Closed | Ricaurte Salamin | Quality Mgt Sys | 2015-01-20 | Zosimo Correa | 2015-03-23 14:20 | 15100- Expansion Locks Atlantic | Tamira Baird
00905 |  | MRB2 columns & | AQ0424 NCR MRB2 columns & studs Def | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-04-25 | Zosimo Correa | 2014-11-13 10:32 | 15100- Expansion Locks Atlantic | Abdiel Santos
00904 |  | MRB3 | AQ0421 NCR MRB3 Anchor bolts | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-04-25 | Armando Quintero | 2016-05-25 11:32 | 15100- Expansion Locks Atlantic | Abdiel Santos
00187 |  |  | A00/UPCCAR5024 DSB | Corrective Action Request | Closed | Rafael Sarmiento | Safety & Health Issue | 2012-06-12 | Marta Small | 2015-09-02 13:45 | 15100- Expansion Locks Atlantic | Jianey Abrahams
00308 |  |  | P-Start Work Cut Off Wall Grout | Noncompliance Notice | Closed | Luis Isaza | Quality Mgt Sys | 2015-01-21 | Marta Small | 2015-04-08 15:13 | 15200- Expansion Locks Pacific | Marco Villarreal
00002 |  | NCR 80T Crane | P75M0002 NCR 80T Crane parts damage | Nonconformance Report | Closed | No Ball in Court | Defective Materials | 2014-05-02 | Lorely Rivera | 2015-08-31 16:44 | 15200- Expansion Locks Pacific | Karlos Azuz
00307 |  |  | P-Gatun Cofferdam Start Work Lack | Noncompliance Notice | Closed | Abdiel Angulo | Quality Mgt Sys | 2015-01-21 | Marta Small | 2015-08-25 09:30 | 15200- Expansion Locks Pacific | Marco Villarreal
00186 |  |  | PE8027CAR DailyCheck storage areas | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2011-07-23 | Marta Small | 2015-09-02 13:47 | 15200- Expansion Locks Pacific | Josimar Torrero
00306 |  |  | P-Thermal Insulation for Control | Noncompliance Notice | Closed | Marta Small | Quality Mgt Sys | 2015-01-21 | Marta Small | 2015-07-31 09:53 | 15200- Expansion Locks Pacific | Marco Villarreal
00009 |  | NCR CIM Position | G50M0010 NCR CIM Position of Anodes | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2014-05-08 | Alberto Alonzo | 2014-06-03 13:51 | 15000- Expansion Locks | Alberto Alonzo
00185 |  |  | PQ0077 CAR Audit Batch Plant Obv#2 | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-06-13 | Veronica Cash | 2013-04-08 15:41 | 15200- Expansion Locks Pacific | Luz Arosemena
00184 |  |  | PQ0076 CAR Audit Batch Plant Obv #1 | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-06-13 | Veronica Cash | 2013-04-08 15:42 | 15200- Expansion Locks Pacific | Luz Arosemena
00309 |  |  | A-Installation of Gates | Noncompliance Notice | Open | Jose Pelaez | Quality Mgt Sys | 2015-01-28 | Zosimo Correa | 2015-03-02 11:28 | 15100- Expansion Locks Atlantic | Tamira Baird
00006 |  | NCR CIM | G50M0009 NCR CIM Watertight Door | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2014-05-08 | Alberto Alonzo | 2014-05-21 09:00 | 15000- Expansion Locks | Alberto Alonzo
00010 |  | NCR CIM | G50M0011 NCR CIM Draft Marks | Nonconformance Report | Closed | Erick Briceno | Construction Deficiency | 2014-05-09 | Roberto Barrios | 2016-05-26 16:04 | 15000- Expansion Locks | Alberto Alonzo
00183 |  |  | PQ0075 CAR Audit Batch Plant Obv #1 | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-06-13 | Veronica Cash | 2013-04-08 15:39 | 15200- Expansion Locks Pacific | Luz Arosemena
00310 |  |  | G–Lack of Quality Records and Doc | Noncompliance Notice | Open | Giuseppe Quarta | Quality Mgt Sys | 2015-01-30 | Zosimo Correa | 2015-11-19 12:50 | 15000- Expansion Locks | Tamira Baird
00182 |  |  | AQ0143 CAR Incorrect APPL of SOP010 | Corrective Action Request | Closed | No Ball in Court | Administrative | 2012-06-08 | Karla Jones | 2012-11-14 11:21 | 15100- Expansion Locks Atlantic | Karla Jones
00906 |  | BOR | NCRP0454CS BOR Dams Dewatering | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-05-24 | Luz Arosemena | 2014-07-25 11:36 | 15200- Expansion Locks Pacific | Lorely Rivera
00311 |  |  | P-Lack Support Doc Interim | Noncompliance Notice | Superseded | No Ball in Court | Administrative | 2015-02-04 | Marco Villarreal | 2015-03-11 10:46 | 15200- Expansion Locks Pacific | Marco Villarreal
00002 |  | NCR SEL | G83M0002 NCR SEL PAC Cabinets | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2014-05-26 | Alberto Alonzo | 2014-06-03 15:12 | 15000- Expansion Locks | Alberto Alonzo
00313 |  |  | Failure to Comply with the Engineer | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2015-02-05 | John Lopacki | 2015-10-13 14:58 | 15000- Expansion Locks | Marco Villarreal
00181 |  |  | PE8043 CAR Affect water flow DispN4 | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2011-12-29 | Marta Small | 2015-09-02 13:48 | 15200- Expansion Locks Pacific | Josimar Torrero
00907 |  | NCR Elect PVC | P93M0001 NCR Elect PVC Fittings LH3 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2014-05-28 | Lorely Rivera | 2016-04-28 15:23 | 15200- Expansion Locks Pacific | Juan Rivera
00312 |  |  | A–Failure to Provide Adequate Prote | Noncompliance Notice | Open | Jose Pelaez | Quality Mgt Sys | 2015-02-05 | Zosimo Correa | 2015-03-02 11:25 | 15100- Expansion Locks Atlantic | Tamira Baird
00180 |  |  | GQ0086 CAR Rebar Shop Drawings | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2012-05-31 | Maria Ho | 2012-08-09 11:25 | 15000- Expansion Locks | Maria Ho
00314 |  |  | P-Clay_1a_Criteria_Dam_2E_UQL_Rock | Noncompliance Notice | Closed | Luis Isaza | Quality Mgt Sys | 2015-02-09 | Marta Small | 2015-04-06 13:42 | 15200- Expansion Locks Pacific | Marco Villarreal
00909 |  | SMC Concre | AQ0420 NCR SMC Concre. not approved | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-06-07 | Abdiel Santos | 2016-12-05 14:47 | 15100- Expansion Locks Atlantic | Abdiel Santos
00179 |  |  | PQ0074 CAR Failure Process Disp. 12 | Corrective Action Request | Terminated | Jorge Perez Blanco | Quality Mgt Sys | 2012-05-29 | Lorely Rivera | 2016-08-23 08:37 | 15200- Expansion Locks Pacific | Luz Arosemena
00908 |  | WSB-T2-C1-01 | NCRP0455CS WSB-T2-C1-01-F01 Rebar | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-06-10 | Luz Arosemena | 2014-10-16 09:16 | 15200- Expansion Locks Pacific | Luz Arosemena
00315 |  |  | P-CB Lift MCB-08-CWa Honey Comb Voi | Noncompliance Notice | Closed | Marta Small | Quality Mgt Sys | 2015-03-13 | Marta Small | 2015-07-16 16:02 | 15200- Expansion Locks Pacific | Marco Villarreal
00178 |  |  | PQ0073 CAR WIR'S for repairs | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-05-29 | Luz Arosemena | 2012-08-02 09:50 | 15200- Expansion Locks Pacific | Luz Arosemena
00177 |  |  | PE8029 CAR MedWaste not well disp | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2011-07-23 | Marta Small | 2015-09-02 13:49 | 15200- Expansion Locks Pacific | Josimar Torrero
00003 |  | NCR SEL | G83M0003 NCR SEL Coat Damages | Nonconformance Report | Closed | Erick Briceno | Construction Deficiency | 2014-06-13 | Erick Briceño | 2015-02-26 12:10 | 15000- Expansion Locks | Alberto Alonzo
00316 |  |  | P-Gate Central Deck C D Site REWO | Noncompliance Notice | Closed | Luis Isaza | Quality Mgt Sys | 2015-03-19 | Marta Small | 2016-04-13 10:14 | 15200- Expansion Locks Pacific | Marco Villarreal
00317 |  |  | P–Agua Dulce DS Start Work Lack D | Noncompliance Notice | Closed | Illya D. Gomez | Quality Mgt Sys | 2015-03-27 | Marta Small | 2015-09-01 15:59 | 15200- Expansion Locks Pacific | Marta Small
00917 |  | AS | AQ0427 NCR - AS/Shaft Misalignment | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-06-19 | Abdiel Santos | 2014-10-14 14:17 | 15100- Expansion Locks Atlantic | Abdiel Santos
00176 |  |  | PE8028 CAR Lack of Inventory regist | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2011-07-23 | Marta Small | 2015-09-02 13:55 | 15200- Expansion Locks Pacific | Josimar Torrero
00175 |  |  | PE8025 CAR Maintenance for WWTPs | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2011-07-14 | Marta Small | 2015-09-02 14:38 | 15200- Expansion Locks Pacific | Josimar Torrero
00910 |  | LH2/3 tees | AQ0422 NCR LH2/3 tees not installed | Nonconformance Report | Open | Ramon Porcell | Construction Deficiency | 2014-06-19 | Karla Jones | 2017-01-25 10:24 | 15100- Expansion Locks Atlantic | Abdiel Santos
00318 |  |  | A–Safety in Confined Space – Elec | Noncompliance Notice | Closed | Jose Pelaez | Safety & Health Issue | 2015-04-13 | Tamira Baird | 2016-02-18 07:56 | 15100- Expansion Locks Atlantic | Tamira Baird
00320 |  |  | P-CMU Wall Erection Buildings PAC M | Noncompliance Notice | Closed | Luis Isaza | Quality Mgt Sys | 2015-04-30 | Marta Small | 2016-07-04 10:03 | 15200- Expansion Locks Pacific | Mercedes Peters
00174 |  |  | AM2501 CAR IL Bollards Prep Docs | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2012-05-25 | Juan Rivera | 2014-02-27 22:02 | 15100- Expansion Locks Atlantic | Alberto Alonzo
00911 |  | NCR H4E-6C-W01 | A82M0001 NCR H4E-6C-W01 HDPE pipes | Nonconformance Report | Open | Ramon Porcell | Construction Deficiency | 2014-06-23 | Larry Ohrn | 2015-06-09 07:59 | 15100- Expansion Locks Atlantic | Abdiel Santos
00319 |  |  | G-CB Truss Base Plate Change Design | Noncompliance Notice | Open | Giuseppe Quarta | Quality Mgt Sys | 2015-04-30 | John Lopacki | 2015-05-07 13:54 | 15000- Expansion Locks | Mercedes Peters
00912 |  | IW-M05-W05a | AQ0423 NCR - IW-M05-W05a Rebar DEF. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-06-30 | Abdiel Santos | 2014-10-08 13:55 | 15100- Expansion Locks Atlantic | Abdiel Santos
00173 |  |  | PM2503 CAR IL Bollards Prep Docs | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2012-05-25 | Juan Rivera | 2014-02-27 22:12 | 15200- Expansion Locks Pacific | Alberto Alonzo
00321 |  |  | A – Safety Issues pertaining Suspen | Noncompliance Notice | Closed | Jose Pelaez | Safety & Health Issue | 2015-05-18 | Tamira Baird | 2015-06-16 10:55 | 15100- Expansion Locks Atlantic | Gene Williams
00914 |  | Bent Elect | AQ0430 NCR Bent Elect. Pipes MRB2&3 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-07-03 | Zosimo Correa | 2015-08-04 08:58 | 15100- Expansion Locks Atlantic | Abdiel Santos
00172 |  |  | GQ0085 CAR LOE Indep Rev Hydr Syst | Corrective Action Request | Closed | NO BIC-GUPC | Administrative | 2012-05-19 | Veronica Cash | 2016-08-05 11:03 | 15000- Expansion Locks | Maria Ho
00322 |  |  | A-Post Operation Env and Recovery P | Noncompliance Notice | Closed | Jose Pelaez | Environmental Situation | 2015-06-03 | Alicia Villalobos | 2016-01-11 11:01 | 15100- Expansion Locks Atlantic | Tamira Baird
00171 |  |  | PE8034CAR Roof Cont. Soil Storage | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2011-09-22 | Marta Small | 2015-09-02 14:39 | 15200- Expansion Locks Pacific | Josimar Torrero
00913 |  | UW-M14-F01 | AQ0425 NCR UW-M14-F01 Pouring DEF. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-07-04 | Zosimo Correa | 2014-11-14 12:46 | 15100- Expansion Locks Atlantic | Abdiel Santos
00007 |  |  |  | Nonconformance Report | Void | Rick Montanari |  | 2014-07-07 | Juan Rivera | 2014-07-09 00:55 |  | Lorely Rivera
00170 |  |  | PE8022 CAR Lacking cond temp stor | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2011-05-10 | Marta Small | 2015-09-02 14:40 | 15200- Expansion Locks Pacific | Josimar Torrero
00323 |  |  | P-Deficiencies in Confined Spaces | Noncompliance Notice | Closed | Rafael Sarmiento | Safety & Health Issue | 2015-06-08 | Marta Small | 2016-02-17 08:37 | 15200- Expansion Locks Pacific | Marta Small
00916 |  | CB-P8, P25 | NCRP0458CS CB-P8, P25, P30 Flaws | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-07-08 | Luz Arosemena | 2015-01-05 11:37 | 15200- Expansion Locks Pacific | Lorely Rivera
00169 |  |  | AE8032 CAR Sandblasting waste bags | Corrective Action Request | Closed | Sergi Ametller | Environmental Situation | 2012-05-15 | Marta Small | 2015-09-02 14:42 | 15100- Expansion Locks Atlantic | Abed Camarena
00324 |  |  | P–WSB Material Fill Liner System | Noncompliance Notice | Closed | Luis Isaza | Quality Mgt Sys | 2015-06-17 | Marta Small | 2015-08-25 09:47 | 15200- Expansion Locks Pacific | Marta Small
00168 |  |  | AQ0144 CAR B. P. Operations AFR01 | Corrective Action Request | Closed | No Ball in Court | Administrative | 2012-05-15 | Karla Jones | 2012-10-25 09:31 | 15100- Expansion Locks Atlantic | Karla Jones
00325 |  |  | A–Hoisting Personnel Safety Def | Noncompliance Notice | Closed | Jose Pelaez | Safety & Health Issue | 2015-06-19 | Tamira Baird | 2015-10-21 08:44 | 15100- Expansion Locks Atlantic | Tamira Baird
00915 |  | CB-P03 | NCRP0457CS CB-P03-D085 Flaws | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-07-08 | Luz Arosemena | 2014-08-05 16:55 | 15200- Expansion Locks Pacific | Lorely Rivera
00167 |  |  | AQ0145 CAR B. P. Operations AFR02 | Corrective Action Request | Closed | No Ball in Court | Administrative | 2012-05-15 | Karla Jones | 2012-10-25 09:39 | 15100- Expansion Locks Atlantic | Karla Jones
00005 |  | BDAM 1W | NCRP0460CS BDAM 1W Filter Material | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-07-08 | Luz Arosemena | 2014-08-18 16:34 | 15200- Expansion Locks Pacific | Luz Arosemena
00326 |  |  | A – Diving Operation Safety Deficie | Noncompliance Notice | Closed | Jose Pelaez | Safety & Health Issue | 2015-06-26 | Tamira Baird | 2016-01-15 07:33 | 15100- Expansion Locks Atlantic | Gene Williams
00166 |  |  | PE8057CAR - Lack of Env. Induction. | Corrective Action Request | Closed | Calin Andreescu | Environmental Situation | 2012-09-14 | Marta Small | 2015-09-02 14:44 | 15000- Expansion Locks | Gonzalo Menendez
00166 |  |  | AQ0146 CAR B. P. Operations AFR03 | Corrective Action Request | Closed | No Ball in Court | Administrative | 2012-05-14 | Karla Jones | 2012-06-01 13:23 | 15100- Expansion Locks Atlantic | Karla Jones
00918 |  | IW-M04-C03 Reb | AQ0426 NCR IW-M04-C03 Reb. Ins. DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-07-11 | Abdiel Santos | 2014-08-04 16:38 | 15100- Expansion Locks Atlantic | Abdiel Santos
00327 |  |  | A–Process of Startup and Testing | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2015-07-17 | Mercedes Peters | 2017-01-23 13:58 | 15100- Expansion Locks Atlantic | Tamira Baird
00328 |  |  | P -No Name DS Fill UQL | Noncompliance Notice | Closed | Luis Isaza | Quality Mgt Sys | 2015-07-28 | Marta Small | 2016-07-19 14:00 | 15200- Expansion Locks Pacific | Marta Small
00165 |  |  | AQ0057 CAR Lack of Basic Hygiene | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-07-19 | Maria Ho | 2012-08-29 08:09 | 15100- Expansion Locks Atlantic | Maria Ho
00919 |  | Superfine as | AQ0429 NCR Superfine as fill mater. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-07-14 | Abdiel Santos | 2014-10-15 10:27 | 15100- Expansion Locks Atlantic | Abdiel Santos
00165 |  |  | PE8042 CAR Non-adeq clean of berms | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2011-12-14 | Marta Small | 2015-09-02 14:46 | 15100- Expansion Locks Atlantic | Josimar Torrero
00164 |  |  | AQ0052 CAR Lack of EVD of Equipment | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-07-19 | Marta Small | 2015-09-02 14:47 | 15100- Expansion Locks Atlantic | Maria Ho
00329 |  |  | P –Locks Chamber Structure Grouting | Noncompliance Notice | Closed | Luis Isaza |  | 2015-08-31 | Marta Small | 2015-12-07 10:20 | 15200- Expansion Locks Pacific | Marta Small
00923 |  | IW-M03-F01 K-b | AQ0433 NCR IW-M03-F01 K-b Rebar DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-07-16 | Abdiel Santos | 2014-10-01 16:06 | 15100- Expansion Locks Atlantic | Abdiel Santos
00164 |  |  | PQ0067 CAR ME & MW QMS Process | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-05-11 | Luz Arosemena | 2012-05-11 15:45 | 15200- Expansion Locks Pacific | Luz Arosemena
00163 |  |  | AQ0062 CAR Monte Lirio Erosion CTRL | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-08-24 | Tamira Baird | 2015-09-04 13:30 | 15100- Expansion Locks Atlantic | Karla Jones
00163 |  |  | CAR5042 P-Insuf Illumination Levels | Corrective Action Request | Closed | Vittorio Robiati | Safety & Health Issue | 2012-05-09 | Ariel Soto | 2013-07-23 09:12 | 15200- Expansion Locks Pacific | Fatima Garcia
00330 |  |  | P-44KV System Energized UQL | Noncompliance Notice | Closed | Luis Isaza | Quality Mgt Sys | 2015-09-01 | Marta Small | 2016-07-05 08:00 | 15200- Expansion Locks Pacific | Marta Small
00922 |  | IE-M02-F01 K-P1 | AQ0432 NCR IE-M02-F01 K-P1 Reb. DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-07-16 | Abdiel Santos | 2014-08-04 16:43 | 15100- Expansion Locks Atlantic | Abdiel Santos
00162 |  |  | PE8031 CAR Lack of Env Ind | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2011-09-28 | Tamira Baird | 2015-09-04 13:33 | 15200- Expansion Locks Pacific | Josimar Torrero
00331 |  |  | A – Starting Remedial Works at LH1 | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2015-09-14 | Mercedes Peters | 2017-01-23 14:01 | 15100- Expansion Locks Atlantic | Gene Williams
00924 |  | VS5-C01b Rebar | AQ0434 NCR VS5-C01b Rebar Inst. DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-07-19 | Abdiel Santos | 2016-12-05 14:52 | 15100- Expansion Locks Atlantic | Abdiel Santos
00162 |  |  | AQ0061 CAR Monte L Traffic CTRL DEF | Corrective Action Request | Closed | No Ball in Court | Unforeseen Conditions | 2010-07-19 | Karla Jones | 2012-08-22 12:42 | 15100- Expansion Locks Atlantic | Karla Jones
00925 |  | GBS | AQ0435 NCR GBS Anchors LH2 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-07-21 | Abdiel Santos | 2014-08-04 16:50 | 15100- Expansion Locks Atlantic | Abdiel Santos
00161 |  |  | AQ0059 CAR Loose Material DEF | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-07-19 | Karla Jones | 2012-08-22 10:11 | 00000- Other | Karla Jones
00161 |  |  | VOID | Corrective Action Request | Void | No Ball in Court | Environmental Situation | 2011-09-28 | Maria Ho | 2012-05-05 10:01 |  | Eliza Florendo
00333 |  |  | P-Suspended Platform Safety PAC | Noncompliance Notice | Closed | Rafael Sarmiento | Safety & Health Issue | 2015-09-16 | Marta Small | 2016-02-17 08:24 | 15200- Expansion Locks Pacific | Marisol Fabrega
00921 |  | H4W-6E-W05 | NCRP0459CS H4W-6E-W05 Low Strength | Nonconformance Report | Closed | Rick Montanari | Construction Deficiency | 2014-07-21 | Ramon Cascante | 2015-06-29 16:57 | 15200- Expansion Locks Pacific | Luz Arosemena
00332 |  |  | A-Starting Repair Works at Gate 8 | Noncompliance Notice | Closed | Ramon Porcell | Quality Mgt Sys | 2015-09-16 | Tamira Baird | 2016-04-21 14:34 | 15100- Expansion Locks Atlantic | Gene Williams
00160 |  |  | AE8021 car Safe Waste Transportatio | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2012-04-24 | Eliza Florendo | 2012-05-21 09:53 | 15100- Expansion Locks Atlantic | Abed Camarena
00160 |  |  | AQ0049 CAR Personnel Protec Equip | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-07-19 | Maria Ho | 2012-08-22 09:23 | 15100- Expansion Locks Atlantic | Maria Ho
00920 |  | Maint. BLDG | AQ0431 NCR Maint. BLDG Anchor Bolt | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-07-21 | Zosimo Correa | 2014-11-13 10:51 | 15100- Expansion Locks Atlantic | Zosimo Correa
00159 |  |  | AE8020 CAR Tecsan personnel induct. | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2012-04-24 | Graciela Palacios | 2012-10-10 13:54 | 15100- Expansion Locks Atlantic | Abed Camarena
00334 |  |  | P-WSB FML Cleanout MH Cover Con | Noncompliance Notice | Closed | Luis Isaza | Quality Mgt Sys | 2015-09-30 | Lorely Rivera | 2016-03-10 09:26 | 15200- Expansion Locks Pacific | Marta Small
00159 |  |  | AQ0053 CAR DEF on Action Plans | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-07-19 | Karla Jones | 2012-08-22 07:42 | 15100- Expansion Locks Atlantic | Karla Jones
00927 |  | Structural | AQ0437 NCR Structural Steel MRB3&2 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-07-23 | Zosimo Correa | 2014-11-14 12:02 | 15100- Expansion Locks Atlantic | Abdiel Santos
00158 |  |  | AQ0051 CAR Subcontractor DOCS | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-07-19 | Karla Jones | 2012-08-21 16:04 | 15100- Expansion Locks Atlantic | Karla Jones
01067 |  |  | created as an error | Noncompliance Notice | Void | Javier Barrera |  | 2015-10-03 | Tamira Baird | 2016-02-02 11:50 |  | Tamira Baird
00158 |  |  | AE8029 CAR POL Mngt Maint. Workshop | Corrective Action Request | Closed | Jose Pelaez | Environmental Situation | 2012-04-20 | Tamira Baird | 2015-09-04 13:34 | 15100- Expansion Locks Atlantic | Adrian Lee
00338 |  |  | P-Elect Install Work | Noncompliance Notice | Closed | Luis Isaza | Quality Mgt Sys | 2015-10-09 | Marta Small | 2016-07-19 13:50 | 15200- Expansion Locks Pacific | Marta Small
00157 |  |  | AQ0050 CAR CPC Machinery Operators | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-07-19 | Karla Jones | 2012-08-21 14:42 | 15100- Expansion Locks Atlantic | Karla Jones
00157 |  |  | PQ0068 CAR AUDIT FINDING REPORT No1 | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-04-12 | Maria Ho | 2012-08-25 11:59 | 15200- Expansion Locks Pacific | Luz Arosemena
00926 |  | CB-EW-03 Conc | AQ0436 NCR CB-EW-03 Conc Consol DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-07-23 | Mayra Santos | 2016-03-09 08:59 | 15100- Expansion Locks Atlantic | Abdiel Santos
00156 |  |  | PQ0066 CAR Middle East & West QMS | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-04-05 | Luz Arosemena | 2012-05-23 08:39 | 15200- Expansion Locks Pacific | Luz Arosemena
00156 |  |  | AQ0048 CAR Social Security Document | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-07-19 | Karla Jones | 2012-08-21 14:44 | 15100- Expansion Locks Atlantic | Karla Jones
00337 |  |  | P - Anchor Door PMF Frames | Noncompliance Notice | Closed | Luis Isaza | Quality Mgt Sys | 2015-10-09 | Marta Small | 2016-10-05 07:52 | 15200- Expansion Locks Pacific | Marta Small
00928 |  | MRB3 Block | AQ0438 NCR MRB3 Block Masonry DEF. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-07-28 | Abdiel Santos | 2014-08-25 16:56 | 15100- Expansion Locks Atlantic | Abdiel Santos
00155 |  |  | PQ0065 CAR UW-M03-C04a QMS Process | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-04-05 | Luz Arosemena | 2012-08-02 09:42 | 15200- Expansion Locks Pacific | Luz Arosemena
00336 |  |  | A – Raised Floor Without Anchoring | Noncompliance Notice | Open | Ramon Porcell | Quality Mgt Sys | 2015-10-09 | Karla Jones | 2017-01-26 14:51 | 15100- Expansion Locks Atlantic | Tamira Baird
00155 |  |  | AQ0047 CAR ADMN CTRL Procedures | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-07-19 | Karla Jones | 2012-08-21 14:44 | 15100- Expansion Locks Atlantic | Karla Jones
00929 |  | MRB-2 Facade | AQ0439 NCR MRB-2 Facade Beam defect | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-07-30 | Zosimo Correa | 2014-11-19 12:00 | 15100- Expansion Locks Atlantic | Abdiel Santos
00335 |  |  | P-Building Isulated Metal Panel Ins | Noncompliance Notice | Open | Rafael Sarmiento | Quality Mgt Sys | 2015-10-09 | Lorely Rivera | 2015-12-16 13:49 | 15200- Expansion Locks Pacific | Marta Small
00154 |  |  | AQ0035B CAR USE of Ext made to truc | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-07-26 | Maria Ho | 2012-08-21 10:10 | 15100- Expansion Locks Atlantic | Maria Ho
00154 |  |  | AE8024 CAR evid of spill prevention | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2012-04-03 | Eliza Florendo | 2012-05-21 09:40 | 15100- Expansion Locks Atlantic | Abed Camarena
00011 |  | NCR CIM | G50M0012 NCR CIM Anodes F1&F2 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2014-08-01 | Alberto Alonzo | 2014-09-11 10:58 | 15000- Expansion Locks | Alberto Alonzo
00153 |  |  | GQ0080 CAR As Built Draw Proccess | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2012-03-28 | Maria Ho | 2012-09-14 11:38 | 15000- Expansion Locks | Maria Ho
00339 |  |  | A – Unsafe Practice in Excavation. | Noncompliance Notice | Closed | No Ball in Court | Safety & Health Issue | 2015-11-19 | Tamira Baird | 2016-05-24 15:13 | 15100- Expansion Locks Atlantic | Tamira Baird
00930 |  | APP-OE-P02A+P02B | NCRP0461CS APP-OE-P02A+P02B Sonic T | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-08-05 | Luz Arosemena | 2014-10-08 14:32 | 15200- Expansion Locks Pacific | Luz Arosemena
00153 |  |  | AQ0060 CAR Edge of the Bench DEF | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-07-19 | Karla Jones | 2012-08-14 11:16 | 15100- Expansion Locks Atlantic | Karla Jones
00152 |  |  | AQ0056 CAR Electric Joints IMPR DEF | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-07-19 | Karla Jones | 2012-08-14 10:42 | 15100- Expansion Locks Atlantic | Karla Jones
00935 |  | NCR Upper Rail US | A50M0013 NCR Upper Rail US Recess 5 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-08-06 | Abdiel Santos | 2014-09-16 09:54 | 15100- Expansion Locks Atlantic | Abdiel Santos
00340 |  |  | P- COP0001 Lack Compliance Handover | Noncompliance Notice | Closed | Luis Isaza | Other | 2015-11-24 | Marta Small | 2016-07-20 11:52 | 15200- Expansion Locks Pacific | Marisol Fabrega
00152 |  |  | AE8027 CAR WasteWater Management Be | Corrective Action Request | Closed | Jose Pelaez | Environmental Situation | 2012-03-27 | Abed Camarena | 2012-05-24 15:01 | 15100- Expansion Locks Atlantic | Adrian Lee
00151 |  |  | AQ0055 CAR MOVMNT of Gas Cylinder | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-07-19 | Karla Jones | 2012-08-14 10:18 | 15100- Expansion Locks Atlantic | Karla Jones
00934 |  | NCR Large | A50M0012 NCR Large EndStop Recess4 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-08-06 | Abdiel Santos | 2014-09-16 09:34 | 15100- Expansion Locks Atlantic | Abdiel Santos
00151 |  |  | AE8019 Inadequate sediment control | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2011-08-08 | Tamira Baird | 2015-09-04 13:38 | 15100- Expansion Locks Atlantic | Adrian Lee
00342 |  |  | P – SOR Pipe Service Install Varian | Noncompliance Notice | Closed | Luis Isaza | Quality Mgt Sys | 2015-12-10 | Marta Small | 2016-07-05 08:22 | 15200- Expansion Locks Pacific | Marta Small
00150 |  |  | AE8028 CAR Compaction of Material | Corrective Action Request | Closed | Calin Andreescu | Environmental Situation | 2012-03-27 | Abed Camarena | 2012-05-02 12:09 | 15100- Expansion Locks Atlantic | Adrian Lee
00341 |  |  | P – SAND Pipe Service Install Varia | Noncompliance Notice | Closed | Juan Arturo Rivera | Quality Mgt Sys | 2015-12-10 | Marta Small | 2016-07-04 10:11 | 15200- Expansion Locks Pacific | Marta Small
00933 |  | NCR Large Recess | A50M0011 NCR Large Recess End Stop | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-08-06 | Abdiel Santos | 2014-09-16 09:29 | 15100- Expansion Locks Atlantic | Abdiel Santos
00150 |  |  | PS5001 CAR Accident Report | Corrective Action Request | Open | Carlos Reyes | Time Extension | 2012-03-19 | Maria Ho | 2012-03-19 15:15 | 15000- Expansion Locks | Maria Ho
00932 |  | NCR Seismic Hook | A50M0010 NCR Seismic Hook-Recess 3 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-08-06 | Abdiel Santos | 2014-09-16 09:23 | 15100- Expansion Locks Atlantic | Abdiel Santos
00149 |  |  | AE8025 CAR spill from a water truck | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2012-03-14 | Tamira Baird | 2015-09-04 13:37 | 15100- Expansion Locks Atlantic | Abed Camarena
00343 |  |  | P-SAND SOR Penetrate Core Dam 2W | Noncompliance Notice | Open | Rafael Sarmiento | Quality Mgt Sys | 2015-12-16 | Fernando Sanchez | 2015-12-22 13:45 | 15200- Expansion Locks Pacific | Marta Small
00149 |  |  | AQ0142 CAR QMS Failure in WIR proce | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2012-03-17 | Karla Jones | 2012-11-14 11:28 | 15100- Expansion Locks Atlantic | Karla Jones
00931 |  | NCR Upper Rail US | A50M0009 NCR Upper Rail US Recess 6 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-08-06 | Abdiel Santos | 2014-09-16 09:13 | 15100- Expansion Locks Atlantic | Abdiel Santos
00344 |  |  | G-Lock Gate Floating Stability | Noncompliance Notice | Open | Jorge de la Guardia |  | 2016-02-08 | Veronica Cash | 2016-02-15 11:44 | 15000- Expansion Locks | Gladys Arias
00148 |  |  | AE8026 CAR lack of proper waste mng | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2012-03-07 | Tamira Baird | 2015-09-04 13:40 | 15100- Expansion Locks Atlantic | Abed Camarena
00147 |  |  | PE8044 CAR Excav Equip Condition | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2012-01-30 | Tamira Baird | 2015-09-04 13:42 | 15200- Expansion Locks Pacific | Eliza Florendo
00939 |  | EMHM214 EndBell | AQ0440 NCR EMHM214 EndBell Not Inst | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-08-13 | Zosimo Correa | 2014-11-27 10:30 | 15100- Expansion Locks Atlantic | Abdiel Santos
00345 |  |  | P- Unsafe Excavation Conditions PAC | Noncompliance Notice | Closed | Rafael Sarmiento | Unsafe conditions | 2016-02-19 | Marta Small | 2016-07-04 11:09 | 15000- Expansion Locks | Marta Small
00346 |  |  | G-Accumulation of scrap tires waste | Noncompliance Notice | Closed | Jorge de la Guardia | Environmental Situation | 2016-02-25 | Marta Small | 2016-10-18 07:33 | 15000- Expansion Locks | Tamira Baird
00146 |  |  | AS5022CAR-Lack of LO-TO | Corrective Action Request | Closed | Patricio Vilo | Safety & Health Issue | 2012-02-15 | Jianey Abrahams | 2013-04-01 13:52 | 15100- Expansion Locks Atlantic | Jianey Abrahams
00937 |  | EMH | NCRP0463CS EMH Pulling Iron | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2014-08-13 | Luz Arosemena | 2015-07-21 16:35 | 15200- Expansion Locks Pacific | Luz Arosemena
00347 |  |  | P – Fire Fighting Hydrant Fixture | Noncompliance Notice | Closed | Luis Isaza | Quality Mgt Sys | 2016-03-02 | Marta Small | 2016-07-05 08:09 | 15200- Expansion Locks Pacific | Marta Small
00145 |  |  | PQ0063 CAR LH3 F.Treatment works | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2012-02-22 | Luz Arosemena | 2012-05-23 08:27 | 15200- Expansion Locks Pacific | Luz Arosemena
00936 |  | APP Sonic Test | NCRP0462CS APP Sonic Test F. Shafts | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-08-13 | Rick Montanari | 2015-01-12 12:10 | 15200- Expansion Locks Pacific | Luz Arosemena
00144 |  |  | PQ0064 CAR RFC Shop Drawings | Corrective Action Request | Closed | No Ball in Court | Administrative | 2012-02-17 | Maria Ho | 2012-07-04 08:44 | 15200- Expansion Locks Pacific | Luz Arosemena
00348 |  |  | P - WWTP Work Product Status QMS Do | Noncompliance Notice | Closed | Luis Isaza | Quality Mgt Sys | 2016-03-07 | Marta Small | 2016-07-11 12:54 | 15200- Expansion Locks Pacific | Marta Small
00938 |  | App. Struc | AQ0428 NCR App. Struc. Found. Disp. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-08-18 | Mayra Santos | 2016-05-14 11:21 | 15100- Expansion Locks Atlantic | Abdiel Santos
00941 |  | BOR 2E & 1W | NCRP0464CS BOR 2E & 1W Filter 3A | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-08-21 | Luz Arosemena | 2014-09-30 15:21 | 15200- Expansion Locks Pacific | Luz Arosemena
00143 |  |  | A00/UPCCAR5021 Suspended loads | Corrective Action Request | Closed | Jose Pelaez | Safety & Health Issue | 2011-11-30 | Tamira Baird | 2015-09-04 13:43 | 15100- Expansion Locks Atlantic | Jianey Abrahams
00349 |  |  | P - Aluminum Window Install Block W | Noncompliance Notice | Closed | Samuel Cohen | Quality Mgt Sys | 2016-03-16 | Marta Small | 2016-11-16 08:23 | 15200- Expansion Locks Pacific | Marta Small
00350 |  |  | P – DIP Coating Method PWD Pipe Pro | Noncompliance Notice | Closed | Samuel Cohen | Quality Mgt Sys | 2016-03-30 | Marta Small | 2016-11-16 08:37 | 15200- Expansion Locks Pacific | Marta Small
00142 |  |  | A00/UPCCAR5020 BTB lack of Cert. | Corrective Action Request | Closed | Tatiany DeJohnson | Safety & Health Issue | 2011-11-15 | Tamira Baird | 2015-09-04 13:44 | 15100- Expansion Locks Atlantic | Jianey Abrahams
00940 |  | NCR LH2 RG3 URail | P50M0007 NCR LH2 RG3 URail Bolts US | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-08-21 | Juan Rivera | 2015-10-19 09:59 | 15200- Expansion Locks Pacific | Karlos Azuz
00351 |  |  | P - PWD Corp Curb Stop Connect | Noncompliance Notice | Closed | Luis Isaza | Quality Mgt Sys | 2016-04-20 | Marta Small | 2016-07-07 15:35 | 15200- Expansion Locks Pacific | Marta Small
00141 |  |  | A00/UPCCAR5018 Fall Protection | Corrective Action Request | Closed | Rafael Sarmiento |  | 2011-09-25 | Tamira Baird | 2015-09-04 13:45 | 15100- Expansion Locks Atlantic | Jianey Abrahams
00942 |  | Zone D | NCRP0456CS Zone D Seepage Barrier | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2014-08-27 | Luz Arosemena | 2015-08-10 14:41 | 15200- Expansion Locks Pacific | Luz Arosemena
00943 |  | Voids UE-M21, M22 | NCRP0465CS Voids UE-M21, M22 & M23 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2014-08-28 | Lorely Rivera | 2015-03-29 09:27 | 15200- Expansion Locks Pacific | Luz Arosemena
8010 |  |  | AQ0494 NCR - SDS Repairs East Side | Noncompliance Notice | Open | Javier Barrera | Construction Deficiency | 2016-09-24 | Abdiel Santos | 2016-12-07 10:45 | 15100- Expansion Locks Atlantic | Abdiel Santos
00140 |  |  | PE8024 CAR Tnk Frm Outlet to O/W S | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2011-08-24 | Tamira Baird | 2015-09-04 13:45 | 15200- Expansion Locks Pacific | Eliza Florendo
8011 |  |  | VOID | Noncompliance Notice | Void | NO BIC-GUPC |  |  | Abdiel Santos | 2016-12-27 15:23 |  | Abdiel Santos
00951 |  | NCR Up Rail Rec. 5 | A50M0015 NCR Up Rail Rec. 5 out tol | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-09-08 | Abdiel Santos | 2014-10-15 09:58 | 15100- Expansion Locks Atlantic | Abdiel Santos
00139 |  |  | AE8012 CAR Drainage Layout | Corrective Action Request | Closed | Diana Velasco | Environmental Situation | 2011-07-11 | Tamira Baird | 2015-09-04 13:47 | 15100- Expansion Locks Atlantic | Eliza Florendo
00950 |  | NCR Up Rail Rec | A50M0014 NCR Up Rail Rec. 6 out | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-09-08 | Abdiel Santos | 2014-10-24 15:36 | 15100- Expansion Locks Atlantic | Abdiel Santos
00138 |  |  | AE8017 CAR Flw Contrl Disposl Sites | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2011-05-10 | Tamira Baird | 2015-09-04 13:48 | 15100- Expansion Locks Atlantic | Eliza Florendo
8009 |  |  |  | Noncompliance Notice | Void | No Ball in Court |  |  | Abdiel Santos | 2014-10-24 15:31 |  | Abdiel Santos
8004 |  |  | VOID | Noncompliance Notice | Void | No Ball in Court | Administrative |  | Maria Ho | 2012-08-29 16:01 | 15100- Expansion Locks Atlantic | Maria Ho
00137 |  |  | AE8016 CAR Disclose WMP | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2011-07-11 | Tamira Baird | 2015-09-04 14:01 | 15100- Expansion Locks Atlantic | Eliza Florendo
00946 |  | Corner Protection | AQ0442 NCR Corner Protection at WSB | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-09-08 | Abdiel Santos | 2014-10-08 14:10 | 15100- Expansion Locks Atlantic | Abdiel Santos
00136 |  |  | G-Weekly Programme Progress Update | Noncompliance Notice | Closed | No Ball in Court | Administrative | 2011-05-25 | Maria Ho | 2012-01-26 12:19 | 15000- Expansion Locks | Vielka Walters
00136 |  |  | AE8015 CAR Soil Protection | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2011-05-10 | Tamira Baird | 2015-09-04 14:10 | 15100- Expansion Locks Atlantic | Eliza Florendo
00944 |  | DevTolerance APP | NCRP0470CS DevTolerance APP-OE-P10A | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-09-09 | Luz Arosemena | 2014-09-30 16:27 | 15200- Expansion Locks Pacific | Luz Arosemena
00135 |  |  | P - Placement of Fill in the 1939 | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2011-05-18 | Larry Ohrn | 2011-05-26 07:06 | 15200- Expansion Locks Pacific | Vielka Walters
00948 |  | DB-CMH206-4 Termof | AM2503 NCR DB-CMH206-4 Termof J DEF | Nonconformance Report | Open | Jose Dorantes | Construction Deficiency | 2014-09-15 | Larry Ohrn | 2015-04-08 14:50 | 15100- Expansion Locks Atlantic | Abdiel Santos
00135 |  |  | PE8019 CAR Distribute WMP | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2011-07-11 | Tamira Baird | 2015-09-04 14:11 | 15200- Expansion Locks Pacific | Eliza Florendo
00134 |  |  | G - Progress Report Submittal | Noncompliance Notice | Open | Itzel Ulloa | Administrative | 2011-05-10 | Ana Glaize | 2014-03-25 15:35 | 15000- Expansion Locks | Lorri Cullivan
00134 |  |  | PE8018 CAR Soil Protection | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2011-05-10 | Tamira Baird | 2015-09-04 14:11 | 15200- Expansion Locks Pacific | Eliza Florendo
00945 |  | Bld Lack | NCRP0010CS Bld Lack Humidity Paint | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2014-09-15 | Lorely Rivera | 2016-07-06 16:02 | 15200- Expansion Locks Pacific | Luz Arosemena
00133 |  |  | P- Disposal Area 4 | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2011-05-06 | Marco Villarreal | 2014-10-29 08:28 | 15200- Expansion Locks Pacific | Vielka Walters
00133 |  |  | PE8017 CAR Drainage Pattern Layout | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2011-07-11 | Tamira Baird | 2015-09-04 14:12 | 15200- Expansion Locks Pacific | Eliza Florendo
00952 |  | MRB-3 Pulley Base | AQ0445 NCR MRB-3 Pulley Base C DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-09-16 | Abdiel Santos | 2014-12-11 11:25 | 15100- Expansion Locks Atlantic | Abdiel Santos
00132 |  |  | P- Equipment Inspection | Noncompliance Notice | Closed | Juan H Wong | Safety & Health Issue | 2011-05-06 | Mercedes Peters | 2012-01-11 14:38 | 15200- Expansion Locks Pacific | Vielka Walters
00132 |  |  | AE8014 CAR Lack Sediment Control | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2011-05-10 | Tamira Baird | 2015-09-04 14:13 | 15100- Expansion Locks Atlantic | Eliza Florendo
00949 |  | MRB4-TS-02-R01 | AQ0444 NCR MRB4-TS-02-R01 Form Fail | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-09-16 | Zosimo Correa | 2015-01-17 09:41 | 15100- Expansion Locks Atlantic | Abdiel Santos
00131 |  |  | P- Fall Protection Vertical | Noncompliance Notice | Closed | Juan H Wong | Safety & Health Issue | 2011-05-06 | Cecilia Ung | 2011-10-06 15:45 | 15200- Expansion Locks Pacific | Vielka Walters
00131 |  |  | AE8013 CAR Cylinder Access Restrict | Corrective Action Request | Closed | Diana Velasco | Environmental Situation | 2012-02-09 | Tamira Baird | 2015-09-04 14:14 | 15100- Expansion Locks Atlantic | Eliza Florendo
00947 |  | Stirrups of | AQ0443 NCR Stirrups of Column Pile | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-09-23 | Jose Dorantes | 2016-07-12 15:50 | 15100- Expansion Locks Atlantic | Abdiel Santos
00130 |  |  | P- Disposal Area 1 | Noncompliance Notice | Closed | Gustavo Rivas Sr. | Quality Mgt Sys | 2011-05-06 | Lorena Jethmal | 2012-07-06 13:51 | 15200- Expansion Locks Pacific | Vielka Walters
00953 |  | MRB2-3 Share Key | AQ0446 NCR MRB2-3 Share Key n/Left | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-10-15 | Abdiel Santos | 2016-12-05 15:02 | 15100- Expansion Locks Atlantic | Abdiel Santos
00130 |  |  | PE8020 CAR - NCN 112 Used Oils | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2011-06-17 | Tamira Baird | 2015-09-04 14:15 | 15200- Expansion Locks Pacific | Eliza Florendo
00129 |  |  | G - Current Programme Submittal | Noncompliance Notice | Closed | No Ball in Court | Administrative | 2011-05-09 | John Lopacki | 2012-07-23 10:12 | 15000- Expansion Locks | Dinesh Damavarapu
00956 |  | Backfi. LLC EAST | AQ0450 NCR Backfi. LLC EAST Geo DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-10-20 | Zosimo Correa | 2015-06-03 14:00 | 15100- Expansion Locks Atlantic | Abdiel Santos
00129 |  |  | PE8010 CAR Emission Monitoring | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2011-04-25 | Tamira Baird | 2015-09-04 14:16 | 15200- Expansion Locks Pacific | Eliza Florendo
00128 |  |  | G - Current Programme Actuals | Noncompliance Notice | Closed | No Ball in Court | Administrative | 2011-05-09 | John Lopacki | 2011-11-11 08:29 | 15000- Expansion Locks | Dinesh Damavarapu
00128 |  |  | PE8045 CAR Hydrocarbon Spills | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2012-02-06 | Tamira Baird | 2015-09-04 14:19 | 15200- Expansion Locks Pacific | Eliza Florendo
00955 |  | Backf. LLC Geo | AQ0448 NCR Backf. LLC Geo Inst DEF. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-10-20 | Zosimo Correa | 2015-06-03 13:54 | 15100- Expansion Locks Atlantic | Abdiel Santos
00127 |  |  | P - Fall Protection Horizontal | Noncompliance Notice | Closed | Juan H Wong | Safety & Health Issue | 2011-05-04 | Cecilia Ung | 2011-10-06 15:55 | 15200- Expansion Locks Pacific | Vielka Walters
00127 |  |  | AE8009 CAR Notify of PM10 Readings | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2011-01-25 | Tamira Baird | 2015-09-04 14:19 | 15100- Expansion Locks Atlantic | Eliza Florendo
00954 |  | Backf. LMC Geo | AQ0447 NCR Backf. LMC Geo Inst DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-10-20 | Zosimo Correa | 2015-06-03 11:43 | 15100- Expansion Locks Atlantic | Abdiel Santos
00126 |  |  | A-Mass Concrete Used as Fill or Dra | Noncompliance Notice | Closed | Jose E. Reyes | Quality Mgt Sys | 2011-04-29 | Mario Montemayor | 2011-07-07 13:51 | 15100- Expansion Locks Atlantic | Mercedes Peters
00957 |  | NCR - Painting DEF | A50M0016 NCR - Painting DEF Gate 5 | Nonconformance Report | Open | Jose Dorantes | Construction Deficiency | 2014-10-24 | Larry Ohrn | 2015-07-16 08:31 | 15100- Expansion Locks Atlantic | Abdiel Santos
00126 |  |  | AE8008 CAR Know of EP and IFC PS | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2011-02-03 | Tamira Baird | 2015-09-04 14:20 | 15100- Expansion Locks Atlantic | Eliza Florendo
00125 |  |  | A-Dock 45 West Fill Failure Follow | Noncompliance Notice | Closed | Bernardo Gonzalez | Quality Mgt Sys | 2011-04-29 | Rick Montanari | 2011-06-22 09:43 | 15100- Expansion Locks Atlantic | Mercedes Peters
00958 |  | UL Conduits | AQ0451 NCR UL Conduits Not Approved | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-11-07 | Zosimo Correa | 2015-01-31 09:39 | 15100- Expansion Locks Atlantic | Abdiel Santos
00125 |  |  | AE8007 CAR Hazard Warning Labels | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2011-02-23 | Tamira Baird | 2015-09-04 14:23 | 15100- Expansion Locks Atlantic | Eliza Florendo
00124 |  |  | P - Underground Utility Damage | Noncompliance Notice | Closed | Juan H Wong | Safety & Health Issue | 2011-04-18 | Vielka Walters | 2011-07-22 15:18 | 15200- Expansion Locks Pacific | Vielka Walters
00124 |  |  | AE8006 CAR Daily Inspection Records | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-10-13 | Tamira Baird | 2015-09-04 14:25 | 15100- Expansion Locks Atlantic | Eliza Florendo
00959 |  | T5-C2 & T6-C2 | AQ0452 NCR T5-C2 & T6-C2 Corbel DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-11-15 | Zosimo Correa | 2014-12-18 11:33 | 15100- Expansion Locks Atlantic | Abdiel Santos
00123 |  |  | P - Concrete Waste Disposal | Noncompliance Notice | Closed | Juan H Wong | Environmental Situation | 2011-04-15 | Vielka Walters | 2011-06-15 14:35 | 15200- Expansion Locks Pacific | Vielka Walters
00963 |  | NCR LH3 RG6 URail | P50M0010 NCR LH3 RG6 URail Bolt UD | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-11-28 | Juan Rivera | 2015-10-19 10:02 | 15200- Expansion Locks Pacific | Luz Arosemena
00123 |  |  | AE8005 CAR Safe Waste Transport | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-11-04 | Tamira Baird | 2015-09-04 14:42 | 15100- Expansion Locks Atlantic | Eliza Florendo
00122 |  |  | P - 1939 Backfilling Excavations | Noncompliance Notice | Closed | Juan H Wong | Quality Mgt Sys | 2011-04-11 | Vielka Walters | 2011-07-25 10:47 | 15200- Expansion Locks Pacific | Vielka Walters
00962 |  | NCR Painting DEF | A50M0017 NCR Painting DEF Gates A1 | Nonconformance Report | Open | Ramon Porcell | Construction Deficiency | 2014-11-28 | Ramon Porcell | 2015-11-19 13:00 | 15100- Expansion Locks Atlantic | Abdiel Santos
00122 |  |  | AE8004 CAR Lack Spill Prevention | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2011-02-03 | Tamira Baird | 2015-09-04 14:43 | 15100- Expansion Locks Atlantic | Eliza Florendo
00121 |  |  | G-Updated Drawing List | Noncompliance Notice | Closed | Antonio M. Zaffaroni | Administrative | 2011-04-11 | Donna Reese | 2011-05-31 09:58 | 15000- Expansion Locks | Vielka Walters
00121 |  |  | PE8009 CAR Execute Monitoring Prog | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2010-11-01 | Tamira Baird | 2015-09-04 14:44 | 15200- Expansion Locks Pacific | Eliza Florendo
00961 |  | NCR LH3 RG5 URail | P50M0009 NCR LH3 RG5 URail Bolt UD | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-11-28 | Juan Rivera | 2015-10-19 10:01 | 15200- Expansion Locks Pacific | Luz Arosemena
00120 |  |  | A-Inappropriate Management of Waste | Noncompliance Notice | Closed | Jose E. Reyes | Environmental Situation | 2011-04-08 | Rick Montanari | 2011-04-29 11:32 | 15100- Expansion Locks Atlantic | Mercedes Peters
00960 |  | NCR LH2 | P50M0008 NCR LH2 RG4 MSupport | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2014-11-28 | Juan Rivera | 2015-10-19 10:06 | 15200- Expansion Locks Pacific | Luz Arosemena
00120 |  |  | PE8008 CAR Notification PM10 Result | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2011-01-25 | Tamira Baird | 2015-09-04 14:46 | 15200- Expansion Locks Pacific | Eliza Florendo
00119 |  |  | G-Audit PIO Design 25 March 2011 | Noncompliance Notice | Void | No Ball in Court | Quality Mgt Sys | 2011-04-04 | Lorri Cullivan | 2011-05-09 15:13 | 15004- Expansion Locks Design | Lorri Cullivan
00970 |  | NCR Gates Paint | P50M0014 NCR Gates Paint Defects RG | Nonconformance Report | Closed | Juan Arturo Rivera | Construction Deficiency | 2014-12-03 | Maria Elena Navarro | 2016-06-04 08:17 | 15200- Expansion Locks Pacific | Lorely Rivera
00119 |  |  | PE8007 CAR IFC Performance Standard | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2011-02-03 | Tamira Baird | 2015-09-04 14:47 | 15200- Expansion Locks Pacific | Eliza Florendo
00118 |  |  | P-NcN Cutting Trees | Noncompliance Notice | Closed | Juan H Wong | Environmental Situation | 2011-04-04 | Vielka Walters | 2011-06-07 14:36 | 15200- Expansion Locks Pacific | Vielka Walters
00118 |  |  | PE8006 CAR Safe Waste Transport | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-12-27 | Tamira Baird | 2015-09-04 14:48 | 15200- Expansion Locks Pacific | Eliza Florendo
00969 |  | NCR LH3-4 RG5-8 | P50M0013 NCR LH3-4 RG5-8 End Stop | Nonconformance Report | Closed | Juan Arturo Rivera | Construction Deficiency | 2014-12-03 | Maria Elena Navarro | 2016-06-04 08:42 | 15200- Expansion Locks Pacific | Lorely Rivera
00117 |  |  | P-Disposal Area 3 | Noncompliance Notice | Closed | Juan H Wong | Quality Mgt Sys | 2011-03-24 | Cecilia Ung | 2011-08-30 07:23 | 15200- Expansion Locks Pacific | Vielka Walters
00117 |  |  | GQ0079 CAR Shop Drawing Control | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2012-01-30 | Maria Ho | 2012-06-05 14:42 | 15000- Expansion Locks | Maria Ho
00968 |  | NCR LH1 RG1 End | P50M0011 NCR LH1 RG1 End Stop LR | Nonconformance Report | Closed | Juan Arturo Rivera | Construction Deficiency | 2014-12-03 | Juan Rivera | 2015-10-19 10:05 | 15200- Expansion Locks Pacific | Lorely Rivera
00116 |  |  | P-Approach Channel Excavation | Noncompliance Notice | Closed | Rick Montanari | Quality Mgt Sys | 2011-03-24 | Rick Montanari | 2012-01-25 12:15 | 15200- Expansion Locks Pacific | Vielka Walters
00116 |  |  | AQ0136 CAR Steel Trowel Finish SPEC | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2011-11-10 | Karla Jones | 2013-03-26 08:23 | 15100- Expansion Locks Atlantic | Karla Jones
00966 |  | NCR LH3-4 RG5 | P50M0016 NCR LH3-4 RG5-8 URail | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-12-03 | Juan Rivera | 2015-10-19 10:24 | 15200- Expansion Locks Pacific | Lorely Rivera
00115 |  |  | P-Miraflores Cofferdam | Noncompliance Notice | Closed | Juan H Wong | Quality Mgt Sys | 2011-03-17 | Javier Gutierrez | 2011-08-12 10:58 | 15200- Expansion Locks Pacific | Vielka Walters
00021 |  | NCR EqValve Rod | P55M0043 NCR EqValve Rod Clamp B02 | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-12-03 | Luz Arosemena | 2015-02-24 14:37 | 15200- Expansion Locks Pacific | Lorely Rivera
00115 |  |  | AQ0141 CAR QMS FAIL on NCR128 CLSR | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2012-02-01 | Karla Jones | 2012-11-14 11:09 | 15100- Expansion Locks Atlantic | Karla Jones
00114 |  |  | P-Construction Waste Management | Noncompliance Notice | Closed | Juan H Wong | Environmental Situation | 2011-03-14 | Vielka Walters | 2011-07-21 11:19 | 15200- Expansion Locks Pacific | Vielka Walters
00972 |  | IW-M01 (I | AQ0441 NCR IW-M01 (I) Missing Hooks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-12-04 | Zosimo Correa | 2014-12-22 08:30 | 15100- Expansion Locks Atlantic | Abdiel Santos
00114 |  |  | PE8005 CAR Oil-Water Separator | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-10-22 | Tamira Baird | 2015-09-04 14:51 | 15200- Expansion Locks Pacific | Eliza Florendo
00113 |  |  | A-GUPC Production QC Documentation | Noncompliance Notice | Closed | Jose E. Reyes | Quality Mgt Sys | 2011-03-11 | Rick Montanari | 2011-06-13 11:07 | 15100- Expansion Locks Atlantic | Mercedes Peters
00971 |  | MRB-1 Facade | AQ0449 NCR MRB-1 Facade Beam defect | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-12-04 | Zosimo Correa | 2015-01-31 08:59 | 15100- Expansion Locks Atlantic | Abdiel Santos
00113 |  |  | AS5002 CAR LACK OF PPE | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-10-13 | Maria Ho | 2012-01-31 17:06 | 15100- Expansion Locks Atlantic | Maria Ho
00112 |  |  | P-Hazardous Waste | Noncompliance Notice | Closed | Juan H Wong | Environmental Situation | 2011-03-09 | Vielka Walters | 2011-06-20 14:07 | 15200- Expansion Locks Pacific | Lorri Cullivan
00112 |  |  | PQ0062 CAR Concrete Mix SMC-P21 | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-01-31 | Luz Arosemena | 2012-05-23 08:32 | 15200- Expansion Locks Pacific | Luz Arosemena
00973 |  | NCR LH2 RG4 LTW PL 4 | P50M0012 NCR LH2 RG4 LTW PL 4 & 5 | Nonconformance Report | Closed | Juan Arturo Rivera | Construction Deficiency | 2014-12-09 | Juan Rivera | 2015-10-19 10:41 | 15200- Expansion Locks Pacific | Luz Arosemena
00111 |  |  | P- Victoria Disposal | Noncompliance Notice | Open | Luis Isaza | Quality Mgt Sys | 2011-03-04 | Marta Small | 2016-11-16 09:05 | 15200- Expansion Locks Pacific | Vielka Walters
00111 |  |  | GQ0078 CAR Drawing Control Process | Corrective Action Request | Closed | No Ball in Court | Administrative | 2012-01-26 | Maria Ho | 2012-06-05 15:08 | 15000- Expansion Locks | Maria Ho
00976 |  | DW-M06D-W01 pipe | AQ0453 NCR DW-M06D-W01 pipe not INS | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-12-12 | Zosimo Correa | 2015-04-20 16:02 | 15100- Expansion Locks Atlantic | Abdiel Santos
00110 |  |  | P-Foundation Prep w-o IFC_DFH2 | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2011-02-24 | Larry Belken | 2011-04-28 15:14 | 15200- Expansion Locks Pacific | Vielka Walters
00975 |  | Lock | NCRP0471CS Lock Subdrainage System | Nonconformance Report | Concluded | Juan Arturo Rivera | Construction Deficiency | 2014-12-18 | Lorely Rivera | 2016-04-16 09:34 | 15200- Expansion Locks Pacific | Lorely Rivera
00110 |  |  | AQ0140 CAR QMS FAIL during NCR CLSR | Corrective Action Request | Closed | No Ball in Court | Administrative | 2012-01-26 | Karla Jones | 2013-03-19 08:08 | 15100- Expansion Locks Atlantic | Karla Jones
00109 |  |  | A - Rock Fall Work No Approved SWP | Noncompliance Notice | Closed | Jose E. Reyes | Safety & Health Issue | 2011-02-18 | Mario Montemayor | 2011-05-19 10:44 | 15100- Expansion Locks Atlantic | Mercedes Peters
00109 |  |  | PM2501 CAR Stud Bending in FSE | Corrective Action Request | Closed | NO BIC-GUPC | Construction Deficiency | 2012-01-19 | Juan Rivera | 2014-07-16 18:57 | 15200- Expansion Locks Pacific | Ariel Jaen
00001 |  | NCR DIP | A66M0001 NCR DIP Damages DEF | Nonconformance Report | Open | Jose Dorantes | Defective Materials | 2014-12-22 | Ramon Porcell | 2015-08-04 10:59 | 15100- Expansion Locks Atlantic | Zosimo Correa
00108 |  |  | A-Lack of Impalement Protection | Noncompliance Notice | Closed | Jose E. Reyes | Safety & Health Issue | 2011-02-18 | Mario Montemayor | 2011-05-19 07:37 | 15100- Expansion Locks Atlantic | Mercedes Peters
00108 |  |  | AM2500 CAR Stud Bending in FSE | Corrective Action Request | Closed | NO BIC-GUPC | Construction Deficiency | 2012-01-18 | Juan Rivera | 2014-02-27 22:06 | 15100- Expansion Locks Atlantic | Ariel Jaen
00977 |  | MRB4 & MRB1 | AQ0454 NCR MRB4 & MRB1 Wrong Metal | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-12-23 | Zosimo Correa | 2015-07-18 11:51 | 15100- Expansion Locks Atlantic | Zosimo Correa
00107 |  |  | A-Monte Lirio Haul Road Slope Const | Noncompliance Notice | Closed | Mario L. Montemayor | Quality Mgt Sys | 2011-02-18 | Tamira Baird | 2011-10-14 16:09 | 15100- Expansion Locks Atlantic | Mercedes Peters
00964 |  | MRB7 | NCRP0475CS MRB7 Incorrect Concrete | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2014-12-27 | Luz Arosemena | 2015-03-03 11:18 | 15200- Expansion Locks Pacific | Lorely Rivera
00107 |  |  |  | Corrective Action Request | Void | Antonio González Trell | Construction Deficiency | 2012-01-18 | Juan Rivera | 2013-07-04 12:54 | 00000- Other | Ariel Jaen
00106 |  |  | A-Monte Lirio Disposal | Noncompliance Notice | Closed | Mario L. Montemayor | Quality Mgt Sys | 2011-02-18 | Mario Montemayor | 2011-09-16 09:03 | 15100- Expansion Locks Atlantic | Mercedes Peters
00106 |  |  | GM2501 CAR Gate FAB W/ SUB Shop DWG | Corrective Action Request | Closed | NO BIC-GUPC | Administrative | 2012-01-14 | Alberto Alonzo | 2013-06-03 14:27 | 15000- Expansion Locks | Maria Ho
00978 |  | Backfill LLC Geo | AQ0455 NCR Backfill LLC Geo ins DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-01-02 | Marta Small | 2015-08-28 09:54 | 15100- Expansion Locks Atlantic | Zosimo Correa
00105 |  |  | P-Lack of Impalement Protection | Noncompliance Notice | Closed | Jorge de la Guardia | Safety & Health Issue | 2011-02-17 | Vielka Walters | 2011-06-20 14:01 | 15200- Expansion Locks Pacific | Lorri Cullivan
00980 |  | NCR Upper US Recess | A50M0020 NCR Upper US Recess 1 out | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-01-05 | Marta Small | 2015-08-28 09:51 | 15100- Expansion Locks Atlantic | Zosimo Correa
00105 |  |  | GQ0077 CAR Retention Period of Docs | Corrective Action Request | Closed | No Ball in Court | Administrative | 2011-12-20 | Maria Ho | 2012-10-30 14:32 | 15000- Expansion Locks | Maria Ho
00104 |  |  | A - Foundation Treatment LUC | Noncompliance Notice | Closed | Jose E. Reyes | Quality Mgt Sys | 2011-02-10 | Rick Montanari | 2011-05-04 07:36 | 15100- Expansion Locks Atlantic | Mercedes Peters
00104 |  |  | GE8011 CAR Inductions CIQSA Personl | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2011-09-28 | Tamira Baird | 2015-09-04 15:27 | 15000- Expansion Locks | Eliza Florendo
00979 |  | NCR SSE REC 2 Out | A50M0018 NCR SSE REC 2 Out of Tol | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-01-05 | Marta Small | 2015-08-28 09:53 | 15100- Expansion Locks Atlantic | Zosimo Correa
00103 |  |  | A-Concrete Batch Plant No Env Plan | Noncompliance Notice | Closed | Jose E. Reyes | Environmental Situation | 2011-02-01 | Luis Castaneda | 2011-04-05 16:46 | 15100- Expansion Locks Atlantic | Mercedes Peters
00103 |  |  | PQ0039 CAR Drilling & Blasting | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-01-11 | Luz Arosemena | 2012-08-28 14:22 | 15200- Expansion Locks Pacific | Luz Arosemena
00982 |  | NCR SSE Upper | A50M0022 NCR SSE Upper Recess2 US | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-01-08 | Marta Small | 2015-08-28 09:42 | 15100- Expansion Locks Atlantic | Zosimo Correa
00102 |  |  | A-Slope Stabilization and Cert.Plan | Noncompliance Notice | Closed | Jose E. Reyes | Safety & Health Issue | 2011-01-26 | Mario Montemayor | 2011-07-07 13:50 | 15100- Expansion Locks Atlantic | Mercedes Peters
00102 |  |  | PQ0058 CAR QMS ETF Process AFR 02 | Corrective Action Request | Closed | No Ball in Court | Administrative | 2011-10-27 | Samuel Santamaría | 2012-01-04 14:34 | 15200- Expansion Locks Pacific | Maria Ho
00102 |  |  | AQ0058 CAR Signaling on Field DEF | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-07-19 | Karla Jones | 2012-08-22 09:44 | 00000- Other | Karla Jones
00981 |  | NCR SSE Upper | A50M0021 NCR SSE Upper Recess1 DS | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-01-08 | Zosimo Correa | 2015-02-19 11:22 | 15100- Expansion Locks Atlantic | Zosimo Correa
00101 |  |  | A- Rock Anchor Installation Testing | Noncompliance Notice | Closed | Jose E. Reyes | Quality Mgt Sys | 2011-01-25 | Rick Montanari | 2011-03-24 17:34 | 15100- Expansion Locks Atlantic | Mercedes Peters
00984 |  | NCR RG Upp Rail | A50M0023 NCR RG Upp Rail Plates OTT | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-01-12 | Armando Quintero | 2015-04-18 10:53 | 15100- Expansion Locks Atlantic | Zosimo Correa
00101 |  |  | PQ0057 CAR QMS ETF Process AFR 01 | Corrective Action Request | Closed | No Ball in Court | Administrative | 2011-10-27 | Samuel Santamaría | 2012-01-04 16:34 | 15200- Expansion Locks Pacific | Maria Ho
00100 |  |  | A-Biannual Emergency Drill Practice | Noncompliance Notice | Closed | Jose E. Reyes | Safety & Health Issue | 2011-01-20 | Rick Montanari | 2011-03-24 17:50 | 15100- Expansion Locks Atlantic | Mercedes Peters
00983 |  | Backfill GEO | AQ0456 NCR Backfill GEO inst DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-01-12 | Zosimo Correa | 2015-05-25 10:11 | 15100- Expansion Locks Atlantic | Zosimo Correa
00100 |  |  | AQ0019 CAR Technical Specifications | Corrective Action Request | Closed | No Ball in Court | Administrative | 2011-12-23 | Karla Jones | 2011-12-23 10:27 | 15100- Expansion Locks Atlantic | Karla Jones
00099 |  |  | P-Slope Stability Daily FieldReport | Noncompliance Notice | Closed | Juan H Wong | Construction Deficiency | 2011-01-11 | Vielka Walters | 2011-08-04 11:33 | 15200- Expansion Locks Pacific | Lorri Cullivan
00099 |  |  | AQ0139 CAR QMS failure on INSP | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2011-12-21 | Karla Jones | 2013-03-19 07:31 | 15100- Expansion Locks Atlantic | Karla Jones
00985 |  | UE-M20-W01 | AQ0457 NCR UE-M20-W01 Consol DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-01-15 | Mayra Santos | 2016-03-29 13:06 | 15100- Expansion Locks Atlantic | Zosimo Correa
00098 |  |  | P-SWP Rodman Port Terminal | Noncompliance Notice | Closed | No Ball in Court | Safety & Health Issue | 2011-01-07 | Christopher Claggett | 2011-02-09 14:46 | 15200- Expansion Locks Pacific | Lorri Cullivan
00987 |  | MRB4 Facade | AQ0459 NCR MRB4 Facade Beam Defect | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-01-20 | Marta Small | 2015-08-28 09:29 | 15100- Expansion Locks Atlantic | Zosimo Correa
00098 |  |  | PQ0037 CAR Test Results Reporting | Corrective Action Request | Closed | No Ball in Court | Administrative | 2011-12-16 | Luz Arosemena | 2011-12-16 15:31 | 15200- Expansion Locks Pacific | Luz Arosemena
00097 |  |  | P-Slope Stability Shop Drawings | Noncompliance Notice | Closed | Larry Belken | Construction Deficiency | 2011-01-04 | Vielka Walters | 2011-06-07 14:31 | 15200- Expansion Locks Pacific | Lorri Cullivan
00986 |  | IWW | AQ0458 NCR IWW Backfill DEF | Nonconformance Report | Open | Beltran Valls | Construction Deficiency | 2015-01-20 | Marta Small | 2015-08-28 09:31 | 15100- Expansion Locks Atlantic | Zosimo Correa
00097 |  |  | PQ0035 CAR RFC Drawings | Corrective Action Request | Closed | No Ball in Court | Administrative | 2011-12-16 | Luz Arosemena | 2011-12-16 15:19 | 15200- Expansion Locks Pacific | Luz Arosemena
00096 |  |  | A - Filling Monte Lirio Ponds | Noncompliance Notice | Closed | Jose E. Reyes | Environmental Situation | 2010-12-30 | Rick Montanari | 2011-03-21 16:09 | 15100- Expansion Locks Atlantic | Mercedes Peters
00096 |  |  | PQ0031 CAR Failure Pre-Construction | Corrective Action Request | Closed | No Ball in Court | Administrative | 2011-12-16 | Luz Arosemena | 2011-12-16 15:20 | 15200- Expansion Locks Pacific | Luz Arosemena
00022 |  | NCR Culvert | P55M0044 NCR Culvert V03 Leakage | Nonconformance Report | Closed | Juan Arturo Rivera | Construction Deficiency | 2015-01-21 | Luz Arosemena | 2015-08-18 10:11 | 15200- Expansion Locks Pacific | Luz Arosemena
00095 |  |  | P-Slope Stability Install Rock Bolt | Noncompliance Notice | Closed | Juan H Wong | Quality Mgt Sys | 2010-12-30 | Vielka Walters | 2011-06-22 15:22 | 15200- Expansion Locks Pacific | Lorri Cullivan
00095 |  |  | AQ0019 NCR EXST COND for Bore Holes | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2010-04-16 | Karla Jones | 2013-05-16 10:01 | 15100- Expansion Locks Atlantic | Maria Ho
00095 |  |  | AQ0135 CAR Recurring deficiencies | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-12-13 | Karla Jones | 2013-03-18 16:51 | 15100- Expansion Locks Atlantic | Karla Jones
00094 |  |  | P-Excavation Methodology | Noncompliance Notice | Closed | No Ball in Court | Construction Deficiency | 2010-12-30 | Lorri Cullivan | 2011-01-06 15:50 | 15200- Expansion Locks Pacific | Lorri Cullivan
00094 |  |  | AQ0016 NCR HAZ material storage | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2010-04-16 | Karla Jones | 2011-12-12 15:15 | 15100- Expansion Locks Atlantic | Maria Ho
00094 |  |  | AQ0016 CAR COMM of Works MTE Lirio | Corrective Action Request | Closed | No Ball in Court | Administrative | 2011-12-12 | Karla Jones | 2011-12-12 15:40 | 15100- Expansion Locks Atlantic | Karla Jones
00093 |  |  | P-Slope Stabil -Anchor Steel Mesh | Noncompliance Notice | Closed | Larry Belken | Quality Mgt Sys | 2010-12-30 | Vielka Walters | 2011-06-01 15:52 | 15200- Expansion Locks Pacific | Lorri Cullivan
00093 |  |  | PQ0059 CAR H2E-3C-F04 ICL not sign | Corrective Action Request | Closed | NO BIC-GUPC | Contract Term | 2011-11-29 | Veronica Cash | 2013-08-27 15:55 | 15200- Expansion Locks Pacific | Luz Arosemena
00991 |  | NCR RG03 Gate B300 | A50M0026 NCR RG03 Gate B300 Hit CON | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-01-26 | Jose Dorantes | 2016-04-16 10:48 | 15100- Expansion Locks Atlantic | Zosimo Correa
00092 |  |  | P-Slope Stabil Shotcrete Weepholes | Noncompliance Notice | Closed | Larry Belken | Quality Mgt Sys | 2010-12-30 | Vielka Walters | 2011-06-07 14:24 | 15200- Expansion Locks Pacific | Lorri Cullivan
00990 |  | NCR LH3 Tensioning | A50M0025 NCR LH3 Tensioning SYS DAM | Nonconformance Report | Open | Ramon Porcell | Defective Materials | 2015-01-26 | Maylin Moreno | 2016-02-17 10:29 | 15100- Expansion Locks Atlantic | Zosimo Correa
00092 |  |  | PQ0061 CAR NCR Process Review | Corrective Action Request | Closed | NO BIC-GUPC | Administrative | 2011-11-24 | Veronica Cash | 2013-08-27 15:59 | 15200- Expansion Locks Pacific | Luz Arosemena
00091 |  |  | P-SlopeProtection NCR Failure | Noncompliance Notice | Closed | Juan H Wong | Quality Mgt Sys | 2010-12-29 | Vielka Walters | 2011-07-22 15:27 | 15200- Expansion Locks Pacific | Lorri Cullivan
00091 |  |  | AQ0138 CAR NCR Process Review | Corrective Action Request | Closed | No Ball in Court | Administrative | 2011-11-17 | Karla Jones | 2011-12-30 15:15 | 15100- Expansion Locks Atlantic | Maria Ho
00989 |  | NCR REC 3&4 UW | A50M0019 NCR REC 3&4 UW Connec pins | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-01-26 | Jose Dorantes | 2016-04-16 10:31 | 15100- Expansion Locks Atlantic | Zosimo Correa
00090 |  |  | A-Unprotected Edge LUC Excavation | Noncompliance Notice | Closed | Jorge de la Guardia | Safety & Health Issue | 2010-12-29 | Mario Montemayor | 2011-05-19 07:24 | 15100- Expansion Locks Atlantic | Lorri Cullivan
00090 |  |  | PQ0060 CAR Lack Implementation QMS | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2011-11-18 | Veronica Cash | 2013-08-27 15:48 | 15200- Expansion Locks Pacific | Luz Arosemena
00988 |  | NCR REC 6 UW | A50M0024 NCR REC 6 UW Rail Cleaners | Nonconformance Report | Open | Jose Dorantes | Construction Deficiency | 2015-01-26 | Ramon Porcell | 2015-11-23 12:04 | 15100- Expansion Locks Atlantic | Zosimo Correa
00089 |  |  | P-Non Spec Material Locks Slopes | Noncompliance Notice | Closed | Larry Belken | Quality Mgt Sys | 2010-12-22 | Vielka Walters | 2011-06-07 14:00 | 15200- Expansion Locks Pacific | Melanie Sanmartin
00089 |  |  | AQ0137 CAR HANDL & STOR of CONC MAT | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2011-11-15 | Veronica Cash | 2013-08-27 15:51 | 15100- Expansion Locks Atlantic | Karla Jones
00992 |  | LWSB | AQ0461 NCR LWSB Sub&Under CONT | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-01-27 | Marta Small | 2015-08-28 09:26 | 15100- Expansion Locks Atlantic | Zosimo Correa
00088 |  |  | P-Dewat Syst in the Locks Chbr Exc | Noncompliance Notice | Closed | Javier Gutierrez | Construction Deficiency | 2010-12-21 | Rick Montanari | 2011-08-19 19:43 | 15200- Expansion Locks Pacific | Melanie Sanmartin
00088 |  |  | AQ0134 CAR QMS ETF Process | Corrective Action Request | Closed | No Ball in Court | Administrative | 2011-11-14 | Karla Jones | 2011-12-21 15:26 | 15100- Expansion Locks Atlantic | Karla Jones
00993 |  | APP | NCRP0472CS APP-IW-P01a | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2015-02-05 | Lorely Rivera | 2015-08-07 08:22 | 15200- Expansion Locks Pacific | Lorely Rivera
00087 |  |  | A - Surface Water Control & Manage | Noncompliance Notice | Closed | Jose E. Reyes | Construction Deficiency | 2010-12-17 | Javier Gutierrez | 2012-07-31 07:39 | 15100- Expansion Locks Atlantic | Mercedes Peters
00087 |  |  | GQ0076 CAR Vendor´S Shop Drawings | Corrective Action Request | Closed | No Ball in Court | Administrative | 2011-10-29 | Maria Ho | 2012-01-26 12:15 | 15000- Expansion Locks | Maria Ho
00087 |  |  | AQ0012 NCR Waste Water Treatment | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2010-11-19 | Karla Jones | 2011-09-07 15:29 | 15100- Expansion Locks Atlantic | Maria Ho
00086 |  |  | P-Use of Victoria Disposal Site | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-11-26 | Lorri Cullivan | 2010-12-28 11:50 | 15200- Expansion Locks Pacific | Lorri Cullivan
00086 |  |  | AQ0010 NCR Handling of Aggregates | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2010-08-13 | Karla Jones | 2011-09-07 15:28 | 15100- Expansion Locks Atlantic | Maria Ho
00086 |  |  | AE8022 CAR Lack of waste management | Corrective Action Request | Closed | No Ball in Court | Field Conditions | 2011-10-21 | Tamira Baird | 2015-09-04 15:23 | 15100- Expansion Locks Atlantic | Abed Camarena
00085 |  |  | P-PPE Use | Noncompliance Notice | Closed | No Ball in Court | Safety & Health Issue | 2010-11-02 | Christopher Claggett | 2011-04-26 14:26 | 15200- Expansion Locks Pacific | Vielka Walters
00995 |  | NCR Crossunder 2 | A67M0002 NCR Crossunder 2 FPW DEF | Nonconformance Report | Open | Beltran Valls | Construction Deficiency | 2015-02-06 | Marta Small | 2015-08-28 09:25 | 15100- Expansion Locks Atlantic | Zosimo Correa
00085 |  |  | GQ0075 CAR QMS Deficiency | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-10-19 | Maria Ho | 2012-02-28 17:14 | 15000- Expansion Locks | Maria Ho
00084 |  |  | A-Cut & Clearing Trees Beyond Limit | Noncompliance Notice | Closed | Jose E. Reyes | Environmental Situation | 2010-11-01 | Rick Montanari | 2011-03-04 15:45 | 15100- Expansion Locks Atlantic | Tamira Baird
00084 |  |  | AE8023 CAR Lack of maintenance pits | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2011-10-20 | Tamira Baird | 2015-09-04 15:24 | 15100- Expansion Locks Atlantic | Abed Camarena
00994 |  | NCR Crossunder 2 | A66M0002 NCR Crossunder 2 PDW DEF | Nonconformance Report | Open | Ramon Porcell | Construction Deficiency | 2015-02-06 | Gene Williams | 2015-05-04 10:07 | 15100- Expansion Locks Atlantic | Zosimo Correa
00083 |  |  | A-ACP Notific Lack Key GUPC Pers | Noncompliance Notice | Closed | No Ball in Court | Safety & Health Issue | 2010-10-27 | Lorri Cullivan | 2010-12-28 11:53 | 15100- Expansion Locks Atlantic | Maureen White
00996 |  | NCR Fire | A67M0001 NCR Fire Pump1 Damaged | Nonconformance Report | Closed | No Ball in Court | Other | 2015-02-11 | Zosimo Correa | 2015-07-13 15:59 | 15100- Expansion Locks Atlantic | Zosimo Correa
00083 |  |  | GQ0074 CAR DSGN CALC & DRW Control | Corrective Action Request | Closed | No Ball in Court | Administrative | 2011-10-13 | Maria Ho | 2012-03-28 14:28 | 15004- Expansion Locks Design | Maria Ho
00082 |  |  | P-Sedimentation Erosion Ctrl Disp 1 | Noncompliance Notice | Closed | No Ball in Court | Environmental Situation | 2010-10-21 | Lorri Cullivan | 2011-01-11 10:12 | 15200- Expansion Locks Pacific | Vielka Walters
00082 |  |  | AQ0133 CAR Lack o Comm Bet | Corrective Action Request | Closed | No Ball in Court | Planned | 2011-10-14 | Karla Jones | 2013-03-18 16:01 | 15100- Expansion Locks Atlantic | Karla Jones
00967 |  | WSB-LMC-T4 | NCRP0473CS WSB-LMC-T4 Pipes Rework | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-02-13 | Luz Arosemena | 2015-05-04 16:43 | 15200- Expansion Locks Pacific | Lorely Rivera
00081 |  |  | P-Spills in the workshop area | Noncompliance Notice | Closed | No Ball in Court | Environmental Situation | 2010-10-18 | Lorri Cullivan | 2010-12-28 11:55 | 15200- Expansion Locks Pacific | Vielka Walters
00081 |  |  | AQ0132 CAR CU1-1W-03b & CC1-L-03 ar | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2011-10-11 | Karla Jones | 2013-03-18 15:26 | 15100- Expansion Locks Atlantic | Karla Jones
00997 |  | CB-08-CWa | NCRP0477CS CB-08-CWa Concrete Place | Nonconformance Report | Closed | Juan Arturo Rivera | Construction Deficiency | 2015-02-18 | Lorely Rivera | 2015-07-09 11:57 | 15200- Expansion Locks Pacific | Luz Arosemena
00080 |  |  | P-Brujas Road Damage | Noncompliance Notice | Closed | Larry Belken | Contract Term | 2010-10-15 | Lorri Cullivan | 2011-04-06 15:20 | 15200- Expansion Locks Pacific | Vielka Walters
00998 |  | MRB3 & 4 | NCRP0476CS MRB3 & 4 Concrete Placem | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-02-27 | Luz Arosemena | 2015-05-02 11:23 | 15200- Expansion Locks Pacific | Luz Arosemena
00080 |  |  | PQ0055 CAR HOLD of Defective Works | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-10-11 | Luz Arosemena | 2012-05-04 14:48 | 15200- Expansion Locks Pacific | Luz Arosemena
00079 |  |  | A-Mandatory PPE the Job Site | Noncompliance Notice | Closed | Bernardo Gonzalez | Safety & Health Issue | 2010-10-15 | Lorri Cullivan | 2011-04-27 15:16 | 15100- Expansion Locks Atlantic | Maureen White
01000 |  | NCR Sheaves RG 8 | A50M0029 NCR Sheaves RG 8 US OUT | Nonconformance Report | Open | Ramon Porcell | Construction Deficiency | 2015-03-06 | Zosimo Correa | 2015-09-01 11:26 | 15100- Expansion Locks Atlantic | Zosimo Correa
00079 |  |  | GQ0073 CAR APPX PROC NOT PROR CODE | Corrective Action Request | Closed | No Ball in Court | Administrative | 2011-09-29 | Maria Ho | 2012-02-28 17:04 | 15000- Expansion Locks | Maria Ho
00078 |  |  | P-Violation of Safety perimeter | Noncompliance Notice | Closed | No Ball in Court | Safety & Health Issue | 2010-10-15 | Christopher Claggett | 2011-02-09 14:47 | 15200- Expansion Locks Pacific | Vielka Walters
00999 |  | NCR MRB4 RG 7&8 | A50M0028 NCR MRB4 RG 7&8 winch out | Nonconformance Report | Open | Ramon Porcell | Construction Deficiency | 2015-03-06 | Zosimo Correa | 2015-08-31 11:12 | 15100- Expansion Locks Atlantic | Zosimo Correa
00078 |  |  | AQ0131 CAR Deployment of ICL & TSC | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-09-09 | Karla Jones | 2012-11-01 14:32 | 15100- Expansion Locks Atlantic | Maria Ho
00077 |  |  | P-Sediments from dewatering of 1939 | Noncompliance Notice | Closed | No Ball in Court | Environmental Situation | 2010-10-14 | Gonzalo Menendez | 2011-01-18 12:35 | 15200- Expansion Locks Pacific | Vielka Walters
01002 |  | SMC A11P | AQ0462 NCR SMC A11P Low Strenght | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2015-03-11 | Abdiel Santos | 2016-12-05 15:15 | 15100- Expansion Locks Atlantic | Zosimo Correa
00077 |  |  | AQ0020 CAR No Rel of Drawings | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-04-16 | Maria Ho | 2011-09-07 12:28 | 15100- Expansion Locks Atlantic | Maria Ho
00076 |  |  | P-Compliance Explosive Material | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-10-12 | Cecilia Ung | 2010-12-28 16:25 | 15200- Expansion Locks Pacific | Vielka Walters
00076 |  |  | AQ0015 CAR Prep. Meeting Cofferdam | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-04-13 | Maria Ho | 2011-09-07 11:38 | 15100- Expansion Locks Atlantic | Maria Ho
01001 |  | SMC A3P | AQ0460 NCR SMC A3P Low Strenght | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2015-03-11 | Abdiel Santos | 2016-12-05 15:10 | 15100- Expansion Locks Atlantic | Zosimo Correa
00075 |  |  | P-Explosive Procedure Delays | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-10-12 | Lorri Cullivan | 2011-01-07 08:25 | 15200- Expansion Locks Pacific | Vielka Walters
00075 |  |  | AQ0002 NCR Protect of Elect Utility | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2010-04-13 | Karla Jones | 2011-09-07 15:18 | 15100- Expansion Locks Atlantic | Karla Jones
00075 |  |  | AQ0014 CAR No Lic Nuclear Training | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-04-13 | Maria Ho | 2012-08-09 15:15 | 15100- Expansion Locks Atlantic | Maria Ho
00074 |  |  | P-WIR Procedures | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-10-11 | Samuel Santamaría | 2011-02-07 14:39 | 15200- Expansion Locks Pacific | Vielka Walters
01003 |  | NCR RG2 End Stop | A50M0027 NCR RG2 End Stop Out TOL | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2015-03-13 | Zosimo Correa | 2015-05-20 10:36 | 15100- Expansion Locks Atlantic | Zosimo Correa
00074 |  |  | AQ0013 CAR Work Proceed No Re Sub | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-04-13 | Maria Ho | 2011-09-07 09:57 | 15100- Expansion Locks Atlantic | Maria Ho
00073 |  |  | P-Final Excavation Design Submittal | Noncompliance Notice | Closed | Samuel Cohen | Quality Mgt Sys | 2010-10-11 | Vielka Walters | 2011-07-20 11:27 | 15200- Expansion Locks Pacific | Vielka Walters
01006 |  | NCR RG2 PIPING | A55M0020 NCR RG2 PIPING SYS DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-03-17 | Marta Small | 2015-08-28 08:09 | 15100- Expansion Locks Atlantic | Zosimo Correa
00073 |  |  | PQ0052 CAR Handling of Concrete Mat | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2011-09-02 | Veronica Cash | 2013-08-27 15:44 | 15200- Expansion Locks Pacific | Luz Arosemena
00072 |  |  | P-Lack of Berms/Edge Protection | Noncompliance Notice | Closed | No Ball in Court | Unsafe conditions | 2010-10-07 | Christopher Claggett | 2011-04-26 14:05 | 15200- Expansion Locks Pacific | Vielka Walters
00072 |  |  | AQ0130 CAR Handl_Storage A-21-AUR02 | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-09-02 | Karla Jones | 2011-11-07 10:33 | 15100- Expansion Locks Atlantic | Karla Jones
01005 |  | UWSB-BRP-16 Road | AQ0465 NCR UWSB-BRP-16 Road lev DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-03-17 | Mayra Santos | 2016-05-14 11:14 | 15100- Expansion Locks Atlantic | Zosimo Correa
00071 |  |  | P-Quality Assurance Audit Followup | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-09-30 | Lorri Cullivan | 2011-01-11 07:38 | 15200- Expansion Locks Pacific | Vielka Walters
00071 |  |  | AQ0129 CAR Handl Storage A21 AUR1 | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2011-09-02 | Karla Jones | 2011-11-07 15:20 | 15100- Expansion Locks Atlantic | Karla Jones
01004 |  | MRB3 HPU conduits | AQ0463 NCR MRB3 HPU conduits not in | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-03-17 | Armando Quintero | 2016-05-18 11:37 | 15100- Expansion Locks Atlantic | Zosimo Correa
00070 |  |  | P-Failure to Implement Ctrl of NCR | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-09-28 | Larry Ohrn | 2011-04-07 07:54 | 15200- Expansion Locks Pacific | Vielka Walters
00070 |  |  | AQ0128 CAR A-ER Audit-Handl_Storage | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2011-09-02 | Karla Jones | 2012-11-14 10:54 | 15100- Expansion Locks Atlantic | Karla Jones
01011 |  | NCR Top | P55M0046 NCR Top Seal V274P | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2015-03-25 | Lorely Rivera | 2015-10-23 08:36 | 15200- Expansion Locks Pacific | Luz Arosemena
00069 |  |  | P-Disposal Site Camp Rousseau | Noncompliance Notice | Closed | Juan H Wong | Environmental Situation | 2010-09-27 | Vielka Walters | 2011-02-18 11:05 | 15200- Expansion Locks Pacific | Vielka Walters
00069 |  |  | PQ0054 CAR - Fall Line Admixtures | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2011-09-01 | Veronica Cash | 2013-08-27 15:45 | 15200- Expansion Locks Pacific | Luz Arosemena
00023 |  | NCR Lintel | P55M0045 NCR Lintel V05 deviation | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2015-03-25 | Lorely Rivera | 2015-04-07 14:37 | 15200- Expansion Locks Pacific | Luz Arosemena
00068 |  |  | G- Employee Transportation Plan | Noncompliance Notice | Closed | No Ball in Court | Environmental Situation | 2010-09-23 | María Ayala | 2011-03-23 13:57 | 15000- Expansion Locks | Gladys Arias
01007 |  | AR Mid East M10 | AQ0466 NCR AR Mid East M10@15 Crack | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-03-26 | Mayra Santos | 2016-03-09 09:19 | 15100- Expansion Locks Atlantic | Zosimo Correa
00068 |  |  | AQ0127 CAR Lack of Calibration | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-08-16 | Maria Ho | 2011-09-06 14:08 | 15100- Expansion Locks Atlantic | Maria Ho
00067 |  |  | A - Failure Monitor Veh Emission | Noncompliance Notice | Closed | Jose E. Reyes | Environmental Situation | 2010-09-23 | Jose Reyes | 2011-02-04 08:26 | 15100- Expansion Locks Atlantic | Maureen White
00067 |  |  | AQ0125 CAR Cold Joints - SF-2H & 4C | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-08-11 | Karla Jones | 2012-08-10 08:35 | 15100- Expansion Locks Atlantic | Zosimo Correa
01013 |  | NCR Painting DEF | A50M0036 NCR Painting DEF Gate D8 | Nonconformance Report | Open | Ramon Porcell | Construction Deficiency | 2015-03-27 | Larry Ohrn | 2015-06-09 07:44 | 15100- Expansion Locks Atlantic | Zosimo Correa
00066 |  |  | A - Failed to Comply Precon Meet | Noncompliance Notice | Closed | Jose E. Reyes | Quality Mgt Sys | 2010-09-15 | Rick Montanari | 2011-01-04 13:42 | 15100- Expansion Locks Atlantic | Maureen White
00066 |  |  | GQ0070 CAR Personnel Contact List | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2011-06-06 | Miguel Tome | 2011-08-17 14:11 | 15000- Expansion Locks | Maria Ho
01012 |  | NCR Painting DEF | A50M0035 NCR Painting DEF Gate B6 | Nonconformance Report | Open | Ramon Porcell | Construction Deficiency | 2015-03-27 | Larry Ohrn | 2015-06-09 07:46 | 15100- Expansion Locks Atlantic | Zosimo Correa
00065 |  |  | A - Failure to Provide Proper WIR | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-09-01 | Lorri Cullivan | 2010-12-28 12:03 | 15100- Expansion Locks Atlantic | Mario Montemayor
00065 |  |  | AQ0008 CAR Field Daily Rept. Compl. | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-04-03 | Maria Ho | 2012-08-21 09:13 | 15100- Expansion Locks Atlantic | Karla Jones
01011 |  | NCR Painting DEF | A50M0034 NCR Painting DEF Gate B5 | Nonconformance Report | Open | Ramon Porcell | Construction Deficiency | 2015-03-27 | Larry Ohrn | 2015-06-09 07:50 | 15100- Expansion Locks Atlantic | Zosimo Correa
00064 |  |  | A - Erosion Control Monte Lirio Rd | Noncompliance Notice | Closed | Jose E. Reyes | Environmental Situation | 2010-08-20 | Javier Gutierrez | 2011-05-21 09:50 | 15100- Expansion Locks Atlantic | Maureen White
00064 |  |  | AQ0003 CAR CALIBRATION CERTIFICATE | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-02-24 | Miguel Tome | 2011-08-17 14:43 | 15100- Expansion Locks Atlantic | Maria Ho
01010 |  | NCR Painting DEF | A50M0033 NCR Painting DEF Gate B4 | Nonconformance Report | Open | Ramon Porcell | Construction Deficiency | 2015-03-27 | Larry Ohrn | 2015-06-09 07:56 | 15100- Expansion Locks Atlantic | Zosimo Correa
00063 |  |  | G - Subcontractors’ Staff Min Wage | Noncompliance Notice | Closed | No Ball in Court | Contract Term | 2010-08-16 | Lorri Cullivan | 2010-12-28 12:04 | 15000- Expansion Locks | Gladys Arias
00063 |  |  | PE8004 CAR Data for Landslide Analy | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-10-04 | Eliza Florendo | 2012-05-21 08:12 | 15200- Expansion Locks Pacific | Eliza Florendo
01009 |  | NCR Painting DEF | A50M0032 NCR Painting DEF Gate B3 | Nonconformance Report | Open | Ramon Porcell | Construction Deficiency | 2015-03-27 | Larry Ohrn | 2015-06-09 07:50 | 15100- Expansion Locks Atlantic | Zosimo Correa
00062 |  |  | P - Drilling and Blasting | Noncompliance Notice | Closed | No Ball in Court | Construction Deficiency | 2010-08-06 | Lorri Cullivan | 2010-12-28 12:33 | 15200- Expansion Locks Pacific | Vielka Walters
01008 |  | NCR Painting DEF | A50M0031 NCR Painting DEF Gate A2 | Nonconformance Report | Open | Ramon Porcell | Defective Materials | 2015-03-27 | Larry Ohrn | 2015-06-09 07:51 | 15100- Expansion Locks Atlantic | Zosimo Correa
00062 |  |  | AE8003 CAR Data for Landslide Analy | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-10-04 | Eliza Florendo | 2012-05-21 08:12 | 15100- Expansion Locks Atlantic | Eliza Florendo
00061 |  |  | A-Lack of Fire Protect and Prevent | Noncompliance Notice | Closed | Jose E. Reyes | Safety & Health Issue | 2010-08-03 | Samuel Santamaría | 2011-03-29 11:53 | 15100- Expansion Locks Atlantic | Maureen White
00061 |  |  | AE8002 CAR Communicate PM10 Result | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-10-04 | Tamira Baird | 2015-09-04 15:24 | 15100- Expansion Locks Atlantic | Eliza Florendo
01014 |  | MRB6 Elec | AQ0472 NCR MRB6 Elec Room topping | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-04-04 | Marta Small | 2015-08-28 08:04 | 15100- Expansion Locks Atlantic | Zosimo Correa
00060 |  |  | D - Audit DQP Holland 21Jul10(2) | Noncompliance Notice | Closed | John Lopacki | Quality Mgt Sys | 2010-08-02 | Lorri Cullivan | 2010-12-28 12:04 | 15004- Expansion Locks Design | Vielka Walters
01017 |  | NCR Painting DEF | A50M0037 NCR Painting DEF Gate D7 | Nonconformance Report | Open | Ramon Porcell | Construction Deficiency | 2015-04-06 | Larry Ohrn | 2015-07-09 10:13 | 15100- Expansion Locks Atlantic | Zosimo Correa
00060 |  |  | PE8002 CAR Spill Response Procedure | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-11-09 | Eliza Florendo | 2012-05-21 08:11 | 15200- Expansion Locks Pacific | Eliza Florendo
00059 |  |  | D - Audit DQP Holland 21Jul10(1) | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-08-02 | Lorri Cullivan | 2010-12-28 12:04 | 15004- Expansion Locks Design | Vielka Walters
00059 |  |  | PE8001 CAR Inadequate Sediment Cont | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-10-20 | Eliza Florendo | 2012-05-21 08:10 | 15200- Expansion Locks Pacific | Eliza Florendo
01016 |  | MRB6 Steel | AQ0473 NCR MRB6 Steel Structure DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-04-06 | Mayra Santos | 2016-05-14 11:30 | 15100- Expansion Locks Atlantic | Zosimo Correa
00058 |  |  | P - East West Cofferdams | Noncompliance Notice | Closed | Samuel Cohen | Quality Mgt Sys | 2010-08-02 | Lorri Cullivan | 2010-12-28 12:04 | 15200- Expansion Locks Pacific | Vielka Walters
00058 |  |  | PQ0051 CAR COCOLI RIVER CROSSING | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-07-14 | Luz Arosemena | 2011-12-16 15:47 | 15200- Expansion Locks Pacific | Luz Arosemena
01015 |  | CB Steel Struc | AQ0467 NCR CB Steel Struc Paint DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-04-06 | Abdiel Santos | 2016-12-07 09:27 | 15100- Expansion Locks Atlantic | Zosimo Correa
00057 |  |  | A-Excavation Works East Side Exca | Noncompliance Notice | Closed | Jose E. Reyes | Construction Deficiency | 2010-07-30 | Rick Montanari | 2011-01-04 13:44 | 15100- Expansion Locks Atlantic | Maureen White
00057 |  |  | PE8000 CAR NCN0069 | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-10-25 | Eliza Florendo | 2012-05-21 08:10 | 15200- Expansion Locks Pacific | Eliza Florendo
00001 |  | NCR SAR | G66M0001 NCR SAR Support Def | Nonconformance Report | Closed | Nelson Umana | Errors and Omissions | 2015-04-06 | Roberto Barrios | 2015-07-13 17:16 | 15200- Expansion Locks Pacific | Carlos Dominguez
00056 |  |  | A- Dock 45 West Start Work | Noncompliance Notice | Closed | Jose E. Reyes | Construction Deficiency | 2010-07-30 | Rick Montanari | 2011-01-04 13:40 | 15100- Expansion Locks Atlantic | Maureen White
00056 |  |  | AE8001 CAR Approved Plans to Suncon | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-10-04 | Graciela Palacios | 2012-10-10 13:53 | 15100- Expansion Locks Atlantic | Eliza Florendo
00056 |  |  | P00UPCCAR5047 | Corrective Action Request | New Item | Ernesto Hugues |  | 2013-12-30 | Gene Williams | 2015-09-04 15:18 | 15200- Expansion Locks Pacific | Ariel Soto
01018 |  | APP-IW-Pile | NCRP0478CS APP-IW-Pile P04 Deviated | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2015-04-08 | Luz Arosemena | 2015-06-03 11:58 | 15200- Expansion Locks Pacific | Lorely Rivera
00055 |  |  | D - Audit Design Chicago Follow up | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-07-26 | John Lopacki | 2011-03-18 15:53 | 15004- Expansion Locks Design | Lorri Cullivan
00055 |  |  | A00/UPCCAR5017 | Corrective Action Request | Closed | Jose Ventocilla | Safety & Health Issue | 2011-09-25 | Gene Williams | 2015-09-04 15:15 | 15100- Expansion Locks Atlantic | Jianey Abrahams
00055 |  |  | PQ0014 NCR Slope Stability System | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-03-12 | Mario Simoes | 2011-08-16 13:54 | 15200- Expansion Locks Pacific | Maria Ho
00055 |  |  | AE8000 CAR GUPC Subcontractor Audit | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-10-04 | Eliza Florendo | 2011-08-11 11:31 | 15100- Expansion Locks Atlantic | Eliza Florendo
00054 |  |  | G-InsurancePolicies | Noncompliance Notice | Closed | No Ball in Court | Administrative | 2010-07-20 | Lorri Cullivan | 2010-12-28 12:08 | 15000- Expansion Locks | Vielka Walters
00054 |  |  | A00/UPCCAR5016 | Corrective Action Request | Closed | Jose Ventocilla |  | 2012-02-01 | Tammie Stover | 2015-07-08 10:48 | 15100- Expansion Locks Atlantic | Jianey Abrahams
00054 |  |  | AQ0023 NCR FNDTN TRTM Lean Concrete | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-02-26 | Karla Jones | 2011-09-01 15:37 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00054 |  |  | PE8003 CAR GUPC Subcontractor Audit | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-10-04 | Eliza Florendo | 2012-05-21 08:09 | 15200- Expansion Locks Pacific | Eliza Florendo
00053 |  |  | P - Disposal Site #1 | Noncompliance Notice | Closed | Jose Luis Olivan | Quality Mgt Sys | 2010-07-15 | Vielka Walters | 2011-02-22 10:03 | 15200- Expansion Locks Pacific | Vielka Walters
00053 |  |  | PQ0006 NCR Permanent Disposal | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2010-10-08 | Mario Simoes | 2011-08-16 13:19 | 15200- Expansion Locks Pacific | Maria Ho
00053 |  |  | VOID | Corrective Action Request | Void | Miguel Tome |  |  | Maria Ho | 2011-05-31 13:19 |  | Miguel Tome
00053 |  |  | PQ0050 CAR CONCRETE VIBRATION | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2011-07-11 | Luz Arosemena | 2011-12-16 15:46 | 15200- Expansion Locks Pacific | Luz Arosemena
00052 |  |  | P - Monitoring Activities | Noncompliance Notice | Closed | No Ball in Court | Environmental Situation | 2010-07-14 | Lorri Cullivan | 2010-12-28 12:08 | 15200- Expansion Locks Pacific | Vielka Walters
00052 |  |  | VOID | Corrective Action Request | Void | Miguel Tome |  |  | Miguel Tome | 2011-04-14 13:53 |  | Miguel Tome
00052 |  |  | PQ0015 NCR Slope Stability Syst | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2010-12-17 | Mario Simoes | 2011-08-16 13:55 | 15200- Expansion Locks Pacific | Maria Ho
00052 |  |  | AE8011 CAR Storage&Training Extingu | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2011-07-08 | Eliza Florendo | 2011-08-11 11:38 | 15100- Expansion Locks Atlantic | Eliza Florendo
00051 |  |  | PQ0020 NCR Miraflores Cofferdam | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-01-25 | Luz Arosemena | 2012-08-28 13:45 | 15200- Expansion Locks Pacific | Maria Ho
00051 |  |  | P - Technical Specifications | Noncompliance Notice | Closed | No Ball in Court | Administrative | 2010-07-12 | Lorri Cullivan | 2010-12-28 12:08 | 15200- Expansion Locks Pacific | Vielka Walters
00051 |  |  | GQ0055 CAR Audit DQP Bellevue | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-10-18 | Miguel Tome | 2011-08-17 10:35 | 15000- Expansion Locks | Miguel Tome
00051 |  |  | AE8010 CAR Solid Waste Management | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-10-22 | Eliza Florendo | 2011-08-11 11:36 | 15100- Expansion Locks Atlantic | Eliza Florendo
00050 |  |  | PQ0004 NCR M.O. & Parking Area | Nonconformance Report | Closed | Antonio Betti | Quality Mgt Sys | 2010-09-11 | Maria Ho | 2011-06-01 10:31 | 15200- Expansion Locks Pacific | Maria Ho
00050 |  |  | GQ0054 CAR SCTR Staff Min Wage | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-09-01 | Miguel Tome | 2011-08-17 10:36 | 15000- Expansion Locks | Miguel Tome
00050 |  |  | A - Erosion at Grid E4 | Noncompliance Notice | Closed | Jose E. Reyes | Environmental Situation | 2010-07-09 | Rick Montanari | 2011-03-04 14:08 | 15100- Expansion Locks Atlantic | Maureen White
00050 |  |  | PQ0049 CAR F. TREATMENT MW-M9 | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2011-07-07 | Javier Gutierrez | 2012-01-10 11:41 | 15200- Expansion Locks Pacific | Luz Arosemena
00049 |  |  | GQ0053 CAR Audit DQP Holland 4 | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-08-09 | Miguel Tome | 2011-08-17 10:40 | 15000- Expansion Locks | Miguel Tome
00049 |  |  | PQ0013 NCR EXC & Overburden RMV | Nonconformance Report | Closed | Antonio Betti | Construction Deficiency | 2010-12-03 | Maria Ho | 2011-06-08 09:14 | 15200- Expansion Locks Pacific | Maria Ho
00049 |  |  | A - Audit Design Quality Plan | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-07-05 | Lorri Cullivan | 2010-12-28 12:10 | 15100- Expansion Locks Atlantic | McLaren Brennan
00049 |  |  | PQ0048 CAR 1939 FILL - ZONE 3 | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-07-07 | Javier Gutierrez | 2012-01-10 11:39 | 15200- Expansion Locks Pacific | Luz Arosemena
00048 |  |  | PQ0008 NCR Basalt Stockpile Area | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2010-11-15 | Luz Arosemena | 2012-05-09 16:34 | 15200- Expansion Locks Pacific | Maria Ho
00048 |  |  | GQ0052 CAR Audit DQO Holland 3 | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-08-09 | Miguel Tome | 2011-08-17 10:43 | 15000- Expansion Locks | Miguel Tome
00048 |  |  | P - Audit QC Plan Implementation | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-06-29 | Lorri Cullivan | 2010-12-28 12:10 | 15200- Expansion Locks Pacific | Vielka Walters
00048 |  |  | PE8012 CAR Used Explosive Disposal | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-10-27 | Eliza Florendo | 2012-05-21 08:08 | 15200- Expansion Locks Pacific | Eliza Florendo
00047 |  |  | GQ0051 CAR Audit DQP Holland 2 | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-08-09 | Miguel Tome | 2011-08-17 10:44 | 15000- Expansion Locks | Miguel Tome
00047 |  |  | P - Audit QMS Implementation | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-06-29 | Lorri Cullivan | 2010-12-28 12:11 | 15200- Expansion Locks Pacific | Vielka Walters
00047 |  |  | PQ0035 NCR PERM Disposals Drainage | Nonconformance Report | Closed | Jorge Perez Blanco | Construction Deficiency | 2011-05-24 | Javier Gutierrez | 2012-07-10 08:32 | 15200- Expansion Locks Pacific | Maria Ho
00047 |  |  | PQ0036 CAR MIRAFLORES COFFERDAM | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2011-06-28 | Veronica Cash | 2013-08-27 15:46 | 15200- Expansion Locks Pacific | Luz Arosemena
00046 |  |  | GQ0050 CAR Audit DQP Holland | Corrective Action Request | Closed | No Ball in Court | Errors and Omissions | 2010-08-09 | Maria Ho | 2012-06-06 10:41 | 15000- Expansion Locks | Miguel Tome
00046 |  |  | G - Maintain Submittal Register PCM | Noncompliance Notice | Closed | No Ball in Court | Administrative | 2010-06-28 | Lorri Cullivan | 2010-12-28 12:11 | 15000- Expansion Locks | McLaren Brennan
00046 |  |  | PQ0034 NCR 2nd SUPPLY REINF. REBARS | Nonconformance Report | Closed | Javier Gutierrez | Quality Mgt Sys | 2011-05-20 | Veronica Cash | 2013-08-28 08:35 | 15200- Expansion Locks Pacific | Maria Ho
00046 |  |  | PQ0047 CAR WIR PROCESS | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-06-23 | Luz Arosemena | 2011-12-16 15:43 | 15200- Expansion Locks Pacific | Luz Arosemena
00045 |  |  | A -Lack Soil Protection Jan de Nul | Noncompliance Notice | Closed | No Ball in Court | Environmental Situation | 2010-06-21 | Lorri Cullivan | 2010-12-28 12:11 | 15100- Expansion Locks Atlantic | Rick Montanari
00045 |  |  | GQ0049 CAR Implement DQP A13 AFR 09 | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-08-13 | Miguel Tome | 2011-08-17 10:45 | 15000- Expansion Locks | Miguel Tome
00045 |  |  | PQ0033 NCR Reinfo Steel Order PAC 1 | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-05-20 | Javier Gutierrez | 2011-08-10 08:03 | 15200- Expansion Locks Pacific | Maria Ho
00045 |  |  | PQ0046 CAR PREP. DOCUMENTS RESUBMIT | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-06-23 | Luz Arosemena | 2012-11-16 10:37 | 15200- Expansion Locks Pacific | Luz Arosemena
00044 |  |  | GQ0048 CAR Implement DQP A13 AFR 08 | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-08-13 | Miguel Tome | 2011-08-17 10:47 | 15000- Expansion Locks | Miguel Tome
00044 |  |  | G- Health and Safety Bulletin Board | Noncompliance Notice | Closed | No Ball in Court | Safety & Health Issue | 2010-06-18 | Lorri Cullivan | 2010-12-28 12:11 | 15000- Expansion Locks | Vielka Walters
00044 |  |  | PQ0023 NCR 1st SUPPLY REINF. REBARS | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-05-30 | Javier Gutierrez | 2011-08-10 07:41 | 15200- Expansion Locks Pacific | Maria Ho
00044 |  |  | PQ0045 CAR 24 Inch Water Line | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2011-06-15 | Luz Arosemena | 2011-12-16 15:39 | 15200- Expansion Locks Pacific | Luz Arosemena
00043 |  |  | AE0027 NCR Hazardous Material Handl | Nonconformance Report | Void | Jeronimo Gutierrez |  | 2011-05-28 | Abed Camarena | 2011-06-06 15:10 |  | Abed Camarena
00043 |  |  | A - Inadequate Waste Management ATL | Noncompliance Notice | Closed | No Ball in Court | Environmental Situation | 2010-06-17 | Lorri Cullivan | 2010-12-28 12:11 | 15100- Expansion Locks Atlantic | Rick Montanari
00043 |  |  | GQ0047 CAR Implement DQP A13 AFR 07 | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-08-13 | Miguel Tome | 2011-08-17 10:48 | 15000- Expansion Locks | Miguel Tome
00043 |  |  | GQ0071 CAR Weekly Programme Update | Corrective Action Request | Closed | No Ball in Court | Administrative | 2011-06-15 | Maria Ho | 2012-06-05 09:58 | 15000- Expansion Locks | Maria Ho
00042 |  |  | AQ0123 CAR GUPC Audit A-2011-06 | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-02-05 | Karla Jones | 2011-12-01 13:14 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00042 |  |  | PQ0017 NCR Disposal 1 | Nonconformance Report | Closed | Antonio Betti | Construction Deficiency | 2010-06-05 | Maria Ho | 2011-06-09 09:05 | 15200- Expansion Locks Pacific | Maria Ho
00042 |  |  | GQ0046 CAR Implement DQP A13 AFR 06 | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-08-13 | Miguel Tome | 2011-08-17 10:49 | 15000- Expansion Locks | Miguel Tome
00042 |  |  | P - Soil Protection Erosion Control | Noncompliance Notice | Closed | No Ball in Court | Environmental Situation | 2010-06-09 | Lorri Cullivan | 2010-12-28 12:11 | 15200- Expansion Locks Pacific | Lorri Cullivan
00041 |  |  | GQ0045 CAR Implement DQP A13 AFR 05 | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-08-13 | Miguel Tome | 2011-08-17 10:52 | 15000- Expansion Locks | Miguel Tome
01019 |  | NCR RG3 Hatch | A50M0038 NCR RG3 Hatch Frame Out | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-04-11 | Zosimo Correa | 2015-05-23 08:58 | 15100- Expansion Locks Atlantic | Zosimo Correa
00041 |  |  | AQ0122 CAR Audit A-2011-03 QC IMPL | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-02-02 | Karla Jones | 2011-12-01 12:17 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00041 |  |  | D -Audit DQP Chicago 2Jun10 | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-06-08 | Lorri Cullivan | 2010-12-28 12:12 | 15004- Expansion Locks Design | Lorri Cullivan
00040 |  |  | GQ0044 CAR Implement DQP A13 AFR 04 | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-08-13 | Miguel Tome | 2011-08-17 10:53 | 15000- Expansion Locks | Miguel Tome
00040 |  |  | A - Exc Clearance Request Bath | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-06-01 | Lorri Cullivan | 2011-04-11 15:09 | 15100- Expansion Locks Atlantic | Rick Montanari
00040 |  |  | AE8001 NCR Cut trees beyond polygo | Nonconformance Report | Closed | Jeronimo Gutierrez | Environmental Situation | 2011-05-20 | Abed Camarena | 2011-09-29 15:00 | 15100- Expansion Locks Atlantic | Eliza Florendo
00040 |  |  | AQ0121 CAR GUPC Production QC DOC | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-04-25 | Karla Jones | 2011-12-01 12:05 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00039 |  |  | A - Lack Coordinate Employer Bath | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-06-01 | Lorri Cullivan | 2011-04-11 15:08 | 15100- Expansion Locks Atlantic | Rick Montanari
00039 |  |  | GQ0043 CAR Implement DQP A13 AFR 03 | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-08-13 | Miguel Tome | 2011-08-17 10:54 | 15000- Expansion Locks | Miguel Tome
00039 |  |  | AQ0039 NCR Mindi Disposal Dry Beds | Nonconformance Report | Closed | No Ball in Court | Environmental Situation | 2011-05-20 | Karla Jones | 2011-09-01 15:42 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00039 |  |  | AQ0111 CAR Surface Water CTRL & MGT | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2011-01-11 | Karla Jones | 2011-11-30 15:34 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00038 |  |  | AQ0105 CAR Coord Opt Fiber Mont L | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-06-02 | Maria Ho | 2011-09-07 12:50 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00038 |  |  | GQ0042 CAR Implement DQP A13 AFR 02 | Corrective Action Request | Closed | No Ball in Court | Errors and Omissions | 2010-08-13 | Miguel Tome | 2011-08-17 10:55 | 15000- Expansion Locks | Miguel Tome
00038 |  |  | A -Not Communicating Utilities Bath | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-06-01 | Lorri Cullivan | 2011-04-11 15:08 | 15100- Expansion Locks Atlantic | Rick Montanari
00038 |  |  | AQ0038 NCR Curing Comp without appr | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-05-17 | Karla Jones | 2011-09-01 15:39 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00037 |  |  | AQ0037 NCR Grout for Vert Anchors | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-05-16 | Karla Jones | 2011-09-07 15:38 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00037 |  |  | A - ML Earthworks Outside Boundary | Noncompliance Notice | Closed | Jose E. Reyes | Construction Deficiency | 2010-05-25 | Lorri Cullivan | 2010-12-28 12:13 | 15100- Expansion Locks Atlantic | Rick Montanari
00037 |  |  | AQ0104 CAR Fiber Optic Pressure TST | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-11-25 | Karla Jones | 2012-08-06 15:30 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00037 |  |  | GQ0041 CAR Implement DQP A13 AFR 01 | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-08-13 | Miguel Tome | 2011-08-17 10:57 | 15000- Expansion Locks | Miguel Tome
00036 |  |  | A - Concrete Truck Washout Gatun | Noncompliance Notice | Closed | No Ball in Court | Environmental Situation | 2010-05-25 | Lorri Cullivan | 2010-12-28 12:14 | 15100- Expansion Locks Atlantic | Rick Montanari
00036 |  |  | GQ0040 CAR Implement DQP A12 AFR 06 | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-08-03 | Miguel Tome | 2011-08-17 11:05 | 15000- Expansion Locks | Miguel Tome
00036 |  |  | AQ0036 NCR Grout for Hor AnchorsUPC | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-05-16 | Karla Jones | 2011-10-31 14:24 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00036 |  |  | AQ0102 CAR ENV Monitoring Plan PRNR | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-11-22 | Karla Jones | 2011-11-30 13:49 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00035 |  |  | AQ0035 NCR Grout for Hor AnchorsJDC | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-05-16 | Karla Jones | 2011-10-25 15:56 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00035 |  |  | AQ0099 CAR No ITP for WST WTR TREAT | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-11-19 | Karla Jones | 2012-08-03 12:40 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00035 |  |  | GQ0039 CAR Implement DQP A12 AFR 05 | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-08-03 | Miguel Tome | 2012-04-19 14:00 | 15000- Expansion Locks | Miguel Tome
00035 |  |  | P-Testing Laboratory | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-05-24 | Lorri Cullivan | 2010-12-28 12:15 | 15200- Expansion Locks Pacific | Vielka Walters
00034 |  |  | GQ0038 CAR Implement DQP A12 AFR 04 | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-08-03 | Miguel Tome | 2011-08-17 11:10 | 15004- Expansion Locks Design | Miguel Tome
00034 |  |  | PQ0032 NCR Disposal Area 4 | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-05-09 | Luz Arosemena | 2012-09-26 08:46 | 15200- Expansion Locks Pacific | Maria Ho
00034 |  |  | P-Construction Waste Management Pl | Noncompliance Notice | Closed | No Ball in Court | Environmental Situation | 2010-05-17 | Lorri Cullivan | 2010-12-28 12:16 | 15200- Expansion Locks Pacific | Vielka Walters
00034 |  |  | AQ0096 CAR No WPR for sewer lines | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-11-22 | Karla Jones | 2012-08-03 10:48 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00033 |  |  | P-Temporary Drainage | Noncompliance Notice | Closed | Juan H Wong | Construction Deficiency | 2010-05-14 | Lorri Cullivan | 2010-12-28 12:18 | 15200- Expansion Locks Pacific | Vielka Walters
00033 |  |  | AQ0101 CAR Dock 45 West WPR PRNR | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-11-23 | Maria Ho | 2012-08-21 09:14 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00033 |  |  | AQ0034 NCR Fine Aggreg for Lea Conc | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-05-14 | Maria Ho | 2011-08-22 08:40 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00033 |  |  | GQ0037 CAR Implement DQP A12 AFR 03 | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-08-03 | Miguel Tome | 2011-08-17 11:11 | 15000- Expansion Locks | Miguel Tome
00032 |  |  | AQ0032 NCR Mass Conc as Backfil | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-05-13 | Maria Ho | 2011-08-11 11:40 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00032 |  |  | GQ0069 CAR Deficiency Peer Review | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-04-19 | Miguel Tome | 2011-08-17 11:12 | 15004- Expansion Locks Design | Maria Ho
00032 |  |  | P - Temporary Lighting System | Noncompliance Notice | Closed | No Ball in Court | Safety & Health Issue | 2010-05-13 | Alfonso Regis | 2011-06-10 16:11 | 15200- Expansion Locks Pacific | Lorri Cullivan
00032 |  |  | GQ0036 CAR Implement DQP A12 AFR 02 | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-08-03 | Miguel Tome | 2011-08-17 11:13 | 15000- Expansion Locks | Miguel Tome
00031 |  |  | G-Certified CSS Payroll | Noncompliance Notice | Closed | John Lopacki | Administrative | 2010-05-10 | Lorri Cullivan | 2010-12-28 12:19 | 15000- Expansion Locks | Lorri Cullivan
00031 |  |  | AQ0098 CAR WPR Waste Water TREAT PL | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-11-19 | Karla Jones | 2012-08-03 11:52 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00031 |  |  | AQ0031 NCR Galvanized Steel Bar 11 | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-05-13 | Karla Jones | 2011-10-31 16:17 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00031 |  |  | GQ0035 CAR Implent DQP A12 AFR 1 | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-08-03 | Miguel Tome | 2011-08-17 11:14 | 15000- Expansion Locks | Miguel Tome
00030 |  |  | GQ0034 CAR Implement Doc CTL PROCD | Corrective Action Request | Closed | No Ball in Court | Unsafe conditions | 2010-07-26 | Miguel Tome | 2011-08-17 11:17 | 15000- Expansion Locks | Miguel Tome
00030 |  |  | G - Lack of Traffic Control | Noncompliance Notice | Closed | No Ball in Court | Safety & Health Issue | 2010-05-05 | Fatima Garcia | 2011-06-03 08:55 | 15000- Expansion Locks | Lorri Cullivan
00030 |  |  | AQ0030 NCR Rebar No. 14 Properties | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-05-12 | Karla Jones | 2011-09-07 15:35 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00030 |  |  |  | Corrective Action Request | Void | No Ball in Court |  |  | Miguel Tome | 2012-01-11 10:21 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00029 |  |  | GQ0033 CAR Maintain Submittal RGST | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-06-28 | Miguel Tome | 2011-08-17 11:18 | 15000- Expansion Locks | Miguel Tome
00029 |  |  | AQ0078 CAR Monte Lirio Slopes DSR | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-11-26 | Karla Jones | 2011-11-30 14:19 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00029 |  |  | G - Document Control Personnel | Noncompliance Notice | Closed | No Ball in Court | Contract Term | 2010-05-05 | Lorri Cullivan | 2011-03-03 14:46 | 15000- Expansion Locks | Lorri Cullivan
00029 |  |  | AQ0029 NCR Second Supply of Rebars | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-05-05 | Karla Jones | 2011-09-07 15:34 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00028 |  |  | AQ0033 NCR Cement Heat of Hydration | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-05-13 | Miguel Tome | 2011-08-17 13:28 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00028 |  |  | A - Mowing Vegetation Locks Site | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-05-04 | Lorri Cullivan | 2011-04-11 15:08 | 15100- Expansion Locks Atlantic | Rick Montanari
00028 |  |  | AQ0024 CAR Slope Stabilization Plan | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-05-04 | Maria Ho | 2012-08-13 09:34 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00028 |  |  | GQ0032 CAR Programme PROG Update | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-04-23 | Miguel Tome | 2011-08-17 11:18 | 15000- Expansion Locks | Miguel Tome
00027 |  |  | AQ0022 NCR LUC Vertical Anchors- FT | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-02-25 | Karla Jones | 2011-09-01 15:35 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00027 |  |  | GQ0031 CAR Implement DQP A08 AFR 3 | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-07-12 | Miguel Tome | 2011-08-17 11:19 | 15000- Expansion Locks | Miguel Tome
00027 |  |  | A - Slope Stabilization Plan | Noncompliance Notice | Closed | Jose E. Reyes | Construction Deficiency | 2010-05-04 | Rick Montanari | 2011-06-08 14:40 | 15100- Expansion Locks Atlantic | Rick Montanari
00027 |  |  | PQ0011 CAR Audit QC Plan Implement | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2010-07-05 | Veronica Cash | 2013-08-27 15:37 | 15200- Expansion Locks Pacific | Luz Arosemena
00026 |  |  | A - 1939 Excavation Exceeding Limit | Noncompliance Notice | Closed | No Ball in Court | Construction Deficiency | 2010-05-04 | Lorri Cullivan | 2010-12-28 12:20 | 15100- Expansion Locks Atlantic | Rick Montanari
00026 |  |  | PQ0010 CAR AUDIT QMS IMPLEMENTATION | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2010-07-05 | Veronica Cash | 2013-08-27 15:38 | 15200- Expansion Locks Pacific | Luz Arosemena
00026 |  |  | GQ0030 CAR Implement DQP A-08 AFR 2 | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-07-12 | Miguel Tome | 2011-08-17 11:20 | 15000- Expansion Locks | Miguel Tome
00026 |  |  | PQ0031 NCR CONCRETE CURING | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-05-04 | Luz Arosemena | 2011-12-06 11:09 | 15200- Expansion Locks Pacific | Luz Arosemena
00025 |  |  | GQ0029 CAR Implement DQP A08 AFR 01 | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-07-12 | Miguel Tome | 2011-08-17 11:21 | 15000- Expansion Locks | Miguel Tome
00025 |  |  | PQ0030 NCR MAIN COFFERDAM | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-04-30 | Javier Gutierrez | 2012-04-10 15:58 | 15200- Expansion Locks Pacific | Luz Arosemena
00025 |  |  | PQ0009 CAR TESTING LABORATORY | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2010-06-25 | Veronica Cash | 2013-08-27 15:39 | 15200- Expansion Locks Pacific | Luz Arosemena
00025 |  |  | A - Sewage Treatment and Disposal | Noncompliance Notice | Closed | No Ball in Court | Environmental Situation | 2010-05-04 | Lorri Cullivan | 2010-12-28 12:20 | 15100- Expansion Locks Atlantic | Rick Montanari
00024 |  |  | PQ0007 CAR FALL PROTECTION | Corrective Action Request | Closed | Alexandre Neves | Safety & Health Issue | 2010-06-05 | Luz Arosemena | 2011-05-05 11:19 | 15200- Expansion Locks Pacific | Luz Arosemena
00024 |  |  | GQ0028 CAR Vector Control | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-06-16 | Miguel Tome | 2011-08-17 11:22 | 15000- Expansion Locks | Miguel Tome
00024 |  |  | PQ0021 NCR SLOPE STABILITY SYSTEM | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-01-25 | Luz Arosemena | 2012-08-28 13:48 | 15200- Expansion Locks Pacific | Luz Arosemena
00024 |  |  | G - Vector Control | Noncompliance Notice | Closed | No Ball in Court | Safety & Health Issue | 2010-04-29 | Lorri Cullivan | 2010-12-28 12:20 | 15000- Expansion Locks | Lorri Cullivan
00023 |  |  | PQ0005 CAR TEMPORARY DRAINAGE | Corrective Action Request | Closed | NO BIC-GUPC | Construction Deficiency | 2010-05-20 | Veronica Cash | 2013-08-27 15:54 | 15200- Expansion Locks Pacific | Luz Arosemena
00023 |  |  | G -First Aid Facilities | Noncompliance Notice | Closed | Eduardo Shaw | Safety & Health Issue | 2010-04-29 | Lorri Cullivan | 2010-12-28 12:20 | 15000- Expansion Locks | Lorri Cullivan
00023 |  |  | GQ0027 CAR First Aid Facilities | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-06-16 | Miguel Tome | 2011-08-17 11:23 | 15000- Expansion Locks | Miguel Tome
00023 |  |  | PQ0012 NCR REBAR RECEPTION | Nonconformance Report | Closed | Antonio Betti | Contract Term | 2010-12-02 | Luz Arosemena | 2011-04-27 10:47 | 15200- Expansion Locks Pacific | Luz Arosemena
01025 |  | NCRRG6 Hatch Frame 1 | A50M0044 NCRRG6 Hatch Frame 1,3 Out | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-04-13 | Zosimo Correa | 2015-05-25 09:20 | 15100- Expansion Locks Atlantic | Zosimo Correa
00022 |  |  | G -Safety Staff FACPR 30Hour Trng | Noncompliance Notice | Closed | No Ball in Court | Safety & Health Issue | 2010-04-29 | Lorri Cullivan | 2010-12-28 12:20 | 15000- Expansion Locks | Lorri Cullivan
00022 |  |  | PQ0011 NCR SLOPE STABILITY SYSTEM | Nonconformance Report | Closed | Antonio Betti | Construction Deficiency | 2010-12-02 | Luz Arosemena | 2011-04-27 10:27 | 15200- Expansion Locks Pacific | Luz Arosemena
00022 |  |  | PQ0006 CAR CONSTRUCTION WASTE | Corrective Action Request | Closed | Antonio Betti | Environmental Situation | 2010-05-24 | Luz Arosemena | 2011-05-04 16:38 | 15200- Expansion Locks Pacific | Luz Arosemena
00022 |  |  | GQ0021 CAR Certified CSS Payroll | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-05-10 | Miguel Tome | 2011-08-17 11:24 | 15000- Expansion Locks | Miguel Tome
01024 |  | NCR RG6 Hatch Frame | A50M0043 NCR RG6 Hatch Frame 2 Out | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-04-13 | Zosimo Correa | 2015-05-25 09:06 | 15100- Expansion Locks Atlantic | Zosimo Correa
00021 |  |  | GQ0011 CAR Inadequate Soil Protect | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-02-19 | Miguel Tome | 2011-08-17 11:25 | 15000- Expansion Locks | Miguel Tome
00021 |  |  | G -Competent Person(s) | Noncompliance Notice | Closed | No Ball in Court | Safety & Health Issue | 2010-04-29 | Christopher Claggett | 2011-09-14 09:55 | 15000- Expansion Locks | Lorri Cullivan
00021 |  |  | PQ0010 NCR SLOPE STABILITY SYSTEM | Nonconformance Report | Closed | Antonio Betti | Construction Deficiency | 2010-12-02 | Luz Arosemena | 2011-04-27 10:02 | 15200- Expansion Locks Pacific | Luz Arosemena
00021 |  |  | AE8018 CAR Inappropiate Mgmt Waste | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2011-04-06 | Eliza Florendo | 2012-05-21 08:03 | 15100- Expansion Locks Atlantic | Alicia Villalobos
01023 |  | NCRRG5 Hatch Frame 3 | A50M0042 NCRRG5 Hatch Frame 3,4 Out | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-04-13 | Zosimo Correa | 2015-05-25 08:58 | 15100- Expansion Locks Atlantic | Zosimo Correa
00020 |  |  | GQ0026 CAR Safety Staff FACPR | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-06-16 | Miguel Tome | 2011-08-17 12:04 | 15000- Expansion Locks | Miguel Tome
00020 |  |  | PQ0002 NCR SITE PLAN PLAT. PREP. | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2010-06-11 | Maria Ho | 2012-02-15 15:45 | 15200- Expansion Locks Pacific | Luz Arosemena
00020 |  |  | PQ0044 CAR DISPOSAL#4 PREP DOCUMENT | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2011-05-04 | Veronica Cash | 2013-08-27 15:40 | 15200- Expansion Locks Pacific | Luz Arosemena
00020 |  |  | G-Incident Investigation Reports | Noncompliance Notice | Closed | No Ball in Court | Safety & Health Issue | 2010-04-26 | Lorri Cullivan | 2010-12-28 12:23 | 15000- Expansion Locks | Christopher Claggett
01022 |  | NCR RG5 Hatch Frame | A50M0041 NCR RG5 Hatch Frame 1 Out | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-04-13 | Zosimo Correa | 2015-05-23 10:34 | 15100- Expansion Locks Atlantic | Zosimo Correa
00020 |  |  | PE8076 CAR- Lack of Spill Kit etc. | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2015-09-07 | Alicia Villalobos | 2015-09-07 16:33 |  | Alicia Villalobos
00019 |  |  | GQ0068 CAR Updated Drawing List | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2011-04-12 | Miguel Tome | 2011-08-17 12:03 | 15000- Expansion Locks | Miguel Tome
00019 |  |  | GQ0025 CAR Implement DQP A06 AFR 03 | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-06-10 | Miguel Tome | 2011-08-17 12:02 | 15000- Expansion Locks | Miguel Tome
00019 |  |  | PQ0001 NCR NON PROPER DRAINAGES | Nonconformance Report | Closed | Antonio Betti | Construction Deficiency | 2010-03-23 | Luz Arosemena | 2011-04-27 09:10 | 15200- Expansion Locks Pacific | Luz Arosemena
00019 |  |  | G-Weekly Programme Progress Update | Noncompliance Notice | Closed | No Ball in Court | Administrative | 2010-04-23 | Lorri Cullivan | 2010-12-28 12:23 | 15000- Expansion Locks | Lorri Cullivan
00019 |  |  | PE8077 CAR- unattended HC Spills | Corrective Action Request | Closed | Sung Tae Byun | Environmental Situation | 2015-09-04 | Alicia Villalobos | 2015-09-04 11:12 |  | Alicia Villalobos
00019 |  |  | PE8075 CAR- Lack of Spill Kit etc. | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2015-09-07 | Alicia Villalobos | 2015-09-07 15:50 |  | Alicia Villalobos
01021 |  | NCRRG3 Hatch Frame | A50M0040 NCRRG3 Hatch Frame 3 Out | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-04-13 | Zosimo Correa | 2015-05-25 08:41 | 15100- Expansion Locks Atlantic | Zosimo Correa
00018 |  |  | A - GUPC Operations Affect ACP | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-04-16 | Lorri Cullivan | 2011-04-11 15:08 | 15100- Expansion Locks Atlantic | Rick Montanari
00018 |  |  | GQ0024 CAR Implement DQP A06 AFR 2 | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-06-10 | Miguel Tome | 2011-08-17 12:01 | 15000- Expansion Locks | Miguel Tome
00018 |  |  | PQ0004 CAR TEMP. LIGHTING SYSTEM | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-05-13 | Maria Ho | 2011-09-10 09:28 | 15200- Expansion Locks Pacific | Luz Arosemena
00018 |  |  | PQ0018 NCR SLOPE STABILITY SYSTEM | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-01-04 | Maria Ho | 2011-09-10 09:45 | 15200- Expansion Locks Pacific | Luz Arosemena
01020 |  | NCRRG3 Hatch Frame | A50M0039 NCRRG3 Hatch Frame 2 Out | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-04-13 | Zosimo Correa | 2015-05-23 10:03 | 15100- Expansion Locks Atlantic | Zosimo Correa
00018 |  |  | PE8074 CAR- Segr of Haz. Materials | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2015-06-18 | Alicia Villalobos | 2015-09-07 15:43 |  | Alicia Villalobos
00018 |  |  | PE8073 CAR- Lack of Waste Segregati | Corrective Action Request | Closed | Sung Tae Byun | Environmental Situation | 2015-09-04 | Alicia Villalobos | 2015-09-07 15:22 |  | Alicia Villalobos
00017 |  |  | A - Commencement of Works Monte | Noncompliance Notice | Closed | Jose E. Reyes | Quality Mgt Sys | 2010-04-16 | Samuel Santamaría | 2011-02-09 13:29 | 15100- Expansion Locks Atlantic | Rick Montanari
00017 |  |  | PQ0019 NCR SLOPE STABILITY SYSTEM | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-01-07 | Luz Arosemena | 2013-04-11 11:55 | 15200- Expansion Locks Pacific | Luz Arosemena
00017 |  |  | GQ0022 CAR Competent Persons | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-06-05 | Miguel Tome | 2011-08-17 11:49 | 15000- Expansion Locks | Miguel Tome
00017 |  |  | PQ0002 CAR EXCAVATION H&S VIOLATION | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-02-02 | Maria Ho | 2011-09-10 09:30 | 15200- Expansion Locks Pacific | Luz Arosemena
00002 |  | IN E | VOID - GENERATED IN ERROR | Nonconformance Report | Void | Jose Guillot |  | 2015-04-17 | Nayubel Cordoba | 2015-04-18 10:31 |  | Carlos Dominguez
00017 |  |  | PE8072 CAR- Temp Hazmat Storage | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2015-09-04 | Alicia Villalobos | 2015-09-07 15:20 |  | Alicia Villalobos
00017 |  |  | AE8061 CAR Gate paint waste | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2015-03-31 | Mayra Santos | 2016-09-30 09:38 | 15100- Expansion Locks Atlantic | Alicia Villalobos
00016 |  |  | PQ0022 NCR SLOPE STABILITY SYSTEM | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-01-25 | Maria Ho | 2011-09-10 09:28 | 15200- Expansion Locks Pacific | Luz Arosemena
00016 |  |  | PQ0001 CAR CUTTING VEGETATION | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2009-10-07 | Maria Ho | 2011-09-10 09:26 | 15200- Expansion Locks Pacific | Luz Arosemena
00016 |  |  | A - Provide Certified Material Lab | Noncompliance Notice | Closed | Miguel Tome | Quality Mgt Sys | 2010-04-16 | Rick Montanari | 2011-01-04 13:37 | 15100- Expansion Locks Atlantic | Rick Montanari
00016 |  |  | GQ0020 CAR Lack of Traffic Control | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-05-05 | Miguel Tome | 2011-08-17 11:46 | 15000- Expansion Locks | Miguel Tome
00016 |  |  | PM2528 CAR HPU Handling | Corrective Action Request | Closed | NO BIC-GUPC | Other | 2015-08-27 | Lorely Rivera | 2016-07-06 11:38 | 15200- Expansion Locks Pacific | Luz Arosemena
00001 |  | NCR TKP | G75M0001 NCR TKP Elevator Def | Nonconformance Report | Open | Jose Guillot | Errors and Omissions | 2015-04-17 | Roberto Barrios | 2015-12-12 08:04 | 15000- Expansion Locks | Alberto Alonzo
00016 |  |  | VOID - GENERATED IN ERROR | Corrective Action Request | Void | Beltran Valls |  |  | Alicia Villalobos | 2015-04-11 10:57 |  | Alicia Villalobos
00015 |  |  | GQ0019 CAR Doc. Control Personnel | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-05-05 | Miguel Tome | 2011-08-17 11:44 | 15000- Expansion Locks | Miguel Tome
00015 |  |  | PQ0024 NCR BULK EXCAVATION | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-02-14 | Veronica Cash | 2013-08-28 08:28 | 15200- Expansion Locks Pacific | Luz Arosemena
00015 |  |  | A - Start of Work No Released Dwg | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-04-16 | Lorri Cullivan | 2011-04-11 15:07 | 15100- Expansion Locks Atlantic | Rick Montanari
00015 |  |  | PQ0043 CAR DRAWINGS IN THE FIELD | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2011-04-20 | Veronica Cash | 2013-08-27 15:40 | 15200- Expansion Locks Pacific | Luz Arosemena
01007 |  | NCR Valve | P55M0048 NCR Valve Liftin Lug | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-04-18 | Luz Arosemena | 2015-06-15 11:54 | 15200- Expansion Locks Pacific | Luz Arosemena
00015 |  |  | AM2529 CAR RFC Drawings | Corrective Action Request | Open | Roberto Magarotto | Quality Mgt Sys | 2015-01-12 | Gene Williams | 2015-09-04 15:13 | 15100- Expansion Locks Atlantic | Veronica Cash
00015 |  |  | P50M0022 NCR RG7 Ctral Deck C&D RWK | Nonconformance Report | Closed | Roberto Magarotto | Construction Deficiency | 2016-04-09 | Lorely Rivera | 2016-04-09 13:30 | 15200- Expansion Locks Pacific | Lorely Rivera
00015 |  |  | PM2519 CAR HSHI Notify repair | Corrective Action Request | Closed | Sung Tae Byun | Construction Deficiency | 2015-05-06 | Martin Morales | 2016-08-24 08:03 | 15200- Expansion Locks Pacific | Luz Arosemena
00014 |  |  | PQ0041 CAR 1939 EXCAVATION FILL | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-04-05 | Maria Ho | 2011-09-10 09:25 | 15200- Expansion Locks Pacific | Luz Arosemena
00014 |  |  | A - Technical Specifications | Noncompliance Notice | Closed | Bernardo Gonzalez | Quality Mgt Sys | 2010-04-16 | Lorri Cullivan | 2010-12-28 12:24 | 15100- Expansion Locks Atlantic | Rick Montanari
00014 |  |  | GQ0018 CAR Incident Investi Report | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-05-05 | Miguel Tome | 2011-08-17 11:43 | 15000- Expansion Locks | Miguel Tome
00014 |  |  | PQ0025 NCR FOUNDATION TREATMENT | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-03-04 | Maria Ho | 2011-09-10 09:21 | 15200- Expansion Locks Pacific | Luz Arosemena
00014 |  |  | P50M0018 NCR RG4 | Nonconformance Report | New Item | Roberto Magarotto |  | 2016-04-08 | Lorely Rivera | 2016-04-08 13:56 | 15200- Expansion Locks Pacific | Lorely Rivera
00014 |  |  | GM2521 CAR HSH Missing SA & QR | Corrective Action Request | Closed | NO BIC-GUPC | Administrative | 2014-09-20 | Alberto Alonzo | 2014-12-09 14:43 | 15000- Expansion Locks | Alberto Alonzo
00014 |  |  | AM2528 CAR Qualific of pers. LG | Corrective Action Request | Open | Roberto Magarotto | Quality Mgt Sys | 2015-01-12 | Gene Williams | 2015-09-04 15:02 | 15100- Expansion Locks Atlantic | Veronica Cash
01026 |  | MRB5 Steel | AQ0474 NCR MRB5 Steel Structure DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-04-22 | Mayra Santos | 2016-05-14 09:41 | 15100- Expansion Locks Atlantic | Zosimo Correa
00013 |  |  | GQ0064 CAR PIO DQP Impleme A7 AFR02 | Corrective Action Request | Closed | No Ball in Court | Administrative | 2011-04-08 | Miguel Tome | 2011-08-17 11:42 | 15004- Expansion Locks Design | Miguel Tome
00013 |  |  | PQ0027 NCR SLOPE STABILITY | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-04-08 | Luz Arosemena | 2012-05-01 14:52 | 15200- Expansion Locks Pacific | Luz Arosemena
00013 |  |  | G-Monthly As Built Drawings | Noncompliance Notice | Closed | No Ball in Court | Administrative | 2010-04-15 | Lorri Cullivan | 2011-05-16 10:53 | 15000- Expansion Locks | John Lopacki
00013 |  |  | VOID | Corrective Action Request | Void | Willmar Muller |  |  | Miguel Tome | 2011-04-14 13:49 |  | Miguel Tome
00013 |  |  | GM2515 CAR HSH Con Vlv Seal Dim | Corrective Action Request | Approved | Sung Tae Byun | Construction Deficiency | 2014-04-03 | Juan Rivera | 2014-07-16 19:23 | 15000- Expansion Locks | Alberto Alonzo
00013 |  |  | AM2527 CAR Field Test. Elect System | Corrective Action Request | Open | Roberto Magarotto | Quality Mgt Sys | 2015-01-12 | Gene Williams | 2015-09-04 14:59 | 15100- Expansion Locks Atlantic | Veronica Cash
01029 |  | NCR RG4 G7039 Out | A50M0047 NCR RG4 G7039 Out of Tol | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-05-04 | Zosimo Correa | 2015-10-21 11:41 | 15100- Expansion Locks Atlantic | Zosimo Correa
01028 |  | NCR RG3 G7039 Out | A50M0046 NCR RG3 G7039 Out of tol | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-05-04 | Zosimo Correa | 2015-10-21 11:43 | 15100- Expansion Locks Atlantic | Zosimo Correa
00012 |  |  | GQ0067 CAR PIO Design Impl A7 AFR05 | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2011-04-08 | Maria Ho | 2011-09-27 15:52 | 15000- Expansion Locks | Miguel Tome
00012 |  |  | PQ0028 NCR SLOPE STABILITY | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-03-18 | Luz Arosemena | 2012-05-01 14:59 | 15200- Expansion Locks Pacific | Luz Arosemena
00012 |  |  | GQ0015 CAR Drawing Log | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-04-15 | Miguel Tome | 2011-08-17 11:41 | 15000- Expansion Locks | Miguel Tome
00012 |  |  | G-Insufficient Detail for Programme | Noncompliance Notice | Closed | No Ball in Court | Administrative | 2010-04-15 | Miguel Tome | 2011-05-11 08:17 | 15000- Expansion Locks | John Lopacki
00012 |  |  | AM2520 CAR Removal of TRANS lugs | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2014-08-02 | Gene Williams | 2015-09-04 14:58 | 15100- Expansion Locks Atlantic | Zosimo Correa
01027 |  | NCR RG6 G7039 Out | A50M0045 NCR RG6 G7039 Out of tol | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-05-04 | Zosimo Correa | 2015-10-21 11:19 | 15100- Expansion Locks Atlantic | Zosimo Correa
01030 |  | NCR Road Blocker | A85M0001 NCR Road Blocker Inst DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-05-25 | Zosimo Correa | 2015-08-14 11:12 | 15100- Expansion Locks Atlantic | Zosimo Correa
00012 |  |  | PM2511 Valves Handling and Unload | Corrective Action Request | Closed | Sung Tae Byun | Defective Materials | 2014-01-17 | Juan Rivera | 2014-10-12 14:45 | 15200- Expansion Locks Pacific | Martin Duran
00011 |  |  | GQ0066 CAR PIO Design Imp. A7 AFR04 | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-04-08 | Maria Ho | 2011-08-08 12:02 | 15000- Expansion Locks | Miguel Tome
00011 |  |  | GQ0014 CAR Intermediate DSGN Gate | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-05-24 | Miguel Tome | 2011-08-17 11:39 | 15000- Expansion Locks | Miguel Tome
00011 |  |  | G-DTCS Current Drawing Log | Noncompliance Notice | Closed | No Ball in Court | Administrative | 2010-04-15 | Lorri Cullivan | 2010-12-28 12:25 | 15000- Expansion Locks | John Lopacki
00011 |  |  | PQ0029 NCR SLOPE STABILITY | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-04-07 | Luz Arosemena | 2012-04-10 16:57 | 15200- Expansion Locks Pacific | Luz Arosemena
01031 |  | Valve leakage | P55M0049 Valve leakage SSE OOT | Nonconformance Report | Void | No Ball in Court | Construction Deficiency | 2015-05-30 | Tamira Baird | 2015-09-07 08:36 |  | Lorely Rivera
00011 |  |  | GM2510 CAR HSH MQP Handl & Stor | Corrective Action Request | Closed | NO BIC-GUPC | Other | 2013-11-02 | Alberto Alonzo | 2014-05-21 16:13 | 15000- Expansion Locks | Alberto Alonzo
01032 |  | MCB | NCRP0482CS MCB Floor Truss | Nonconformance Report | Closed | Juan Arturo Rivera | Construction Deficiency | 2015-06-01 | Lorely Rivera | 2015-09-08 14:44 | 15200- Expansion Locks Pacific | Lorely Rivera
00011 |  |  | AM2505 CAR Cimolai Install. Doc. | Corrective Action Request | Closed | No Ball in Court |  | 2013-06-20 | Abdiel Santos | 2014-05-26 11:58 | 15100- Expansion Locks Atlantic | Martin Duran
00010 |  |  | A - No Ministry Lic Nuclear Testing | Noncompliance Notice | Closed | No Ball in Court | Safety & Health Issue | 2010-04-07 | Lorri Cullivan | 2010-12-28 12:26 | 15100- Expansion Locks Atlantic | Rick Montanari
00010 |  |  | PQ0016 NCR TEMP. CLAY STOCKPILE | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-04-05 | Maria Ho | 2011-09-10 09:20 | 15200- Expansion Locks Pacific | Luz Arosemena
00010 |  |  | GQ0013 CAR Implementation of Doc. | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-04-05 | Miguel Tome | 2011-08-17 11:38 | 15000- Expansion Locks | Miguel Tome
00010 |  |  | GQ0065 CAR PIO Design Impl A7 AFR03 | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-04-08 | Maria Ho | 2011-08-22 15:15 | 15000- Expansion Locks | Miguel Tome
00010 |  |  | GM2505 CAR CIM System Ass Plan | Corrective Action Request | Closed | Roberto Magarotto | Contract Term | 2013-06-03 | Carlos Dominguez | 2015-05-06 16:33 | 15000- Expansion Locks | Alberto Alonzo
01014 |  | NCR Valve | P55M0047 NCR Valve Nylon Washer | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-06-02 | Lorely Rivera | 2015-12-09 15:26 | 15200- Expansion Locks Pacific | Lorely Rivera
00010 |  |  | GQ0105 CAR Revision Reason | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2013-04-24 | Veronica Cash | 2016-08-05 11:21 | 15200- Expansion Locks Pacific | Boris Vergara
01013 |  | NCR Valve leakage | P55M0049 NCR Valve leakage SSE OOT | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-06-02 | Lorely Rivera | 2015-12-09 15:25 | 15200- Expansion Locks Pacific | Lorely Rivera
00010 |  |  | PM2509 CAR Documents Control | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2013-09-26 | Luz Arosemena | 2015-07-15 16:17 | 15200- Expansion Locks Pacific | Martin Duran
00009 |  |  | GQ0063 CAR PIO Design Imple A7 AFR1 | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2011-04-08 | Miguel Tome | 2011-08-17 11:35 | 15000- Expansion Locks | Miguel Tome
00009 |  |  | PQ0009 NCR BASALT STOCKPILE | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-04-05 | Luz Arosemena | 2012-02-08 14:31 | 15200- Expansion Locks Pacific | Luz Arosemena
00009 |  |  | A - Work Proceeds No Re Submittal | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-04-07 | Lorri Cullivan | 2011-04-11 15:07 | 15100- Expansion Locks Atlantic | Rick Montanari
00009 |  |  | GQ0012 CAR REQ. for Clarification | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-03-05 | Miguel Tome | 2011-08-17 11:34 | 15000- Expansion Locks | Miguel Tome
01033 |  | WSB1 | NCRP0483CS WSB1 Bottom Liners | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2015-06-03 | Lorely Rivera | 2015-08-14 11:45 | 15200- Expansion Locks Pacific | Lorely Rivera
01034 |  | PBR6& PBR7W01 | AQ0468 NCR PBR6& PBR7W01 Consol def | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-06-04 | Abdiel Santos | 2016-12-05 15:23 | 15100- Expansion Locks Atlantic | Zosimo Correa
00009 |  |  | VOID | Corrective Action Request | Void | NO BIC-GUPC | Contract Term | 2013-02-04 | Tamira Baird | 2015-09-07 08:38 |  | Maria Ho
00009 |  |  | GM2507 CAR HSH SYP HPU | Corrective Action Request | Closed | NO BIC-GUPC | Administrative | 2013-06-21 | Alberto Alonzo | 2014-05-21 16:10 | 15000- Expansion Locks | Alberto Alonzo
00009 |  |  | PQ0091 CAR Borinquen Dam EMBK | Corrective Action Request | Closed | NO BIC-GUPC | Construction Deficiency | 2013-04-11 | Gene Williams | 2015-09-04 14:54 | 15200- Expansion Locks Pacific | Veronica Cash
00008 |  |  | GQ0061 CAR Valve DQP A05 AFR01 | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-04-04 | Maria Ho | 2011-08-29 13:26 | 15000- Expansion Locks | Miguel Tome
00008 |  |  | PQ0007 NCR TEMP. CLAY STOCKPILE | Nonconformance Report | Closed | Antonio Betti | Construction Deficiency | 2011-03-31 | Luz Arosemena | 2011-04-04 08:03 | 15200- Expansion Locks Pacific | Luz Arosemena
00008 |  |  | GQ0010 CAR Monthly Report Req. | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-02-02 | Miguel Tome | 2011-08-17 11:33 | 15000- Expansion Locks | Miguel Tome
00008 |  |  | A - Preparatory Meeting Cofferdam | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-04-07 | Lorri Cullivan | 2011-04-11 15:07 | 15100- Expansion Locks Atlantic | Rick Montanari
00008 |  |  | PM2539 CAR Eaton Missing Installati | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2015-11-12 | Veronica Cash | 2016-08-22 11:38 | 15200- Expansion Locks Pacific | Roberto Barrios
00008 |  |  | PQ0090 CAR Borinquen Dam EMBK | Corrective Action Request | Closed | NO BIC-GUPC | Construction Deficiency | 2013-04-11 | Gene Williams | 2015-09-04 14:51 | 15200- Expansion Locks Pacific | Veronica Cash
01035 |  | AGG Base GRAD out | AQ0469 NCR AGG Base GRAD out of tol | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2015-06-18 | Abdiel Santos | 2016-12-05 15:29 | 15100- Expansion Locks Atlantic | Zosimo Correa
00008 |  |  | GM2506 CAR HSH SYP HPU | Corrective Action Request | Closed | Sung Tae Byun | Quality Mgt Sys | 2013-01-24 | Alberto Alonzo | 2014-05-21 16:09 | 15004- Expansion Locks Design | Alberto Alonzo
01036 |  | Riprap Outlet | NCRP0484CS Riprap Outlet Ocean Side | Nonconformance Report | Open | Samuel Cohen | Construction Deficiency | 2015-06-19 | Lorely Rivera | 2016-11-15 09:05 | 15200- Expansion Locks Pacific | Lorely Rivera
00008 |  |  |  | Corrective Action Request | Void | NO BIC-GUPC | Contract Term |  | Veronica Cash | 2014-02-03 09:47 |  | Maria Ho
00007 |  |  | GQ0057 CAR QMS Doc. Schedule | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-10-27 | Maria Ho | 2011-08-01 15:30 | 15000- Expansion Locks | Miguel Tome
00007 |  |  | A - Haul Road Crossed Fiber Optic | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-04-07 | Lorri Cullivan | 2011-04-11 15:07 | 15100- Expansion Locks Atlantic | Rick Montanari
00007 |  |  | GQ0009 CAR Inspection Check List | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-02-02 | Miguel Tome | 2011-08-17 11:32 | 15000- Expansion Locks | Miguel Tome
00007 |  |  | PQ0005 NCR ROOF SLAB FAILURE | Nonconformance Report | Closed | Antonio Betti | Construction Deficiency | 2011-03-31 | Luz Arosemena | 2011-04-04 08:03 | 15200- Expansion Locks Pacific | Luz Arosemena
00007 |  |  | GQ0101 CAR Thermal Monitoring Model | Corrective Action Request | Closed | NO BIC-GUPC | Administrative | 2012-12-04 | Veronica Cash | 2013-08-27 14:48 | 15000- Expansion Locks | Maria Ho
00007 |  |  | PM2537 CAR Eaton Changes of Equipme | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2015-10-29 | Veronica Cash | 2016-08-22 11:26 | 15200- Expansion Locks Pacific | Roberto Barrios
01037 |  | MRB UL pipes | AQ0470 NCR MRB UL pipes not INS | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-06-29 | Zosimo Correa | 2015-12-21 14:34 | 15100- Expansion Locks Atlantic | Zosimo Correa
01040 |  | T2&T1 | AQ0475 NCR T2&T1 Missing Kickers | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-07-03 | Abdiel Santos | 2016-12-05 15:34 | 15100- Expansion Locks Atlantic | Zosimo Correa
00007 |  |  | PM2505 CAR Packing Valves & App | Corrective Action Request | Closed | NO BIC-GUPC | Errors and Omissions | 2013-01-17 | Martin Duran | 2013-12-03 10:50 | 15200- Expansion Locks Pacific | Alberto Alonzo
01039 |  | NCR CER Steel | A40B0001 NCR CER Steel Paint DEF | Nonconformance Report | Open | Beltran Valls | Construction Deficiency | 2015-07-03 | Marta Small | 2015-08-28 07:50 | 15100- Expansion Locks Atlantic | Zosimo Correa
00007 |  |  | GM2504 CAR CIM Coating System | Corrective Action Request | Closed | NO BIC-GUPC | Defective Materials | 2012-10-18 | Roberto Barrios | 2016-07-04 16:47 | 15000- Expansion Locks | Alberto Alonzo
00006 |  |  | A - Protection of Electric Utility | Noncompliance Notice | Closed | No Ball in Court | Quality Mgt Sys | 2010-04-07 | Lorri Cullivan | 2011-04-11 15:06 | 15100- Expansion Locks Atlantic | Rick Montanari
00006 |  |  | GQ0008 CAR Subcontractor Compliance | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-02-02 | Miguel Tome | 2011-08-17 11:31 | 15000- Expansion Locks | Miguel Tome
00006 |  |  | PQ0003 NCR PERMANENT DISPOSAL # 1 | Nonconformance Report | Closed | Antonio Betti | Construction Deficiency | 2011-03-26 | Luz Arosemena | 2014-06-24 14:19 | 15200- Expansion Locks Pacific | Miguel Tome
00006 |  |  | GQ0056 CAR QMS Management Review | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2010-10-27 | Maria Ho | 2012-08-02 10:16 | 15000- Expansion Locks | Miguel Tome
00006 |  |  | GM2503 CAR CIM Welding Deficiency | Corrective Action Request | Closed | NO BIC-GUPC | Construction Deficiency | 2012-06-20 | Roberto Barrios | 2016-07-04 16:46 | 15000- Expansion Locks | Maria Ho
01038 |  | NCR CER2-I Without | A40B0002 NCR CER2-I Without QMS INS | Nonconformance Report | Open | Beltran Valls | Construction Deficiency | 2015-07-03 | Zosimo Correa | 2015-07-03 11:12 | 15100- Expansion Locks Atlantic | Zosimo Correa
01042 |  | MRBs | NCRP0486CS MRBs Welding Works | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2015-07-07 | Lorely Rivera | 2016-03-31 08:20 | 15200- Expansion Locks Pacific | Luz Arosemena
00006 |  |  | PM2536 CAR Eaton Missing Instal | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2015-10-28 | Veronica Cash | 2016-08-22 11:31 | 15200- Expansion Locks Pacific | Roberto Barrios
00006 |  |  | AQ0209 CAR FLP Audit Findings | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2015-04-13 | Zosimo Correa | 2015-07-15 16:05 | 15100- Expansion Locks Atlantic | Zosimo Correa
00006 |  |  | AM2502 CAR Packing Valves & APP | Corrective Action Request | Closed | NO BIC-GUPC | Errors and Omissions | 2013-01-17 | Juan Rivera | 2014-02-27 22:07 | 15100- Expansion Locks Atlantic | Alberto Alonzo
01041 |  | MRB | NCRP0485CS MRB Transformers Found | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2015-07-07 | Lorely Rivera | 2015-10-26 16:23 | 15200- Expansion Locks Pacific | Luz Arosemena
00006 |  |  | GQ0098 CAR Concrete Specification | Corrective Action Request | Closed | No Ball in Court | Administrative | 2012-12-04 | Veronica Cash | 2013-04-10 17:13 | 15000- Expansion Locks | Maria Ho
00005 |  |  | P - Safety - NNC - Fall Protection | Noncompliance Notice | Closed | No Ball in Court | Safety & Health Issue | 2010-03-19 | Lorri Cullivan | 2010-12-28 12:28 | 15200- Expansion Locks Pacific | Christopher Claggett
00005 |  |  | AQ0017 NCR 1st SUPPLY REINF. REBARS | Nonconformance Report | Closed | No Ball in Court | Quality Mgt Sys | 2011-03-25 | Karla Jones | 2011-09-07 15:31 | 15100- Expansion Locks Atlantic | Miguel Tome
00005 |  |  | GQ0016 CAR ISFC detail for Program | Corrective Action Request | Closed | No Ball in Court | Planned | 2010-04-15 | Miguel Tome | 2011-08-17 11:29 | 15000- Expansion Locks | Miguel Tome
00005 |  |  | GQ0007 CAR Fuel Hdng M & E Maint | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-02-02 | Miguel Tome | 2011-08-17 11:30 | 15000- Expansion Locks | Miguel Tome
00005 |  |  | AQ0161 CAR - Cyl Concrete Specimens | Corrective Action Request | Closed | NO BIC-GUPC | Construction Deficiency | 2013-07-08 | Veronica Cash | 2013-08-29 09:46 | 15100- Expansion Locks Atlantic | Veronica Cash
00005 |  |  | PM2504 CAR Sill Beam Install LUC | Corrective Action Request | Closed | NO BIC-GUPC | Errors and Omissions | 2012-11-14 | Luz Arosemena | 2015-07-15 16:09 | 15200- Expansion Locks Pacific | Alberto Alonzo
00005 |  |  | GQ0084 CAR Lack of the CIM ICL's | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2012-04-27 | Maria Ho | 2012-08-09 09:23 | 15000- Expansion Locks | Maria Ho
01044 |  | NCR FER2 F6,5,4 | A40B0004 NCR FER2 F6,5,4,3 Cracks | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-07-10 | Armando Quintero | 2016-05-18 13:56 | 15100- Expansion Locks Atlantic | Zosimo Correa
01043 |  | NCR FER1 F01,02,03 | A40B0003 NCR FER1 F01,02,03,04 CRKS | Nonconformance Report | Open | Ramon Porcell | Construction Deficiency | 2015-07-10 | Larry Ohrn | 2015-07-16 08:36 | 15100- Expansion Locks Atlantic | Zosimo Correa
00005 |  |  | GQ0095 CAR Thermal Analysis | Corrective Action Request | Closed | NO BIC-GUPC | Administrative | 2012-12-04 | Gene Williams | 2015-09-04 14:47 | 15004- Expansion Locks Design | Maria Ho
00001 |  | NCR Cable | P92M0001 NCR Cable Jacket Damaged | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2015-07-18 | Lorely Rivera | 2015-12-28 15:56 | 15200- Expansion Locks Pacific | Luz Arosemena
00005 |  |  | PM2529 CAR EATON RG5 Incident QMS | Corrective Action Request | Closed | Carlos Perez | Quality Mgt Sys | 2015-08-27 | Martin Morales | 2016-08-19 10:21 | 15200- Expansion Locks Pacific | Luz Arosemena
01051 |  | NCR BCB | A40B0011 NCR BCB Topping DEF | Nonconformance Report | Open | Beltran Valls | Construction Deficiency | 2015-07-22 | Zosimo Correa | 2015-07-22 16:22 | 15100- Expansion Locks Atlantic | Zosimo Correa
00005 |  |  | AQ0007 NCR Disposing material | Nonconformance Report | Closed | No Ball in Court | Environmental Situation | 2010-11-12 | Karla Jones | 2011-09-07 15:25 | 15100- Expansion Locks Atlantic | Maria Ho
00004 |  |  | AQ0024 NCR Reloc 44kV Found Concret | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2011-02-26 | Maria Ho | 2011-11-18 14:30 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00004 |  |  | D - Physical Model Filling & Empty | Noncompliance Notice | Closed | No Ball in Court | Contract Term | 2010-03-12 | Lorri Cullivan | 2010-12-28 12:28 | 15004- Expansion Locks Design | John Lopacki
00004 |  |  | GQ0006 CAR Erosion Control Measures | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-02-02 | Miguel Tome | 2011-08-17 11:28 | 15000- Expansion Locks | Miguel Tome
00004 |  |  | AQ0002 CAR CONTROL OF SURVEY INST | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2010-02-24 | Maria Ho | 2011-09-14 09:28 | 15100- Expansion Locks Atlantic | Karla Jones
00004 |  |  | AE8035 CAR Lack of Hazardous Labels | Corrective Action Request | Closed | Sung Tae Byun | Environmental Situation | 2012-07-30 | Gene Williams | 2015-09-04 14:39 | 15100- Expansion Locks Atlantic | Adrian Lee
00004 |  |  | PE8060 CAR - Prod Labels/Ware Issue | Corrective Action Request | Closed | Hernan Vargas | Environmental Situation | 2012-12-02 | Gene Williams | 2015-09-04 14:41 | 15200- Expansion Locks Pacific | Gonzalo Menendez
00004 |  |  | PM2525 CAR SAT - QMS Documentation | Corrective Action Request | Closed | Carlos Perez | Quality Mgt Sys | 2015-08-26 | Ian Barria | 2016-09-07 14:20 | 15200- Expansion Locks Pacific | Luz Arosemena
00004 |  |  | GQ0094 CAR Thermal MNT Calculation | Corrective Action Request | Closed | NO BIC-GUPC | Administrative | 2012-12-04 | Veronica Cash | 2013-08-28 13:48 | 15000- Expansion Locks | Maria Ho
00004 |  |  | GQ0093 CAR FLP ACI Certification | Corrective Action Request | Closed | NO BIC-GUPC | Contract Term | 2012-10-09 | Veronica Cash | 2013-08-27 15:56 | 15100- Expansion Locks Atlantic | Maria Ho
01050 |  | NCR CB | A40B0010 NCR CB Topping DEF | Nonconformance Report | Open | Beltran Valls | Construction Deficiency | 2015-07-22 | Zosimo Correa | 2015-07-22 16:11 | 15100- Expansion Locks Atlantic | Zosimo Correa
01049 |  | NCR MRB8 | A40B0009 NCR MRB8 Topping DEF | Nonconformance Report | Open | Beltran Valls | Construction Deficiency | 2015-07-22 | Zosimo Correa | 2015-07-22 15:39 | 15100- Expansion Locks Atlantic | Zosimo Correa
01048 |  | NCR MRB7 | A40B0008 NCR MRB7 topping DEF | Nonconformance Report | Open | Beltran Valls | Construction Deficiency | 2015-07-22 | Zosimo Correa | 2015-07-22 15:23 | 15100- Expansion Locks Atlantic | Zosimo Correa
01047 |  | NCR MRB6 | A40B0007 NCR MRB6 Topping DEF | Nonconformance Report | Open | Beltran Valls | Construction Deficiency | 2015-07-22 | Zosimo Correa | 2015-07-22 13:58 | 15100- Expansion Locks Atlantic | Zosimo Correa
00004 |  |  | PQ0101 CAR MB Column Repair | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2014-04-22 | Luz Arosemena | 2015-07-14 11:13 | 15200- Expansion Locks Pacific | Luz Arosemena
00004 |  |  | GQ0083 CAR Lack of NCR's Control | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2012-04-27 | Maria Ho | 2012-08-08 16:43 | 15000- Expansion Locks | Maria Ho
00004 |  |  | PQ0084 CAR Grout Courtain Test 1W | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2013-02-26 | Veronica Cash | 2013-08-27 15:41 | 15200- Expansion Locks Pacific | Luz Arosemena
00004 |  |  | AQ0006 NCR Landslides at ML Slopes | Nonconformance Report | Closed | No Ball in Court | Field Conditions | 2010-11-26 | Veronica Cash | 2013-08-28 08:22 | 24016- Slope Protection and Erosion Control | Maria Ho
01046 |  | NCR MRB4 | A40B0006 NCR MRB4 Topping DEF | Nonconformance Report | Open | Beltran Valls | Construction Deficiency | 2015-07-22 | Marta Small | 2015-08-28 07:49 | 15100- Expansion Locks Atlantic | Zosimo Correa
00003 |  |  | PQ0040 CAR MAIN COFFERDAM | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2011-03-31 | Luz Arosemena | 2011-12-16 15:35 | 15200- Expansion Locks Pacific | Luz Arosemena
00003 |  |  | A - Inadequate Soil Protect Measure | Noncompliance Notice | Closed | No Ball in Court | Environmental Situation | 2010-02-12 | Lorri Cullivan | 2010-12-28 12:29 | 15100- Expansion Locks Atlantic | Vielka Walters
00003 |  |  | G55M0002 NCR HSH Clv Lnr Ship 1 | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2011-02-21 | Alberto Alonzo | 2013-06-03 13:37 | 15000- Expansion Locks | Samuel Santamaría
00003 |  |  | GQ0005 CAR Job Description | Corrective Action Request | Closed | No Ball in Court | Environmental Situation | 2010-02-02 | Miguel Tome | 2011-08-17 11:27 | 15000- Expansion Locks | Miguel Tome
00003 |  |  | GQ0082 CAR Def in CIM QLTY Records | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2012-04-27 | Maria Ho | 2012-08-08 16:44 | 15000- Expansion Locks | Maria Ho
01045 |  | NCR MRB2 | A40B0005 NCR MRB2 Topping DEF | Nonconformance Report | Open | Beltran Valls | Construction Deficiency | 2015-07-22 | Zosimo Correa | 2015-07-22 14:11 | 15100- Expansion Locks Atlantic | Zosimo Correa
00003 |  |  | GQ0090 CAR Updated DRW List Def | Corrective Action Request | Closed | No Ball in Court | Administrative | 2012-08-15 | Maria Ho | 2013-02-25 14:08 | 15000- Expansion Locks | Miguel Tome
00003 |  |  | PM2523 CAR Lack QMS Documentation | Corrective Action Request | Closed | Carlos Perez | Construction Deficiency | 2015-05-12 | Ian Barria | 2016-09-07 14:27 | 15200- Expansion Locks Pacific | Luz Arosemena
00003 |  |  | GM2522 CAR Indra Quality Records Ou | Corrective Action Request | Closed | Imanol Esteban Ramajo | Quality Mgt Sys | 2015-10-29 | Roberto Barrios | 2016-06-10 15:36 | 15000- Expansion Locks | Roberto Barrios
00003 |  |  | PM2538 CAR Sampol Changes of Equipm | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2015-10-29 | Veronica Cash | 2016-09-30 14:07 | 15200- Expansion Locks Pacific | Roberto Barrios
00003 |  |  |  | Corrective Action Request | Void | No Ball in Court |  | 2014-04-22 | Luz Arosemena | 2014-06-06 11:03 |  | Luz Arosemena
00003 |  |  | AQ0005 NCR Contaminating Material | Nonconformance Report | Closed | No Ball in Court | Environmental Situation | 2010-08-19 | Karla Jones | 2011-09-07 15:22 | 15100- Expansion Locks Atlantic | Maria Ho
8002 |  |  | VOID | Noncompliance Notice | Void | Jose Pelaez |  |  | Maria Ho | 2012-03-31 10:29 |  | Karla Jones
00003 |  |  | PQ0083 CAR BDam 1W WIR Process | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-10-22 | Luz Arosemena | 2013-10-09 11:19 | 15200- Expansion Locks Pacific | Luz Arosemena
01052 |  | CB Steel Welds not | A40B0012 CB Steel Welds not in comp | Nonconformance Report | Open | Ramon Porcell | Construction Deficiency | 2015-07-25 | Zosimo Correa | 2015-09-07 09:38 | 15100- Expansion Locks Atlantic | Zosimo Correa
00003 |  |  | PE8037 CAR Operation Permits | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2011-11-17 | Gene Williams | 2015-09-04 14:12 | 15200- Expansion Locks Pacific | Eliza Florendo
01053 |  | LH1 & LH4 Outer | AQ0471 NCR LH1 & LH4 Outer slot DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-08-04 | Zosimo Correa | 2015-12-21 14:10 | 15100- Expansion Locks Atlantic | Zosimo Correa
00003 |  |  | PM2502 CAR Culvert Liner Install | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2012-05-16 | Juan Rivera | 2014-02-27 22:16 | 15200- Expansion Locks Pacific | Alberto Alonzo
01054 |  | NCR Gates D700 & | A50M0054 NCR Gates D700 & D800 Fail | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2015-08-07 | Abdiel Santos | 2015-08-07 14:57 | 15100- Expansion Locks Atlantic | Abdiel Santos
00003 |  |  | GM2514 CAR SGS Insp Services | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2013-12-23 | Alberto Alonzo | 2014-05-21 16:17 | 15000- Expansion Locks | Erick Briceño
00003 |  |  | PE8040CAR Flamm prod not adqt stord | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2011-11-19 | Gene Williams | 2015-09-04 14:11 | 15200- Expansion Locks Pacific | Josimar Torrero
01056 |  | NCR EMH | P90M0001 NCR EMH-44KV Deficiencies | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2015-08-19 | Lorely Rivera | 2016-06-21 16:45 | 15200- Expansion Locks Pacific | Lorely Rivera
00003 |  |  | PE8013 CAR - TrevG Mech Maintenance | Corrective Action Request | Closed | Roberto Galante | Environmental Situation | 2010-11-02 | Gene Williams | 2015-09-04 14:07 | 15200- Expansion Locks Pacific | Gonzalo Menendez
00003 |  |  | PE8039CAR Required PPE | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2011-12-03 | Gene Williams | 2015-09-04 14:09 | 15200- Expansion Locks Pacific | Josimar Torrero
01055 |  | LH3C Large | NCRP0487CS LH3C Large Seepage Cond | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2015-08-19 | Lorely Rivera | 2016-06-17 17:15 | 15200- Expansion Locks Pacific | Lorely Rivera
00002 |  |  | GQ0001 CAR Deficient Daily Report | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2010-01-12 | Miguel Tome | 2011-08-17 11:26 | 15000- Expansion Locks | Miguel Tome
00002 |  |  | D - Design Quality Plan Not Submit | Noncompliance Notice | Closed | No Ball in Court | Administrative | 2010-01-25 | Lorri Cullivan | 2010-12-28 12:29 | 15004- Expansion Locks Design | John Lopacki
00002 |  |  | AQ0001 NCR Haul Road Crossed FO | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2010-04-13 | Miguel Tome | 2011-08-17 13:24 | 15100- Expansion Locks Atlantic | McLaren Brennan
00002 |  |  | AQ0113 CAR Slope stabil Cond 2 LUC | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2011-01-18 | Karla Jones | 2012-11-01 14:43 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00002 |  |  | PE8016 CAR Trevi HC storage | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2010-11-02 | Gene Williams | 2015-09-04 15:22 | 15200- Expansion Locks Pacific | Josimar Torrero
00002 |  |  | GQ0081 CAR Lack of Issuance the MQP | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2012-04-27 | Maria Ho | 2012-08-08 16:19 | 15000- Expansion Locks | Maria Ho
00002 |  |  | VOID | Corrective Action Request | Void | Alex Monzo | Quality Mgt Sys | 2013-11-25 | Veronica Cash | 2013-11-25 15:07 |  | Veronica Cash
01057 |  | UE-M03 | NCRP0488CS UE-M03 Capstan Damaged | Nonconformance Report | Closed | Juan Arturo Rivera | Construction Deficiency | 2015-08-20 | Lorely Rivera | 2016-04-07 17:35 | 15200- Expansion Locks Pacific | Lorely Rivera
00002 |  |  | PQ0071 CAR Reinf. Steel Grade 60 | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2012-06-02 | Luz Arosemena | 2012-06-15 10:48 | 15200- Expansion Locks Pacific | Luz Arosemena
00002 |  |  | GM2512 CAR ETN Syst Ass Plan | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2013-11-29 | Alberto Alonzo | 2014-05-21 16:15 | 15000- Expansion Locks | Alberto Alonzo
00002 |  |  | PQ0082 CAR BDam 1W Traceability | Corrective Action Request | Closed | No Ball in Court | Construction Deficiency | 2012-10-22 | Luz Arosemena | 2013-09-21 08:38 | 15200- Expansion Locks Pacific | Luz Arosemena
00002 |  |  | GQ0092 CAR Truck of POZZ CONTAMINED | Corrective Action Request | Closed | No Ball in Court | Administrative | 2012-08-17 | Maria Ho | 2013-02-21 14:27 | 15000- Expansion Locks | Maria Ho
01008 |  | NCR HPU damaged | P55M0050 NCR HPU damaged at MRB4 | Nonconformance Report | Closed | Sung Tae Byun | Construction Deficiency | 2015-08-26 | Maria Elena Navarro | 2016-05-26 15:00 | 15200- Expansion Locks Pacific | Luz Arosemena
8001 |  |  | VOID | Noncompliance Notice | Void | No Ball in Court |  |  | Luz Arosemena | 2011-06-22 09:07 |  | Luz Arosemena
00002 |  |  | PE8033 CAR Lack train HARSCO staf | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2011-09-28 | Tamira Baird | 2015-09-04 15:17 | 15200- Expansion Locks Pacific | Josimar Torrero
01058 |  | NCR RG01 UW End | A50M0030 NCR RG01 UW End Stop Dama | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2015-09-01 | Tamira Baird | 2015-09-04 13:25 | 15100- Expansion Locks Atlantic | Zosimo Correa
01059 |  | Access Roads | AQ0476 NCR Access Roads MH covered | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-09-03 | Mayra Santos | 2016-03-09 09:39 | 15100- Expansion Locks Atlantic | Zosimo Correa
00002 |  |  | GM2518 CAR IND Storage Conditions | Corrective Action Request | Closed | NO BIC-GUPC | Administrative | 2014-04-02 | Alberto Alonzo | 2014-05-21 16:21 | 15000- Expansion Locks | Alberto Alonzo
01060 |  | NCR RG D800 US Leak | A50M0056 NCR RG D800 US Leak and J | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2015-09-14 | Zosimo Correa | 2015-11-19 09:02 | 15100- Expansion Locks Atlantic | Abdiel Santos
01061 |  | NCR MRB1-4 HVAC | A40B0013 NCR MRB1-4 HVAC Fire Damp | Nonconformance Report | Open | Alvaro Herrero | Construction Deficiency | 2015-09-15 | Zosimo Correa | 2015-09-15 16:28 |  | Zosimo Correa
00002 |  |  | PQ0100 CAR MB Steel Str. Erection | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2014-04-21 | Luz Arosemena | 2015-07-14 11:08 | 15200- Expansion Locks Pacific | Luz Arosemena
8000 |  |  |  | Noncompliance Notice | Void | Jeronimo Gutierrez |  |  | Alicia Villalobos | 2011-06-11 08:12 |  | Abed Camarena
00002 |  |  | PE8036 CAR Fueling Procedure | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2012-02-23 | Tamira Baird | 2015-09-04 15:16 | 15200- Expansion Locks Pacific | Eliza Florendo
01122 |  | LWSB-B-RP Road | AQ0477 NCR LWSB-B-RP Road Slab Fail | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2015-09-22 | Abdiel Santos | 2016-12-07 10:02 | 15100- Expansion Locks Atlantic | Abdiel Santos
00002 |  |  | GM2500 CAR Shipment Deficiencies | Corrective Action Request | Closed | NO BIC-GUPC | Contract Term | 2012-02-18 | Alberto Alonzo | 2013-06-03 14:14 | 15000- Expansion Locks | Maria Ho
00002 |  |  | VOID - GENERATED IN ERROR | Corrective Action Request | Void | Jair Rozo |  | 2015-10-23 | Nayubel Cordoba | 2015-10-29 15:37 |  | Lorely Rivera
01085 |  | NCR RG4 GBS pads out | A50M0059 NCR RG4 GBS pads out of to | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2015-10-03 | Tamira Baird | 2016-02-02 11:49 | 15100- Expansion Locks Atlantic | Tamira Baird
00002 |  |  | AQ0004 NCR UNSUITABLE FILL CLAY | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2010-06-07 | Karla Jones | 2011-09-07 15:21 | 15100- Expansion Locks Atlantic | Maria Ho
00352 |  |  | VOID | Noncompliance Notice | Void | NO BIC-GUPC |  |  | Luz Arosemena | 2016-06-01 10:14 | 00000- Other | Lorely Rivera
01077 |  | NCR RG5 GBS pads out | A50M0052 NCR RG5 GBS pads out of to | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2015-10-03 | Richard Barrow | 2015-12-15 16:42 | 15100- Expansion Locks Atlantic | Richard Barrow
00002 |  |  | PM2530 CAR SAMPOL - MPP MH Racks | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2015-09-15 | Lorely Rivera | 2016-07-08 09:54 | 15200- Expansion Locks Pacific | Marta Small
01076 |  | NCR RG8 GBS pads out | A50M0051 NCR RG8 GBS pads out of to | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2015-10-03 | Richard Barrow | 2015-12-15 16:19 | 15100- Expansion Locks Atlantic | Richard Barrow
00002 |  |  | GQ0072 CAR Design Change Management | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-09-08 | Maria Ho | 2012-08-24 09:41 | 15000- Expansion Locks | Maria Ho
00002 |  |  | AQ0188 CAR Logisfer Shop Drawings | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2014-06-17 | Gene Williams | 2015-09-04 14:16 | 15100- Expansion Locks Atlantic | Veronica Cash
00002 |  |  | PECAR8041 Addit without sec contain | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2011-11-19 | Gene Williams | 2015-09-04 14:18 | 15200- Expansion Locks Pacific | Josimar Torrero
00001 |  |  | AQ0118 CAR Geotech DWG Not Stamped | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2011-02-07 | Miguel Tome | 2011-08-17 14:45 | 15100- Expansion Locks Atlantic | Javier Gutierrez
00001 |  |  | G55M0001 NCR HSH FSE Length Dev | Nonconformance Report | Closed | NO BIC-GUPC | Defective Materials | 2011-02-21 | Alberto Alonzo | 2014-05-21 15:34 | 15000- Expansion Locks | Miguel Tome
00001 |  |  | PQ0003 CAR DRAWINGS WITHOUT STAMP | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2010-03-12 | Luz Arosemena | 2014-06-24 14:14 | 15200- Expansion Locks Pacific | Luz Arosemena
00001 |  |  | GQ0023 CAR Implementation DQP AFR 1 | Noncompliance Notice | Closed | No Ball in Court | Contract Term | 2010-06-10 | Miguel Tome | 2011-08-17 11:26 | 15000- Expansion Locks | Miguel Tome
00001 |  |  | AQ0001 CAR Total Station Calibrate | Corrective Action Request | Closed | No Ball in Court | Administrative | 2010-02-24 | Maria Ho | 2012-10-09 09:16 | 15100- Expansion Locks Atlantic | McLaren Brennan
00001 |  |  | A - Citizen Participate Plan Impl | Noncompliance Notice | Closed | No Ball in Court | Administrative | 2009-12-22 | Lorri Cullivan | 2010-12-28 12:29 | 15100- Expansion Locks Atlantic | Mario Montemayor
01075 |  | NCR RG7 GBS pads out | A50M0050 NCR RG7 GBS pads out of to | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2015-10-03 | Richard Barrow | 2015-12-15 15:54 | 15100- Expansion Locks Atlantic | Richard Barrow
01066 |  | NCR RG3 GBS pads out | A50M0055 NCR RG3 GBS pads out of t | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2015-10-03 | Richard Barrow | 2015-11-02 16:24 |  | Richard Barrow
00001 |  |  | AM2541 CAR Auditel Missing Installa | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2015-11-12 | Mayra Santos | 2016-06-07 13:53 | 15100- Expansion Locks Atlantic | Roberto Barrios
00283 |  |  |  | Noncompliance Notice | Void | Kurt Zwanenepoel |  |  | Lorely Rivera | 2014-07-08 08:36 |  | Lorely Rivera
00001 |  |  | GM2513 CAR SMC Design Submittals | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2013-11-29 | Alberto Alonzo | 2014-05-21 16:16 | 15000- Expansion Locks | Alberto Alonzo
01065 |  | NCR RG6 GBS pads out | A50M0053 NCR RG6 GBS pads out of to | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2015-10-03 | Richard Barrow | 2015-11-02 16:24 | 15100- Expansion Locks Atlantic | Richard Barrow
00001 |  |  | GM2511 CAR ETN Inspection Notice | Corrective Action Request | Closed | NO BIC-GUPC | Administrative | 2013-11-15 | Alberto Alonzo | 2014-05-21 16:14 | 15000- Expansion Locks | Alberto Alonzo
00001 |  |  | PM2520 CAR QMS Documentation | Corrective Action Request | Closed | Sergio Garcia | Quality Mgt Sys | 2015-05-12 | Ian Barria | 2016-09-07 14:36 | 15200- Expansion Locks Pacific | Luz Arosemena
00001 |  | Functionality | TMB PCM Functionality test 20151004 | Nonconformance Report | Closed | Tamira Baird | Safety & Health Issue | 2015-10-04 | Tamira Baird | 2015-10-04 12:25 | 15100- Expansion Locks Atlantic | Tamira Baird
00001 |  |  | PM2507 CAR Inspection of PWS | Corrective Action Request | Closed | NO BIC-GUPC |  | 2013-08-23 | Juan Rivera | 2014-02-27 22:17 | 15200- Expansion Locks Pacific | Martin Duran
00001 |  |  | PQ0042 CAR Failure to test concrete | Corrective Action Request | Closed | No Ball in Court | Administrative | 2011-12-17 | Luz Arosemena | 2011-12-17 11:36 | 15200- Expansion Locks Pacific | Luz Arosemena
00001 |  |  | GQ0060 CAR CICP DQ Process A06-AFR3 | Corrective Action Request | Closed | No Ball in Court | Contract Term | 2011-04-04 | Maria Ho | 2011-09-10 09:16 | 15000- Expansion Locks | Maria Ho
00001 |  |  | PE8032 CAR - Lack Env Ind - HARSCO | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2011-09-28 | Tamira Baird | 2015-09-04 15:15 | 15200- Expansion Locks Pacific | Eliza Florendo
01062 |  | Road | NCRP0491CS Road Blocker Embedments | Nonconformance Report | Concluded | Juan Arturo Rivera | Construction Deficiency | 2015-10-07 | Lorely Rivera | 2016-05-03 16:05 | 15200- Expansion Locks Pacific | Lorely Rivera
00001 |  |  | P91M0001 NCR MCC Retest | Nonconformance Report | Closed | Javier Garcia |  | 2016-05-10 | Lorely Rivera | 2016-12-03 11:19 | 15200- Expansion Locks Pacific | Maria Elena Navarro
01063 |  | Large seepage | NCRP0492CS Large seepage cond LH2C | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2015-10-15 | Lorely Rivera | 2016-06-17 17:18 | 15200- Expansion Locks Pacific | Lorely Rivera
00001 |  |  | GM2502 CAR FSE Inst. Cimolai Repr | Corrective Action Request | Closed | NO BIC-GUPC | Contract Term | 2012-03-01 | Alberto Alonzo | 2014-05-21 16:06 | 15000- Expansion Locks | Juan Rivera
00002 |  |  |  | Noncompliance Notice | Void | NO BIC-GUPC |  |  | Karlos Azuz | 2015-02-05 10:22 |  | Karlos Azuz
00001 |  |  | PE8035 CAR Lack of Env. Induction | Corrective Action Request | Closed | Luis Wang | Environmental Situation | 2011-11-17 | Martin Morales | 2016-08-19 10:28 | 15200- Expansion Locks Pacific | Eliza Florendo
01064 |  | NCR MCB | P40M0001 NCR MCB Faraday Cage | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2015-10-16 | Lorely Rivera | 2016-04-05 17:46 | 15200- Expansion Locks Pacific | Lorely Rivera
00001 |  |  | PQ0078 CAR QMS Process on site | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2012-07-27 | Luz Arosemena | 2013-09-21 08:29 | 15200- Expansion Locks Pacific | Luz Arosemena
00001 |  |  | AQ0003 NCR Clear & Grubbing OPS | Nonconformance Report | Closed | No Ball in Court | Roadway Conditions | 2010-04-23 | Karla Jones | 2011-09-07 15:19 | 15100- Expansion Locks Atlantic | Maria Ho
00001 |  |  | PM2535 EIASA | Corrective Action Request | Closed | Jair Rozo | Quality Mgt Sys | 2015-10-23 | Veronica Cash | 2016-09-22 11:24 | 15200- Expansion Locks Pacific | Lorely Rivera
00001 |  |  | AQ0035A CAR Accidents/Incident Rept | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-05-27 | Maria Ho | 2012-08-21 09:52 | 15100- Expansion Locks Atlantic | Maria Ho
00001 |  |  | GM2519 CAR TKP Prep Docs | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2014-07-19 | Alberto Alonzo | 2014-12-11 15:57 | 15000- Expansion Locks | Alberto Alonzo
00001 |  |  |  | Noncompliance Notice | Void | Sung Tae Byun | Defective Materials |  | Juan Rivera | 2013-07-04 12:55 | 00000- Other | Juan Rivera
00001 |  |  | PM2546 CAR Lack of QC Selex | Corrective Action Request | Closed | NO BIC-GUPC |  | 2016-05-09 | Lorely Rivera | 2016-07-06 11:15 | 15200- Expansion Locks Pacific | Maria Elena Navarro
00001 |  |  | PE8014CAR Proc for hydroc spill | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2010-11-02 | Tamira Baird | 2015-09-04 15:14 | 15200- Expansion Locks Pacific | Josimar Torrero
00001 |  |  | PQ0097 CAR Doval Shop Drawings | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2013-11-25 | Samuel Santamaría | 2014-06-09 10:20 | 15200- Expansion Locks Pacific | Veronica Cash
01068 |  | Curb Road 217 out | AQ0480 NCR Curb Road 217 out of tol | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-11-12 | Mayra Santos | 2016-03-09 10:30 | 15100- Expansion Locks Atlantic | Mayra Santos
00001 |  |  | PM2500 CAR Clvrt Lnr Coating Insp | Corrective Action Request | Closed | NO BIC-GUPC | Errors and Omissions | 2011-11-12 | Juan Rivera | 2014-02-27 22:18 | 15200- Expansion Locks Pacific | Maria Ho
00001 |  |  | AQ0054 CAR JDN/CUSA Workshop DEF | Corrective Action Request | Closed | No Ball in Court | Safety & Health Issue | 2010-07-19 | Maria Ho | 2012-08-14 09:55 | 15100- Expansion Locks Atlantic | Karla Jones
01067 |  | Curb Road 214 out | AQ0479 NCR Curb Road 214 out of tol | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-11-12 | Mayra Santos | 2016-03-09 09:58 | 15100- Expansion Locks Atlantic | Mayra Santos
01070 |  | Underdrain pipes | AQ0481 NCR Underdrain pipes UWS DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-11-23 | Mayra Santos | 2016-05-14 10:01 | 15100- Expansion Locks Atlantic | Zosimo Correa
01069 |  | NCR RG7 GBS pads out | A50M0050 NCR RG7 GBS pads out of to | Nonconformance Report | Open | Javier Barrera | Construction Deficiency | 2015-11-23 | Zosimo Correa | 2015-11-23 10:02 | 15100- Expansion Locks Atlantic | Zosimo Correa
01073 |  | Underdrain pipes | AQ0484 NCR Underdrain pipes UWS DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-12-03 | Mayra Santos | 2016-05-14 10:40 | 15100- Expansion Locks Atlantic | Zosimo Correa
01072 |  | Underdrain pipes | AQ0483 NCR Underdrain pipes UWS DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-12-03 | Mayra Santos | 2016-05-14 10:29 | 15100- Expansion Locks Atlantic | Zosimo Correa
01071 |  | Underdrain pipes | AQ0482 NCR Underdrain pipes UWS DE | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-12-03 | Mayra Santos | 2016-05-14 10:17 | 15100- Expansion Locks Atlantic | Zosimo Correa
00001 |  |  | PQ0119 CAR Panel Installation RFC | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2015-05-15 | Luz Arosemena | 2015-07-15 16:32 | 15200- Expansion Locks Pacific | Luz Arosemena
00001 |  |  | GQ0106 CAR Technical Specifications | Corrective Action Request | Closed | NO BIC-GUPC |  | 2013-06-28 | Gene Williams | 2015-09-04 15:03 | 15004- Expansion Locks Design | Veronica Cash
00012 |  | NCR Gates Paint | P50M0004 NCR Gates Paint Defects RG | Nonconformance Report | Closed | NO BIC-GUPC | Construction Deficiency | 2015-12-03 | Juan Rivera | 2015-12-23 12:50 | 15200- Expansion Locks Pacific | Lorely Rivera
00001 |  |  | GQ0091 CAR DEF Values of Loss IGN | Corrective Action Request | Closed | No Ball in Court | Administrative | 2012-08-17 | Maria Ho | 2013-02-21 14:21 | 15000- Expansion Locks | Maria Ho
01074 |  | NCR FPS | P67M0001 NCR FPS Surface Treatment | Nonconformance Report | Open | Karel Dewaele | Construction Deficiency | 2015-12-15 | Lorely Rivera | 2015-12-15 16:25 | 15200- Expansion Locks Pacific | Lorely Rivera
01078 |  | NCR SSE Corrosion | P55M0051 NCR SSE Corrosion Syst Def | Nonconformance Report | Concluded | Juan Arturo Rivera | Construction Deficiency | 2015-12-21 | Lorely Rivera | 2016-04-02 10:06 | 15200- Expansion Locks Pacific | Lorely Rivera
01080 |  | Underdrain pipes | AQ0487 NCR Underdrain pipes MWS DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-12-28 | Mayra Santos | 2016-05-14 11:07 | 15100- Expansion Locks Atlantic | Zosimo Correa
00001 |  |  | GM2508 CAR IMC WPR ITP | Corrective Action Request | Closed | NO BIC-GUPC | Administrative | 2013-06-21 | Alberto Alonzo | 2014-05-21 16:11 | 15000- Expansion Locks | Alberto Alonzo
01079 |  | Underdrain pipes | AQ0485 NCR Underdrain pipes UWS DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency | 2015-12-28 | Mayra Santos | 2016-05-14 10:55 | 15100- Expansion Locks Atlantic | Zosimo Correa
00001 |  |  | PE8030 CAR Lack of Operation Permit | Corrective Action Request | Closed | NO BIC-GUPC | Environmental Situation | 2012-01-25 | Luis Villarreal | 2013-10-17 10:45 | 15200- Expansion Locks Pacific | Eliza Florendo
00001 |  |  | GM2517 CAR IND Shipment w/out SA-1 | Corrective Action Request | Closed | Imanol Esteban Ramajo | Administrative | 2014-04-02 | Samuel Santamaría | 2014-07-28 16:52 | 15000- Expansion Locks | Alberto Alonzo
00573 |  |  |  | Nonconformance Report | Void | No Ball in Court |  |  | Alberto Alonzo | 2012-08-14 16:31 |  | Alberto Alonzo
00001 |  |  | PQ0056 CAR Rebar Intallation Seq. | Corrective Action Request | Closed | NO BIC-GUPC | Quality Mgt Sys | 2011-10-15 | Veronica Cash | 2013-08-27 15:42 | 15200- Expansion Locks Pacific | Luz Arosemena
00001 |  |  | AQ0177 CAR Technical Specification | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2013-12-13 | Abdiel Santos | 2014-06-05 13:48 | 15100- Expansion Locks Atlantic | Veronica Cash
00001 |  |  | AQ0173 CAR Manufact Metallic Struct | Corrective Action Request | Closed | No Ball in Court | Quality Mgt Sys | 2013-11-22 | Abdiel Santos | 2014-07-15 09:12 | 15100- Expansion Locks Atlantic | Veronica Cash
00572 |  |  |  | Nonconformance Report | Void | No Ball in Court | Contract Term |  | Alberto Alonzo | 2012-08-14 16:32 |  | Alberto Alonzo
00571 |  |  |  | Nonconformance Report | Void | No Ball in Court |  |  | Alberto Alonzo | 2012-08-14 16:32 |  | Alberto Alonzo
00567 |  |  |  | Nonconformance Report | Void | No Ball in Court |  |  | Juan Rivera | 2013-07-04 12:54 | 00000- Other | Alberto Alonzo
00565 |  |  |  | Nonconformance Report | Void | No Ball in Court |  |  | Alberto Alonzo | 2012-08-14 16:28 |  | Alberto Alonzo
00431 |  | LE-M13-F03 REB | AQ0231 NCR LE-M13-F03 REB INST DEF | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency |  | Karla Jones | 2012-04-18 14:31 | 15100- Expansion Locks Atlantic | Karla Jones
00247 |  |  |  | Nonconformance Report | Closed | No Ball in Court | Construction Deficiency |  | Karla Jones | 2012-01-27 13:55 | 15100- Expansion Locks Atlantic | Karla Jones
00041 |  |  |  | Nonconformance Report | Void | Antonio Betti |  |  | Maria Ho | 2011-05-30 10:27 |  | Maria Ho
00013 |  |  | Void | Nonconformance Report | Void | NO BIC-GUPC | Construction Deficiency |  | Lorely Rivera | 2016-06-27 16:41 | 15200- Expansion Locks Pacific | Lorely Rivera
00001 |  |  |  | Nonconformance Report | Void | NO BIC-GUPC |  |  | Alberto Alonzo | 2014-05-08 14:02 |  | Alberto Alonzo
00001 |  |  |  | Nonconformance Report | Void | Roy Williams |  |  | Juan Rivera | 2013-07-04 12:54 | 00000- Other | Ariel Jaen